## Document Guide
UNDERSTANDING THIS DOCUMENT
PURPOSE: | This document lists all upcoming Track Possessions for the ARTC Interstate Network. The document contains multiple worksheets that break down the full listing into their respective states for ease of reading. If there are any information conflicts, refer to the 'All Possessions' sheet
PUBLISHER: | The Interstate Possesisons Team maintain the Interstate Possessions Calendar (this document) and are the contatct point for any questions or enquiries relating to the document. Email: interstatepossessions@artc.com.au
REQUEST STATUS | Each Request listed is assigned a status depending on its progression through the approval process. Approved: The track possession will proceed as planned. Supported: The possession request has been endorsed for approval by the ARTC business unit, subject to ongoing stakeholder feedback. Pending: The possession request is still subject to ongoing review and has not yet been endorsed by the ARTC business unit Cancelled: A previously listed possession that will not proceed
IMPACT RATINGS | 1 | A track possession where both passenger and freight services are impacted by a possession that: • Impacts services scheduled to operate through the network where there are service cancellations, or • is a track possession that exceeds a duration of 10 continuous hours in length. Adhoc trains are not able to operate through the affected area.
| 2 | A track possession where mandatory freight & passenger services are impacted in a way that they require a temporary path variation: • to alter the route of a planned service, or • the timings of the planned service. A track possession that requires the implementation of a method of special working (e.g. Pilot Staff Working), or, bidirectional working, to continue to operate services – limiting available network capacity. Adhoc trains are generally not able to operate through the affected area, unless allowed by exception
| 3 | A track possession where mandatory freight services are not impacted, and the possession window is approved “Clear of mandatory services” only. Passenger services are not impacted. Adhoc trains are not able to operate through the affected area. A track possession taken on a Crossing Loop or Siding, that may affect overall network capacity or provide a service to a load point.
| 4 | A track possession where the timings of passenger and mandatory freight services are not impacted. Adhoc trains may not be able to operate through the affected area, subject to path availability.
| 5 | A track possession that is approved to operate As Traffic Permits, that does not restrict the operation of the network.
| 6 | Reserved for the use for scheduling Special Events, Additional trains, Ultrasonic Testing & other information relevant to the Annual Possession Plan
| 1P | A track possession where passenger services are impacted in a way that they require either: • major path variation, • commence/terminate short at stations, or • cancellation. Where mandatory freight services can run with a temporary variation to the MTP, and/or diverted to another route. Adhoc trains are not able to operate through the affected area.
| 1F | A Special Event occurring where freight services are impacted in a way that may require either: • temporary path variation, or • cancellation. And, where additional passenger services are provided to service the event. These are included in the annual possession plan to avoid the scheduling of a track possession during a major event, and, to prevent cumulative impacts along the path of a planned service. Adhoc trains may not be able to operate through the affected area, subject to path availability.

## ARTC IS - All Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Possession Limits | Safeworking Requirements | Date Submitted
IPR-2324-1667 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Bordertown | Keith | Mainline | 2023-11-24 07:00 | 2023-11-24 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1256 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main line | 2023-11-24 07:30 | 2023-11-24 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1536 | 2023-09-25 | Cancelled |  |  | 1 | Total Possession | Wagga Wagga | Bomen | Main | 2023-11-25 05:30 | 2023-11-25 13:00 | 7:30 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Possession Impacts 9331 (Cancel or Lift 70") & 7MW7 (Delay 4.5 hours) | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-1668 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Wirrega | Coombe | Mainline | 2023-11-25 07:00 | 2023-11-25 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1257 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-25 07:30 | 2023-11-25 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1748 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-25 08:00 | 2023-11-25 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-548 | 2022-12-20 | Approved | 1366-2023 | 2023-11-10 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-11-25 11:00 | 2023-11-25 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-66 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2023-11-25 22:00 | 2023-11-26 06:00 | 8:00 | ARTC MARL UTX Installation | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-410 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-11-26 00:05 | 2023-11-26 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1537 | 2023-09-25 | Cancelled |  |  | 1 | Total Possession | Wagga Wagga | Bomen | Main | 2023-11-26 05:30 | 2023-11-26 11:30 | 6:00 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Possession Impacts 7SM2 (delay 3.5hrs & 7WM7 (Delay 1 hour) | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-1754 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-26 06:00 | 2023-11-26 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1669 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Keith | Coonalpyn | Mainline | 2023-11-26 07:00 | 2023-11-26 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1258 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-26 07:30 | 2023-11-26 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1749 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-26 09:00 | 2023-11-26 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-1538 | 2023-09-25 | Cancelled |  |  | 3 | Window Possession | Wagga Wagga | Bomen | Main | 2023-11-27 05:30 | 2023-11-27 13:00 | 7:30 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Windows between MTP Services | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-1533 | 2023-09-22 | Approved | 1419-2023 | 2023-11-10 | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2023-11-27 06:00 | 2023-12-16 18:00 | 468:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2023-09-12
IPR-2324-1755 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-27 06:00 | 2023-11-27 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1670 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Tintinara | Coonalpyn | Mainline | 2023-11-27 07:00 | 2023-11-27 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1703 | 2023-10-25 | Approved | 1517-2023 | 2023-11-10 | 3 | Window Possession | Newport | Manor Loop | Mainline | 2023-11-27 07:00 | 2023-11-27 18:00 | 11:00 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Adhoc Traffic | Bryce Gore | Chan Sarai |  |  | 2023-10-23
IPR-2324-1259 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main line | 2023-11-27 07:30 | 2023-11-27 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1462 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-11-27 13:00 | 2023-11-27 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1413 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-11-27 16:00 | 2023-11-27 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1756 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-28 06:00 | 2023-11-28 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1671 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Coonalpyn | Tailem Bend | Mainline | 2023-11-28 07:00 | 2023-11-28 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1260 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-28 07:30 | 2023-11-28 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1610 | 2023-09-25 | Approved | 1485-2023 | 2023-11-03 | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2023-11-28 14:00 | 2023-11-28 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-09-20
IPR-2324-1704 | 2023-10-25 | Cancelled | 1517-2023 | 2023-11-10 | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-11-29 02:15 | 2023-11-29 07:45 | 5:30 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-10-23
IPR-2324-1757 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-29 06:00 | 2023-11-29 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1261 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-29 07:30 | 2023-11-29 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1672 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Coomandook | Murray Bridge | Mainline | 2023-11-29 08:00 | 2023-11-29 17:00 | 9:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1758 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-11-30 06:00 | 2023-11-30 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1679 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-11-30 07:00 | 2023-11-30 15:00 | 8:00 | Pt Bonython Rd LX Upgrade | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1673 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Murray Bridge | Mount Barker | Mainline | 2023-11-30 07:20 | 2023-11-30 17:30 | 10:10 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1262 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-30 07:30 | 2023-11-30 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1759 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-01 06:00 | 2023-12-01 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1680 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-01 07:00 | 2023-12-01 13:00 | 6:00 | Pt Bonython Rd LX Upgrade | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1263 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-12-01 07:30 | 2023-12-01 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1674 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Mount Barker | Mount Lofty | Mainline | 2023-12-01 08:00 | 2023-12-01 17:00 | 9:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-20 | 2022-07-26 | Approved | 1454-2023 | 2023-11-17 | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2023-12-02 02:30 | 2023-12-03 22:30 | 44:00 | Config-16 | North - South | Moss Vale to Unanderra | WE23 ​Closedown LPA | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-1760 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-02 06:00 | 2023-12-02 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-549 | 2022-12-20 | Approved | 1453-2023 | 2023-11-17 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-02 11:00 | 2023-12-02 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-638 | 2023-06-26 | Approved | 1511-2023 | 2023-11-09 | 2 | Total Possession | Snowtown | Redhill | Mainline | 2023-12-02 21:00 | 2023-12-03 11:00 | 14:00 | Underbridge Replacement 159.065km | East - West | Dry Creek to Crystal Brook | ​​No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-1982 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-02 21:30 | 2023-12-03 05:30 | 8:00 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-2324-67 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2023-12-02 22:00 | 2023-12-03 06:00 | 8:00 | ARTC MARL UTX Installation | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-411 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-03 00:05 | 2023-12-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1761 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-03 06:00 | 2023-12-03 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-639 | 2023-04-26 | Approved | 1511-2023 | 2023-11-09 | 2 | Window Possession | Snowtown | Redhill | Mainline | 2023-12-03 23:00 | 2023-12-04 05:00 | 6:00 | Underbridge Replacement 159.065km | East - West | Dry Creek to Crystal Brook | ​No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-1733 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 06:00 | 2023-12-04 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1691 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-04 07:00 | 2023-12-04 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1622 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-04 07:30 | 2023-12-04 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1734 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 10:30 | 2023-12-04 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1463 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-04 13:00 | 2023-12-04 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1735 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 14:00 | 2023-12-04 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1414 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-04 16:00 | 2023-12-04 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1736 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 06:00 | 2023-12-05 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1692 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-05 07:00 | 2023-12-05 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1623 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-05 07:30 | 2023-12-05 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1593 | 2023-09-25 | Cancelled | 1313-2023 |  | 3 | Window Possession | Snowtown | Redhill | Main Line | 2023-12-05 09:20 | 2023-12-05 13:40 | 4:20 | Level Crossing Upgrade | North - South | Dry Creek to Crystal Brook | Level Crossing Upgrade - Lake View Road - 162.288kmNO Ad Hoc Services | Bryce Gore | Jessica Tai | Snowtown 24 Sig (146.586km) to Redhill 3 Sig (170.926km) |  | 2023-09-21
IPR-2324-1737 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 10:30 | 2023-12-05 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1738 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 13:00 | 2023-12-05 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1693 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-06 07:00 | 2023-12-06 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1716 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-06 07:00 | 2023-12-06 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1624 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-06 07:30 | 2023-12-06 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1681 | 2023-10-25 | Approved | 1535-2023 | 2023-11-21 | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-07 07:00 | 2023-12-07 15:00 | 8:00 | Pt Bonython Rd LX Upgrade and ATMS HiRail Testing | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1694 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-07 07:00 | 2023-12-07 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1717 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-07 07:00 | 2023-12-07 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1625 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-07 07:30 | 2023-12-07 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1682 | 2023-10-25 | Approved | 1535-2023 | 2023-11-21 | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-08 07:00 | 2023-12-08 13:00 | 6:00 | Pt Bonython Rd LX Upgrade and ATMS HiRail Testing | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1695 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-08 07:00 | 2023-12-08 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1731 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-08 07:00 | 2023-12-08 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1626 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-08 07:30 | 2023-12-08 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-1983 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-09 00:01 | 2023-12-09 07:30 | 7:29 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-1824 | 2023-10-05 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-09 06:00 | 2023-12-09 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-05
IPR-2324-1696 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-09 07:00 | 2023-12-09 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1721 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-09 07:00 | 2023-12-09 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-550 | 2022-12-20 | Approved | 1458-2023 | 2023-11-17 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-09 11:00 | 2023-12-09 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-1264 | 2023-07-24 | Cancelled |  |  | 2 | Total Possession | South Dynon | Sims St Jct | Main Line | 2023-12-09 22:30 | 2023-12-10 07:00 | 8:30 | DYN157, DYN155 and DYN Mixed Gauge Diamond Works | East - West | Melbourne Metro | ​No Train Period - Extension to Sunday morning Maintenance Window | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-412 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-10 00:05 | 2023-12-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1636 | 2023-10-05 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-10 06:00 | 2023-12-10 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-05
IPR-2324-1697 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-10 07:00 | 2023-12-10 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1719 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-10 07:00 | 2023-12-10 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1637 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-11 06:00 | 2023-12-15 18:00 | 108:00 | Level Crossing Upgrades and Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period for continuous 5 day shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1649 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-11 06:00 | 2023-12-15 18:00 | 108:00 | Re-Sleepering | North - South | Benalla to Oakland Line | Total 5 Day Shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1739 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 06:00 | 2023-12-11 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1698 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-11 07:00 | 2023-12-11 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1720 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-11 07:00 | 2023-12-11 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1629 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-11 07:30 | 2023-12-11 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1740 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 10:30 | 2023-12-11 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1464 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-11 13:00 | 2023-12-11 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IP-2324-1596 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2023-12-11 13:00 | 2023-12-11 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1741 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 14:00 | 2023-12-11 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1415 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-11 16:00 | 2023-12-11 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1762 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-12 03:30 | 2023-12-12 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1584 | 2023-09-25 | Approved | 1312-2023 | 2023-11-22 | 2 | Total Possession | Coombe | Coombe | Main Line | 2023-12-12 05:30 | 2023-12-12 13:30 | 8:00 | Turnout Renewal | East - West | Serviceton to Islington (SA) | No Train Period 12 Pts (228.770km) Turnout Renewal. New V-Xing & Timbers - Was 5th Dec | Bryce Gore | Bonnar Mahains | Coombe Signals 14 & 15 to Coombe 16 |  | 2023-09-21
IPR-2324-1742 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 06:00 | 2023-12-12 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1699 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-12 07:00 | 2023-12-12 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1722 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-12 07:00 | 2023-12-12 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1630 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-12 07:30 | 2023-12-12 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1743 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 10:30 | 2023-12-12 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1744 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 13:00 | 2023-12-12 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1585 | 2023-09-25 | Approved | 1312-2023 | 2023-11-22 | 2 | Total Possession | Coombe | Coombe | Main Line | 2023-12-12 14:30 | 2023-12-12 19:00 | 4:30 | Turnout Renewal | East - West | Serviceton to Islington (SA) | 12 Pts (228.770km) Turnout Renewal. New V-Xing & Timbers - Was 5th Dec Ad-Hoc services only permitted with Project Approval at least 3 days prior to start | Bryce Gore | Bonnar Mahains | Coombe Signals 14 & 15 to Coombe 16 |  | 2023-09-21
IPR-2324-1763 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-13 03:30 | 2023-12-13 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1818 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-13 07:00 | 2023-12-13 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1631 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-13 07:30 | 2023-12-13 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-1897 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-13 14:00 | 2023-12-13 17:00 | 3:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-2324-1764 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-14 03:30 | 2023-12-14 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1819 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-14 07:00 | 2023-12-14 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1632 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-14 07:30 | 2023-12-14 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1642 | 2023-10-25 | Cancelled |  |  | 1 | Total Possession | Goobang Jct | Goobang Jct North | Main Line | 2023-12-14 12:45 | 2023-12-14 22:45 | 10:00 | Level Crossing Removal | East - West | Goobang Junction to Broken Hill;#Cootamundra West to Goobang Junction | No Train Period during Possession. | Andrew Duncan | Chan Sarai |  |  | 2023-10-05
IPR-2324-1765 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-15 03:30 | 2023-12-15 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1820 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-15 07:00 | 2023-12-15 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1633 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-15 07:30 | 2023-12-15 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1643 | 2023-10-25 | Cancelled |  |  | 1 | Total Possession | Goobang Jct | Goobang Jct North | Main Line | 2023-12-15 12:45 | 2023-12-15 22:45 | 10:00 | Level Crossing Removal (Contingency) | East - West | Goobang Junction to Broken Hill;#Cootamundra West to Goobang Junction | No Train Period during Possession. | Andrew Duncan | Chan Sarai |  |  | 2023-10-05
IPR-2324-1766 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-16 03:30 | 2023-12-16 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1708 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-16 06:00 | 2023-12-16 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1821 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-16 07:00 | 2023-12-16 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-551 | 2022-12-20 | Approved | 1459-2023 | 2023-11-24 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-16 11:00 | 2023-12-16 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-1875 | 2023-11-20 | Approved | 1541-2023 | 2023-11-22 | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2023-12-16 15:00 | 2023-12-17 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-11-17
IPR-1898 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-16 15:00 | 2023-12-16 17:00 | 2:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-2324-70 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2023-12-16 22:00 | 2023-12-17 06:00 | 8:00 | ARTC MARL UTX Installation | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-413 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-17 00:05 | 2023-12-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1709 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-17 06:00 | 2023-12-17 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1822 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-17 07:00 | 2023-12-17 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1768 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-18 03:30 | 2023-12-18 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1710 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-18 06:00 | 2023-12-18 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1823 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-18 07:00 | 2023-12-18 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1465 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-18 13:00 | 2023-12-18 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1416 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-18 16:00 | 2023-12-18 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1767 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-19 03:30 | 2023-12-19 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1711 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-19 06:00 | 2023-12-19 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1712 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-20 06:00 | 2023-12-20 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1713 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-21 06:00 | 2023-12-21 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1714 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-22 06:00 | 2023-12-22 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-461 | 2022-12-21 | Pending |  |  | 5 | Window Possession | Cooks River | Enfield | Up and Down Goods | 2023-12-23 02:00 | 2024-01-08 22:00 | 404:00 | Sydney Metro Southwest | North - South | Sydney MFN | Possessions to be taken ATP on Up Goods LineWindow Possessions advertised on TAA 1484-2023 for Down Goods Line | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1535 | 2023-09-25 | Approved | 1460-2023 | 2023-11-24 | 1 | Total Possession | Enfield West | Enfield West | The Goods Line | 2023-12-23 02:00 | 2024-01-05 02:00 | 312:00 | Sydney Trains Protection | North - South | Sydney MFN | No trains impacted due to already occurring Sydney Trains Possession. No ad-hocs through possession area. No impacts to SSFL. | Andrew Duncan | Deane Thrower | SP3 Signal to EW420 Signal |  | 2023-09-06
IPR-2324-1715 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-23 06:00 | 2023-12-23 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-414 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-24 00:05 | 2023-12-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-456 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 06:00 | 2023-12-27 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1750 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 08:00 | 2023-12-27 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1751 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 14:10 | 2023-12-27 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1903 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 06:00 | 2023-12-28 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1906 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 08:00 | 2023-12-28 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1908 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 14:10 | 2023-12-28 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1904 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 06:00 | 2023-12-29 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1907 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 08:00 | 2023-12-29 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1909 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 14:10 | 2023-12-29 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1905 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 06:40 | 2023-12-30 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1910 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 10:30 | 2023-12-30 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-71 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2023-12-30 22:00 | 2023-12-31 06:00 | 8:00 | ARTC MARL UTX Installation | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-415 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-31 00:05 | 2023-12-31 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1911 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-31 09:20 | 2023-12-31 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1912 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 08:00 | 2024-01-01 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1921 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 14:10 | 2024-01-01 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1913 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 06:00 | 2024-01-02 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1917 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 08:00 | 2024-01-02 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1922 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 14:10 | 2024-01-02 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1914 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 06:00 | 2024-01-03 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1918 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 08:00 | 2024-01-03 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1923 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 14:10 | 2024-01-03 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1915 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 06:00 | 2024-01-04 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1919 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 08:00 | 2024-01-04 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1924 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 14:10 | 2024-01-04 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1916 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 06:00 | 2024-01-05 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1920 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 08:00 | 2024-01-05 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1925 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 14:10 | 2024-01-05 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1926 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 06:40 | 2024-01-06 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1430 | 2023-08-24 | Approved | 0009-2024 |  | 2 | Total Possession | Marulan | Goulburn | Down Main | 2024-01-06 10:20 | 2024-01-06 16:30 | 6:10 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​Date changed to avoid additional service impacts ​CriticalCompliance Testing Pilot Staff Working to be Implemented via Up Main Train Alterations Required, NO Cancellations Impacts to: NSWTL: SP33PN: 4PS6, 3924, 1225, 2128, 9327, 9323QUBE: 7MW7 | John Hilton | David Knee | Marulan: Clear of E Frame to Goulburn: Clear of 135 Points | LPA with PSW | 2023-08-21
IPR-1928 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 10:30 | 2024-01-06 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-72 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-01-06 22:00 | 2024-01-07 06:00 | 8:00 | ARTC MARL UTX Installation | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-416 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-07 00:05 | 2024-01-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1930 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-07 09:20 | 2024-01-07 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1427 | 2023-08-24 | Approved | 0006-2024 |  | 2 | Total Possession | Wingello | Marulan | Down Main | 2024-01-07 10:30 | 2024-01-07 17:00 | 6:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Up Main Train Alterations Required, No Cancellations Impacts to: NSWTL: SP34, SP33 PN: 2290, 9327, 3924, 1297, 2226 | John Hilton | David Knee | Wingello: Clear of D Frame to Marulan: Clear of E Frame | LPA with PSW | 2023-08-21
IPR-1932 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 08:00 | 2024-01-08 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1428 | 2023-08-24 | Approved | 0007-2024 |  | 1 | Total Possession | Moss Vale | Penrose | Down Main | 2024-01-08 09:40 | 2024-01-08 13:00 | 3:20 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing NO Pilot Staff Working to be Implemented Train Alterations & Cancellations Required 1311 (Qube) Delay1297 (PN) Delay1225 (PN) Delay2225 (PN) Cancel | John Hilton | David Knee | Moss Vale: MV69 Signal to Penrose: 170.9 Signal | TOA: Moss Vale to Penrose May require extension to MY1 to Off-track from 12:00 - 12:30 | 2023-08-21
IPR-2324-1468 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-08 13:00 | 2024-01-08 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-1935 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 14:10 | 2024-01-08 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1827 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-08 14:30 | 2024-01-08 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1432 | 2023-08-24 | Approved | 0007-2024 |  | 1 | Total Possession | Penrose | Moss Vale | Up Main | 2024-01-08 15:00 | 2024-01-08 17:40 | 2:40 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​Critical Compliance Testing NO Pilot Staff Working to be Implemented Train Alterations & Cancellations Required 2226 (PN) - Cancel2MW7 (Qube) Amend2120 (PN)- Amend2128 (PN) - Delay | John Hilton | David Knee | Penrose: Signal PE2 to Moss Vale: MV60 Signal | TOA: Penrose to Moss Vale via Up Refuge Will require to transition to Down Refuge at end of Window to Off-Track | 2023-08-21
IPR-2324-1417 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-08 16:00 | 2024-01-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1938 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 06:00 | 2024-01-09 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1730 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-09 07:00 | 2024-01-09 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 12th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1941 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 08:00 | 2024-01-09 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1429 | 2023-08-24 | Approved | 0008-2024 |  | 1 | Total Possession | Marulan | Wingello | Up Main | 2024-01-09 08:15 | 2024-01-09 13:30 | 5:15 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Down Main Train Alterations and Cancellations Required. Impacts to: NSWTL: SP32, SP31, ST23 (All incur delays)PN: 3930 (Cancel), 3922 (Cancel), 2126 (Amend), 2225 (Cancel), 2226 (Cancel), 7PS6 (Delay 100" at Goulburn), 1225 (Amend), 1297 (Amend)Qube: 1311 (Delay)Aurizon: 3SM1 (Delay) | John Hilton | David Knee | Marulan: Clear of E Frame to Wingello: Clear of D Frame | LPA with PSW | 2023-08-21
IPR-1830 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-09 14:00 | 2024-01-09 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1944 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 14:10 | 2024-01-09 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1947 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 06:00 | 2024-01-10 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1718 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-10 07:00 | 2024-01-10 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1950 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 08:00 | 2024-01-10 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1431 | 2023-08-24 | Approved | 0010-2024 |  | 2 | Total Possession | Marulan | Goulburn | Up Main | 2024-01-10 10:00 | 2024-01-10 17:00 | 7:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Down Main Train Alterations and Cancellations Required Impacts to: NSWTL: SP34, SP33 (Delays)PN: 3922 (Delays), 2PS7 (Lift 80min), 3924 (Cancel), 1225 (Delays), 9327 (Delays), 4BM4 (Delays), 2128 (Delays), 2120 (Delays)QUBE: 1311 (Delays), 5MW7 (Delays), 5SM7 (Delays)SCT: 4BM9 (Delays) | John Hilton | David Knee | Goulburn: Clear of 130 Points to Marulan: Clear of D Frame | LPA with PSW | 2023-08-21
IPR-1829 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-10 14:00 | 2024-01-10 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1953 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 14:10 | 2024-01-10 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1882 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-10 18:00 | 2024-01-11 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1828 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-01-11 00:30 | 2024-01-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1956 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 06:00 | 2024-01-11 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1769 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-11 07:00 | 2024-01-11 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1959 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 08:00 | 2024-01-11 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1425 | 2023-08-24 | Approved | 0004-2024 |  | 1 | Total Possession | Moss Vale | Medway Jct | Down Main | 2024-01-11 10:00 | 2024-01-11 13:00 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations and Cancellations RequiredImpacts to 1225, 1297, 1311 (All Delay)2225 & 2226 (Cancel) | John Hilton | David Knee | Moss Vale to Medway Junction | TOA | 2023-08-21
IPR-1896 | 2023-08-24 | Approved | 0004-2024 |  | 1 | Total Possession | Lynwood | Medway Jct | Up Main | 2024-01-11 10:00 | 2024-01-11 13:00 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations Required to 2128 | John Hilton | David Knee | Lynwood to Medway Junction | TOA | 2023-08-21
IPR-1962 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 14:10 | 2024-01-11 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1883 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-11 18:00 | 2024-01-12 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1965 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 06:00 | 2024-01-12 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1967 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 08:00 | 2024-01-12 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1426 | 2023-08-24 | Approved | 0005-2024 |  | 2 | Total Possession | Moss Vale | Wingello | Up Main | 2024-01-12 10:30 | 2024-01-12 13:00 | 2:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations Required Impacts to 3922 (Lift)2126 (Lift)2928 (Delay)2290 (Delay) | John Hilton | David Knee | Medway to Moss Vale | TOA | 2023-08-21
IPR-1969 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 14:10 | 2024-01-12 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1884 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-12 18:00 | 2024-01-13 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1927 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 06:40 | 2024-01-13 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1831 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-13 08:00 | 2024-01-13 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1436 | 2023-08-24 | Approved | 0052-2024 | 2023-11-23 | 3 | Window Possession | Moss Vale | Berrima Jct | Up Main, Up Refuge | 2024-01-13 10:00 | 2024-01-13 18:00 | 8:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn;#Macarthur to Moss Vale | ​​CriticalCompliance Testing No Ad Hoc Services, Unhealthy services may be delayed. No Direct Impact to MTP Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-2324-1437 | 2023-08-24 | Approved | 0052-2024 | 2023-11-23 | 3 | Window Possession | Moss Vale | Berrima Jct | Down Main, Down Refuge | 2024-01-13 10:00 | 2024-01-13 18:00 | 8:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn;#Macarthur to Moss Vale | ​​CriticalCompliance Testing No Ad Hoc Services, Unhealthy services may be delayed. No Direct Impact to MTP Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1929 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 10:30 | 2024-01-13 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-387 | 2022-12-21 | Cancelled |  |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-13 11:30 | 2024-01-13 15:30 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​​​4 hour Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. There is access to Moorebank Terminal from the South | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-11-25
IPR-1885 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-13 18:00 | 2024-01-14 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-2324-417 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-14 00:05 | 2024-01-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1433 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Goulburn | Joppa Jct | Down Main | 2024-01-14 06:30 | 2024-01-14 09:30 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1832 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-14 09:00 | 2024-01-14 20:30 | 11:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1931 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-14 09:20 | 2024-01-14 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1434 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Gunning | Joppa Jct | Up Main | 2024-01-14 09:30 | 2024-01-14 11:30 | 2:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-2324-1435 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Joppa Jct | Goulburn | Up Main, Up Refuge | 2024-01-14 09:30 | 2024-01-14 13:00 | 3:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1886 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-14 18:00 | 2024-01-15 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-2324-824 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Wirrega | Wirrega | Mainline | 2024-01-15 05:00 | 2024-01-15 11:00 | 6:00 | Turnout renewal | East - West | Serviceton to Islington (SA) | ​Was 19th September 2023 | Bryce Gore | Bonnar Mahains | Wirrega Signals 14 & 15 to 16 |  | 2023-05-22
IPR-1893 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Cooks River | Cooks River | Cooks River Loop | 2024-01-15 06:00 | 2024-01-26 02:00 | 260:00 | Stabling Track Machines | North - South | Port Botany to Marrickville Jct | Cooks River Loop will be unavailable for movements or stowing wagons. | Andrew Duncan | Jensen Kelly | C/O 788A to C/O 787B points |  | 2023-11-23
IPR-2324-111 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-01-15 07:00 | 2024-01-26 14:00 | 271:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-1933 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 08:00 | 2024-01-15 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1469 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-15 13:00 | 2024-01-15 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1597 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-01-15 13:00 | 2024-01-15 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-1936 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 14:10 | 2024-01-15 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1833 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-15 14:30 | 2024-01-15 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1418 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-15 16:00 | 2024-01-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1887 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-15 18:00 | 2024-01-16 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1817 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-15 20:00 | 2024-01-16 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-823 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Wirrega | Wirrega | Mainline | 2024-01-16 05:00 | 2024-01-16 14:00 | 9:00 | Turnout renewal | East - West | Serviceton to Islington (SA) | ​Was 18th September 2023​. | Bryce Gore | Bonnar Mahains | Wirrega Signals 14 & 15 to 16 |  | 2023-05-22
IPR-2324-1646 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Deep Lead | Great Western Loop | Main Line | 2024-01-16 06:00 | 2024-01-16 16:00 | 10:00 | Seaby St Subway Deck Subsidence Repairs | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Vernie Chong |  |  | 2023-10-12
IPR-1939 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 06:00 | 2024-01-16 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1942 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 08:00 | 2024-01-16 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1945 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 14:10 | 2024-01-16 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1834 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-16 14:30 | 2024-01-16 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1888 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-16 18:00 | 2024-01-17 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1876 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-16 20:00 | 2024-01-17 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1948 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 06:00 | 2024-01-17 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1951 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 08:00 | 2024-01-17 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1954 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 14:10 | 2024-01-17 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1835 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-17 14:30 | 2024-01-17 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1889 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Forbes | Parkes | Main Line | 2024-01-17 18:00 | 2024-01-18 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1877 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-17 20:00 | 2024-01-18 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1957 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 06:00 | 2024-01-18 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1960 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 08:00 | 2024-01-18 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1963 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 14:10 | 2024-01-18 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1890 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Gunningbland | Gunningbland | Main Line | 2024-01-18 18:00 | 2024-01-19 06:00 | 12:00 | Track Resurfacing | East - West | Goobang Junction to Broken Hill | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1878 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-18 20:00 | 2024-01-19 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1966 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 06:00 | 2024-01-19 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1968 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 08:00 | 2024-01-19 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1970 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 14:10 | 2024-01-19 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1891 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-19 18:00 | 2024-01-20 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1879 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-19 20:00 | 2024-01-20 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-1686 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Cooks River | Cooks River | Up Botany + Cooks Loop | 2024-01-19 22:00 | 2024-01-20 02:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | CR736G Signal TO C/O 790pts |  | 2023-10-06
IPR-2324-1688 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Port Botany Yard | Port Botany Yard | Road 4 + Gelco Siding | 2024-01-19 22:00 | 2024-01-20 02:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | C/O 150pts TO BY15 Signal |  | 2023-10-06
IPR-2324-1787 | 2022-07-26 | Supported |  |  | 1 | Config 10-C | Port Botany Yard | Cooks River | All Tracks | 2024-01-19 22:00 | 2024-01-22 06:00 | 56:00 | Config-10C | North - South | Port Botany to Marrickville Jct | BRD Final CommissioningNo Access to Boral or Cooks River | Andrew Duncan | Jensen Kelly | Port Botany to Cooks River |  | 2022-06-23
IPR-2324-19 | 2022-07-26 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Tracks | 2024-01-20 02:00 | 2024-01-22 02:00 | 48:00 | Config-10A | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​WE30 Config 10A | Andrew Duncan | Deane Thrower | Cooks River to Flemington Junction and Enfield West |  | 2022-06-23
IPR-2324-466 | 2023-04-26 | Cancelled |  |  | 3 | Window Possession | Leightonfield | Glenfield | SSFL | 2024-01-20 02:00 | 2024-01-21 23:00 | 45:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​Windows (min. 4 hours) will be identified and advertised after finalisation of the WE30 train plan. Ad hoc paths may be considered for approval with notice to the Interstate Possessions team. Access to Moorebank will be available from the south only. | Andrew Duncan | Daniel Wakefield | Leightonfield LF11 and LF14 to Glenfield GF16, GF18 and GF22. |  | 2023-01-18
IPR-1825 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-20 09:00 | 2024-01-20 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSFL and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-1892 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-20 18:00 | 2024-01-21 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1880 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-20 20:00 | 2024-01-21 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-636 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-01-20 21:00 | 2024-01-21 11:00 | 14:00 | Underbridge Replacement 161.297km | East - West | Dry Creek to Crystal Brook | ​Was 23-24 Sep then 11-12 Nov | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-418 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-21 00:05 | 2024-01-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1826 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-21 09:00 | 2024-01-21 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSLF and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-1881 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-21 20:00 | 2024-01-22 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-637 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-01-21 23:00 | 2024-01-22 05:00 | 6:00 | Underbridge Replacement 161.297km | East - West | Dry Creek to Crystal Brook | Was 24-25 Sep then 12-13 Nov | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-1689 | 2023-10-25 | Pending |  |  | 3 | Window Possession | Cooks River | Cooks River | Up Botany + Cooks Loop | 2024-01-22 02:00 | 2024-01-22 06:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | CR736G Signal TO C/O 790pts |  | 2023-10-06
IPR-2324-1690 | 2023-10-25 | Pending |  |  | 3 | Window Possession | Port Botany Yard | Port Botany Yard | Road 4 + Gelco Siding | 2024-01-22 02:00 | 2024-01-22 06:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | C/O 150pts TO BY15 Signal |  | 2023-10-06
IPR-2324-1267 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main Line | 2024-01-22 07:30 | 2024-01-22 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-1934 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 08:00 | 2024-01-22 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1470 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-22 13:00 | 2024-01-22 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-1937 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 14:10 | 2024-01-22 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1419 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-22 16:00 | 2024-01-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1657 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-22 22:00 | 2024-01-22 23:59 | 1:59 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1658 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-23 01:30 | 2024-01-23 02:30 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1659 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-23 04:00 | 2024-01-23 05:00 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1647 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Deep Lead | Great Western Loop | Main Line | 2024-01-23 06:00 | 2024-01-23 16:00 | 10:00 | Seaby St Subway Deck Subsidence Repairs | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Vernie Chong |  |  | 2023-10-12
IPR-1940 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 06:00 | 2024-01-23 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1268 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main Line | 2024-01-23 07:30 | 2024-01-23 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-1943 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 08:00 | 2024-01-23 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1700 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Balhannah | Balhannah | Main Line | 2024-01-23 10:30 | 2024-01-23 20:00 | 9:30 | Balhannah 20pts V-Crossing Upgrade | East - West | Serviceton to Islington (SA) | No Train Period - Was originally Ped crossing at Petwood | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-2324-1701 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-01-23 11:30 | 2024-01-23 20:30 | 9:00 | Netley Road LX Upgrade 93.019km | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-1946 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 14:10 | 2024-01-23 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1949 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 06:00 | 2024-01-24 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1269 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main line | 2024-01-24 07:30 | 2024-01-24 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-1952 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 08:00 | 2024-01-24 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1955 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 14:10 | 2024-01-24 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1660 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-24 22:00 | 2024-01-24 23:59 | 1:59 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1661 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-25 01:30 | 2024-01-25 02:30 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1662 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-25 04:00 | 2024-01-25 05:00 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-1958 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 06:00 | 2024-01-25 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1961 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 08:00 | 2024-01-25 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1964 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 14:10 | 2024-01-25 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1656 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-25 22:30 | 2024-01-26 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-1663 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-26 22:30 | 2024-01-27 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-388 | 2023-09-25 | Supported |  |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-27 11:30 | 2024-01-27 15:30 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​​​4 hour Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. There is access to Moorebank Terminal from the South | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-11-25
IPR-2324-1664 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-27 22:30 | 2024-01-28 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-419 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-28 00:05 | 2024-01-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1665 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-28 22:30 | 2024-01-29 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-101 | 2022-12-21 | Approved |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-01-29 03:00 | 2024-01-29 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1111 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-01-29 06:00 | 2024-02-05 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-1471 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-29 13:00 | 2024-01-29 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1420 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-29 16:00 | 2024-01-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1902 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | All Tracks | 2024-01-29 21:00 | 2024-01-30 03:00 | 6:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | West Track Possession - All services Divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-16
IPR-2324-1702 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Tailem Bend | Tailem Bend | Main Line | 2024-01-30 12:30 | 2024-01-30 21:00 | 8:30 | Magpie Drive LX Renewal at 122.335km | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-1836 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-30 14:00 | 2024-01-30 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1837 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-31 14:00 | 2024-01-31 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1838 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-01 00:30 | 2024-02-01 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-18 | 2022-07-26 | Supported |  |  | 1 | Config 14 | Enfield West | Moss Vale | Main South | 2024-02-02 22:30 | 2024-02-05 02:00 | 51:30 | Config-14 | North - South | Macarthur to Moss Vale;#Southern Sydney Freight Line | WE32 ​LPA Closedown | Andrew Duncan | Deane Thrower | Glenlee to Berrima Junction (Exclusive) |  | 2022-06-23
IPR-2324-1449 | 2023-08-24 | Supported |  |  | 1 | Config 14 | Leightonfield | Glenfield | SSFL | 2024-02-02 22:30 | 2024-02-05 10:00 | 59:30 | Cabramatta Loop Commissioning | North - South | Southern Sydney Freight Line | ​In conjunction with WE32 Config 14 Possession. To Facilitate Commissioning of Cabramatta Loop.Based on April 2023 Config 14 the following additional services will be impacted. 5PS6, 1MB4, 1MS2, 1WM7, 2124, 2192, T232, T233 | Andrew Duncan | Miguel Alcantara | Leightonfield to Glenfield on SSFL |  | 2022-06-23
IPR-2324-17 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-02-03 06:00 | 2024-02-03 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE32 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-1723 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-03 06:00 | 2024-02-03 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1839 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-03 08:00 | 2024-02-03 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-552 | 2023-02-22 | Pending |  |  | 2 | Total Possession | Kiacatoo | Kiacatoo | Mainline | 2024-02-03 16:00 | 2024-02-04 03:30 | 11:30 | Culvert Renewal | East - West | Goobang Junction to Broken Hill | ​​Was 02 - 03 December | Bryce Gore | Kim Lawes | Kiacatoo Down YLB - Up YLB |  | 2023-02-21
IPR-2324-420 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-04 00:05 | 2024-02-04 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-16 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-02-04 06:00 | 2024-02-04 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE32 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-1724 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-04 06:00 | 2024-02-04 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1840 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-04 09:00 | 2024-02-04 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-102 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-05 05:00 | 2024-02-05 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1472 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-05 13:00 | 2024-02-05 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-1841 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-05 14:30 | 2024-02-05 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1421 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-05 16:00 | 2024-02-05 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1676 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-06 11:00 | 2024-02-06 22:00 | 11:00 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1842 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-06 14:00 | 2024-02-06 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1677 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-07 11:30 | 2024-02-07 14:00 | 2:30 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1843 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-07 14:00 | 2024-02-07 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1678 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-07 15:00 | 2024-02-07 17:30 | 2:30 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1844 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-08 00:30 | 2024-02-08 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-103 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-08 06:00 | 2024-02-08 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-262 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-09 06:00 | 2024-02-09 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-263 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-10 06:00 | 2024-02-10 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1871 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Crystal Brook | Mainline | 2024-02-10 07:30 | 2024-02-10 13:00 | 5:30 | Drovers Rd LX Upgrade 4.722km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-553 | 2023-02-22 | Pending |  |  | 2 | Total Possession | Kiacatoo | Kiacatoo | Mainline | 2024-02-10 16:00 | 2024-02-11 03:30 | 11:30 | Culvert Renewal | East - West | Goobang Junction to Broken Hill | ​​Was 09 - 12 December | Bryce Gore | Kim Lawes | Kiacatoo Down YLB - Up TLB |  | 2023-02-21
IPR-1865 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-10 21:00 | 2024-02-11 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-421 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-11 00:05 | 2024-02-11 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1853 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-11 00:30 | 2024-02-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-264 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-11 06:00 | 2024-02-11 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1866 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-11 23:00 | 2024-02-12 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-104 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-12 05:00 | 2024-02-12 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1683 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Port Augusta | Winninowie | Mainline | 2024-02-12 05:00 | 2024-02-12 11:00 | 6:00 | Harris St LX Upgrade | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-2324-265 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-12 06:00 | 2024-02-12 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1687 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mambray Creek | Mambray Creek | Mainline | 2024-02-12 07:30 | 2024-02-12 12:00 | 4:30 | Mambray Creek 7pts and 20pts Renewal | East - West | Crystal Brook to Spencer Junction | No Train Period - Was 14/2 | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-2324-1473 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-12 13:00 | 2024-02-12 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1598 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-02-12 13:00 | 2024-02-12 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1422 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-12 16:00 | 2024-02-12 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-266 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-13 06:00 | 2024-02-13 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1845 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-13 14:00 | 2024-02-13 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1685 | 2023-10-25 | Pending |  |  | 3 | Total Possession | Mambray Creek | Mambray Creek | Mainline | 2024-02-14 05:00 | 2024-02-14 16:00 | 11:00 | Mambray Creek 7pts and 20pts Renewal | East - West | Crystal Brook to Spencer Junction | No Adhocs | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-2324-267 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-14 06:00 | 2024-02-14 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1846 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-14 14:00 | 2024-02-14 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1847 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-15 00:30 | 2024-02-15 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-268 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-15 06:00 | 2024-02-15 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-269 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-16 06:00 | 2024-02-16 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1872 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-16 06:00 | 2024-02-16 15:30 | 9:30 | Turnout replacement at 17 Points | East - West | Crystal Brook to Spencer Junction | ​Crossing Loop - No Access to Pt Germein Siding from Adelaide End | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-11-21
IPR-2324-105 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-16 20:00 | 2024-02-17 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-459 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Cooks River | Enfield | Up and Down Goods | 2024-02-17 02:00 | 2024-02-18 22:00 | 44:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested windows on the Up and Down Goods lines aligned with the Sydenham-Sefton Closedown on the ST Network. This would prevent access to Cooks River and Botany, Enfield would be available from the South only. As at 4/1/23 this is under review by ARTC to determine suitable window to exclude ad hoc trains and possibly impact late/unhealthy mandatory services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-462 | 2022-12-21 | Pending |  |  | 5 | As Traffic Permits | Cooks River | Enfield | Up and Down Goods | 2024-02-17 02:00 | 2024-02-18 22:00 | 44:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested ad hoc windows on the Up and Down Goods as well as the advertised ones. These will be managed solely through the CAA process and will have no impact to services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1725 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-17 06:00 | 2024-02-17 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-2324-1684 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-17 07:30 | 2024-02-17 13:00 | 5:30 | Coonamia 8pts Vee Crossing Upgrade | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1849 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-17 08:00 | 2024-02-17 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-314 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-17 20:00 | 2024-02-18 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-73 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-02-17 22:00 | 2024-02-18 06:00 | 8:00 | Signalling work | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km - 20.75 km |  | 2022-08-23
IPR-2324-422 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-18 00:05 | 2024-02-18 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1726 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-18 06:00 | 2024-02-18 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1850 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-18 09:00 | 2024-02-18 13:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1586 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-18 15:00 | 2024-02-19 03:00 | 12:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2324-90 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-19 05:00 | 2024-02-19 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1474 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-19 13:00 | 2024-02-19 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-1851 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-19 14:30 | 2024-02-19 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1587 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-19 15:00 | 2024-02-19 20:00 | 5:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2324-1589 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Main Line | 2024-02-19 15:00 | 2024-02-20 03:00 | 12:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Main. Mandatory Trains to use Loop line when Loop not under Possession | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-1423 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-19 16:00 | 2024-02-19 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-270 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-19 20:00 | 2024-02-20 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1588 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-20 | 2024-02-20 03:00 | 3:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2324-880 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-20 06:00 | 2024-02-20 18:00 | 12:00 | Turnout replacement at 16 Points | East - West | Crystal Brook to Spencer Junction | ​Crossing Loop - No Access to Pt Germein Siding from Adelaide End - Was 14/11/2023 | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-06-21
IPR-1861 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 07:00 | 2024-02-20 11:15 | 4:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1862 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 11:45 | 2024-02-20 20:30 | 8:45 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-1590 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Main Line | 2024-02-20 14:00 | 2024-02-21 03:00 | 13:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Main. Mandatory Trains to use Loop line when Loop not under Possession | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-1591 | 2023-09-25 | Pending | 0002-2024 |  | 3 | Window Possession | Dry Creek | Dry Creek | Loop | 2024-02-20 14:00 | 2024-02-20 19:30 | 5:30 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Ad Hoc Train Period | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-1852 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-20 14:00 | 2024-02-20 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-271 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-20 20:00 | 2024-02-21 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1592 | 2023-09-25 | Pending | 0002-2024 |  | 3 | Window Possession | Dry Creek | Dry Creek | Loop | 2024-02-21 00:40 | 2024-02-21 03:40 | 3:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Ad Hoc Train Period | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-881 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-21 06:00 | 2024-02-21 18:00 | 12:00 | Turnout replacement at 16 Points | East - West | Crystal Brook to Spencer Junction | No Access to Pt Germein Siding from Adelaide End - Was 15/11/2023 | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-06-21
IPR-1848 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-21 14:00 | 2024-02-21 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-272 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-21 20:00 | 2024-02-22 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1857 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-22 00:30 | 2024-02-22 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-273 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-22 20:00 | 2024-02-23 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-274 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-23 20:00 | 2024-02-24 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-12 | 2022-07-26 | Supported | 0022-2024 |  | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2024-02-24 01:00 | 2024-02-25 23:00 | 46:00 | Config-16 | North - South | Moss Vale to Unanderra | Extended Config 16 PossessionRequest for Feedback Email sent 14/11/23 | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-315 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-24 20:00 | 2024-02-25 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1868 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-24 21:00 | 2024-02-25 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-423 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-25 00:05 | 2024-02-25 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1867 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-25 23:00 | 2024-02-26 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-1594 | 2023-09-25 | Pending | 0003-2024 |  | 2 | Total Possession | Torrens Jct | Torrens Jct | Main | 2024-02-26 10:40 | 2024-02-26 18:40 | 8:00 | Pedestrian Crossing Upgrade | East - West | Serviceton to Islington (SA) | Pedestrian Crossing Upgrade - Dudley Park Station - 6.353kmNo Train Period - Full Upgrade | Bryce Gore | Jessica Tai | Torrens Junction AN21 (3.042km) to Islington 30 (6.916km) |  | 2023-09-21
IPR-2324-1475 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-26 13:00 | 2024-02-26 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1424 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-26 16:00 | 2024-02-26 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-91 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | West Track | 2024-02-26 18:00 | 2024-02-28 18:00 | 48:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform for 48hrs after 60hr Vic Shut | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-107 | 2022-12-21 | Cancelled |  |  | 1 | Total Possession | Albion Jct | Jacana | Broad Gauge & Dual Gauge Only | 2024-02-26 18:00 | 2024-03-04 18:00 | 168:00 | New Dual Gauge Turnout & Removal Of Redundant Broad Gauge Rail | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​​Will follow immediately after 60hr Shutdown has finished, Broad Gauge / DG Track Only | Ralph Artho | Calum Leslie | Albion Jct MCT/14 to Tullamarine TME/18 Broad Gauge & Dual Gauge Only |  | 2022-10-17
IPR-2324-275 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-26 20:00 | 2024-02-27 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1854 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-27 14:00 | 2024-02-27 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-276 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-27 20:00 | 2024-02-28 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1869 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-27 22:00 | 2024-02-28 09:00 | 11:00 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-277 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-02-28 07:00 | 2024-02-28 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1856 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-28 14:00 | 2024-02-28 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1870 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-28 21:30 | 2024-02-29 08:00 | 10:30 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1855 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-29 00:30 | 2024-02-29 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-92 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-02-29 07:00 | 2024-02-29 17:00 | 10:00 | Inland Rail - Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-278 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-29 20:00 | 2024-03-01 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-353 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-01 07:00 | 2024-03-01 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on New West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-279 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-01 20:00 | 2024-03-02 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-452 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-03-02 02:00 | 2024-03-03 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-316 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-02 20:00 | 2024-03-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-424 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-03 00:05 | 2024-03-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-93 | 2022-10-12 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-03-04 03:00 | 2024-03-04 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-354 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-04 07:00 | 2024-03-04 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1863 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-04 08:45 | 2024-03-04 19:00 | 10:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-1476 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-04 13:00 | 2024-03-04 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1770 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-04 16:00 | 2024-03-04 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-280 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-04 20:00 | 2024-03-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-355 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-05 07:00 | 2024-03-05 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1864 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-05 07:00 | 2024-03-05 19:00 | 12:00 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-281 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-05 20:00 | 2024-03-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-356 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-06 07:00 | 2024-03-06 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-282 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-06 20:00 | 2024-03-07 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-357 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-07 07:00 | 2024-03-07 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-283 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-07 20:00 | 2024-03-08 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-358 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | West Track | 2024-03-08 07:00 | 2024-03-08 17:00 | 10:00 | Inland Rail Genrowan | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-284 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-08 20:00 | 2024-03-09 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-82 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Moss Vale | Goulburn | All Tracks | 2024-03-09 00:01 | 2024-03-11 18:00 | 65:59 | SHOO Project Works | North - South | Moss Vale to Goulburn | WE35 ​Construction of Passing Lanes at Joppa Junction and Werai. Other Corridor Works to be conducted | Andrew Duncan | Ewen Henderson | Moss Vale (Exclusive) to Joppa Junction (Inclusive) |  | 2022-09-19
IPR-2324-83 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Goulburn | Albury | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Various Corridor Maintenance & Enhancement Works | North - South | Goulburn to Junee;#Junee to Albury | ​WE35 ​60hr 'Super' Shut in alignment with Vic & North Coast NSW Possessions | Andrew Duncan | Deane Thrower | Goulburn (Exc) to Albury (Inc) |  | 2022-09-19
IPR-2324-84 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Cootamundra West | Forbes | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Various Corridor Maintenance & Enhancement Works | North - South | Cootamundra West to Goobang Junction | ​WE37 ​60hr 'Super' Shut in alignment with Vic & North Coast NSW Possessions | Andrew Duncan | Deane Thrower | Cootamundra West (Inclusive) to Forbes (DYLB) |  | 2022-09-19
IPR-2324-86 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Albury | Tottenham | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | NE Victoria 'Super' Shut | North - South | Albury to Somerton;#Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​NE Victoria 60hr Possession | Bryce Gore | Warren Williams |  |  | 2022-10-11
IPR-2324-791 | 2023-06-26 | Supported |  |  | 1 | Total Possession | Leightonfield | Glenfield | SSFL | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Commissioning Cabramatta Loop Project | North - South | Southern Sydney Freight Line | ​This is a contingency window only and if required, will be 12 hours continuous. Times will be determined at T-4 in order to add impact to the least amount of trains possible. | Andrew Duncan | Steven Chance |  |  | 2023-05-02
IPR-2324-1789 | 2023-11-15 | Supported |  |  | 1 | Total Possession | Forbes | Goobang Jct | All Tracks | 2024-03-09 06:00 | 2024-03-12 22:00 | 88:00 | Inland Rail Construction | North - South | Cootamundra West to Goobang Junction | ​Extended Possession for Inland Rail Construction Activities | Andrew Duncan | Chris Fay | Forbes (DYLB) to Goobang Junction (End TOW) | TOA | 2022-09-19
IPR-1815 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-09 07:00 | 2024-03-09 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-14 | 2022-07-26 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Tracks | 2024-03-09 09:00 | 2024-03-10 17:00 | 32:00 | Config-9 | North - South | Telarah to Acacia Ridge | WE37 ​Closedown LPA | Andrew Duncan | Peter Lee | Telarah - Acacia Ridge |  | 2022-06-23
IPR-1899 | 2023-11-24 | Pending |  |  | 3 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 13:00 | 2024-03-09 15:00 | 2:00 | WGTP | East - West | Melbourne Metro | No Adhocs - Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-1900 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 15:00 | 2024-03-10 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-2324-317 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-09 20:00 | 2024-03-10 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-425 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-10 00:05 | 2024-03-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1901 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-11 | 2024-03-11 06:00 | 6:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-2324-359 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-11 07:00 | 2024-03-11 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1477 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-11 13:00 | 2024-03-11 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1771 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-11 16:00 | 2024-03-11 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1729 | 2023-10-10 | Approved |  |  | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-03-11 18:00 | 2024-03-15 18:00 | 96:00 | Bridge Deck Replacements | North - South | Benalla to Oakland Line | Total 6 Day Shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1753 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-03-11 18:00 | 2024-03-13 18:00 | 48:00 | Inland Rail - Wangaratta Station | North - South | Albury to Somerton | Nil Access to Wangaratta Passenger Platform - All services divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-02
IPR-2324-285 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-11 20:00 | 2024-03-12 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-360 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-12 07:00 | 2024-03-12 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1974 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-12 12:45 | 2024-03-13 01:45 | 13:00 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-286 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-12 20:00 | 2024-03-13 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-361 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-13 07:00 | 2024-03-13 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1975 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-13 10:45 | 2024-03-13 15:40 | 4:55 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-287 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-13 20:00 | 2024-03-14 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-362 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-14 07:00 | 2024-03-14 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-288 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-14 20:00 | 2024-03-15 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-363 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-15 07:00 | 2024-03-15 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-289 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-15 20:00 | 2024-03-16 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-455 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-03-16 02:00 | 2024-03-17 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-318 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-16 20:00 | 2024-03-17 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-75 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-03-16 22:00 | 2024-03-17 06:00 | 8:00 | Signalling work | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-06
IPR-2324-1442 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Westmere Loop | Tatyoon Loop | Mainline | 2024-03-16 22:00 | 2024-03-17 08:00 | 10:00 | Glenelg Why LX Renewal 213.384km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-426 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-17 00:05 | 2024-03-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-112 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-03-18 07:00 | 2024-03-19 14:00 | 31:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-2324-1233 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-18 07:00 | 2024-03-18 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1816 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-18 07:00 | 2024-03-18 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1478 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-18 13:00 | 2024-03-18 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1599 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-03-18 13:00 | 2024-03-18 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1772 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-18 16:00 | 2024-03-18 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-290 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-18 20:00 | 2024-03-19 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1115 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-03-19 06:00 | 2024-03-26 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-94 | 2022-12-21 | Pending |  |  | 6 | Advice Only | Chiltern | Wangaratta |  | 2024-03-19 07:00 | 2024-06-20 17:00 | 2242:00 | Inland Rail - Wangaratta Station Works | North - South | Albury to Somerton | ​​Passenger Trains run on New East Track to access existing Platform - Freight can use either Tracks | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1234 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main line | 2024-03-19 07:00 | 2024-03-19 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1443 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Tatyoon Loop | Maroona Loop | Mainline | 2024-03-19 07:00 | 2024-03-19 17:00 | 10:00 | Helendite Rd LX Renewal 244.094km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-294 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-19 20:00 | 2024-03-20 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1978 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 | 2024-03-20 12:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1235 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main line | 2024-03-20 07:00 | 2024-03-20 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1979 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 19:00 | 2024-03-21 01:00 | 6:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | . | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-295 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-20 20:00 | 2024-03-21 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1446 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Lubeck | Murtoa Loop | Mainline | 2024-03-21 03:30 | 2024-03-21 13:30 | 10:00 | Murtoa-Donald Rd LX Upgrade 299.010km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1236 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-21 07:00 | 2024-03-21 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-296 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-21 20:00 | 2024-03-22 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1980 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-22 03:00 | 2024-03-22 15:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1237 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-22 07:00 | 2024-03-22 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-297 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-22 20:00 | 2024-03-23 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-11 | 2022-07-26 | Supported |  |  | 1 | Config 10-B | Cooks River | Chullora Jct | All Tracks | 2024-03-23 02:00 | 2024-03-25 02:00 | 48:00 | Config-10B | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​​WE39 Config 10B | Andrew Duncan | Deane Thrower | Cooks River to Chullora Junction (Config-10B) |  | 2022-06-23
IPR-1981 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-23 03:00 | 2024-03-23 13:00 | 10:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1238 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-23 07:00 | 2024-03-23 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-319 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-23 20:00 | 2024-03-24 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1444 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Maroona Loop | Pyrenees | Mainline | 2024-03-23 21:30 | 2024-03-24 07:30 | 10:00 | Walkers Rd LX Renewal 266.728km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-76 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-03-23 22:00 | 2024-03-24 06:00 | 8:00 | Signalling work | East - West | Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-07
IPR-2324-1445 | 2023-09-25 | Cancelled |  |  | 2 | Total Possession | Great Western Loop | Deep Lead | Mainline | 2024-03-23 23:00 | 2024-03-24 09:00 | 10:00 | Seaby Rd LX Renewal 241.354km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-427 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-24 00:05 | 2024-03-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1239 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-24 07:00 | 2024-03-24 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1976 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-24 16:00 | 2024-03-25 04:00 | 12:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1240 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-25 07:00 | 2024-03-25 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1479 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-25 13:00 | 2024-03-25 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1773 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-25 16:00 | 2024-03-25 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-291 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-25 20:00 | 2024-03-26 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1977 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-25 21:00 | 2024-03-26 04:00 | 7:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1447 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Murtoa Loop | Horsham | Mainline | 2024-03-26 06:00 | 2024-03-26 16:00 | 10:00 | North Jung Rd 308.777 LX Upgrade | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1241 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-26 07:00 | 2024-03-26 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1270 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Lillimur | Kaniva Loop | Main Line | 2024-03-26 07:00 | 2024-03-26 17:00 | 10:00 | Removal of redundant turnout at Kaniva Down end (A4386D) | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-298 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-26 20:00 | 2024-03-27 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1242 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-27 07:00 | 2024-03-27 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-299 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-27 20:00 | 2024-03-28 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1448 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Pimpinio Loop | Dimboola | Mainline | 2024-03-28 04:00 | 2024-03-28 13:00 | 9:00 | Cemetery Rd LX Upgrade 363.139km | East - West | Tottenham to Serviceton | ​No Train Period - Was 29-30 March | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1243 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-28 07:00 | 2024-03-28 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-300 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-28 20:00 | 2024-03-29 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-301 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-29 20:00 | 2024-03-30 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-320 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-30 20:00 | 2024-03-31 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-428 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-31 00:05 | 2024-03-31 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1971 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-04-01 03:00 | 2024-04-01 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2324-292 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-01 20:00 | 2024-04-02 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-302 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-02 20:00 | 2024-04-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-306 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-02 20:00 | 2024-04-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-303 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-03 20:00 | 2024-04-04 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-307 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-03 20:00 | 2024-04-04 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-304 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-04 20:00 | 2024-04-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-308 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-04 20:00 | 2024-04-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-305 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-05 20:00 | 2024-04-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-309 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-05 20:00 | 2024-04-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-321 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-06 20:00 | 2024-04-07 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-77 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-04-06 22:00 | 2024-04-07 06:00 | 8:00 | Signalling work | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-07
IPR-2324-429 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-07 00:05 | 2024-04-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1775 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-08 16:00 | 2024-04-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-293 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-08 20:00 | 2024-04-09 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-310 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-09 20:00 | 2024-04-10 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-311 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-10 20:00 | 2024-04-11 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-312 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-11 20:00 | 2024-04-12 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-313 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-12 20:00 | 2024-04-13 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-322 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-13 20:00 | 2024-04-14 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-78 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-04-13 22:00 | 2024-04-14 06:00 | 8:00 | Signalling work | East - West | Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-09
IPR-2324-430 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-14 00:05 | 2024-04-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-457 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Cooks River | Enfield | Up and Down Goods | 2024-04-14 02:00 | 2024-04-24 22:00 | 260:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested windows on the Up and Down Goods lines aligned with the Sydenham-Sefton Closedown on the ST Network. This would prevent access to Cooks River and Botany, Enfield would be available from the South only. As at 4/1/23 this is under review by ARTC to determine suitable window to exclude ad hoc trains and possibly impact late/unhealthy mandatory services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-463 | 2022-12-21 | Pending |  |  | 5 | As Traffic Permits | Cooks River | Enfield | Up and Down Goods | 2024-04-14 02:00 | 2024-04-24 22:00 | 260:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested ad hoc windows on the Up and Down Goods as well as the advertised ones. These will be managed solely through the CAA process and will have no impact to services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1112 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-04-15 06:00 | 2024-04-22 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-1776 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-15 16:00 | 2024-04-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-323 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-15 20:00 | 2024-04-16 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-106 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-16 07:00 | 2024-04-16 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-324 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-17 07:00 | 2024-04-17 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-573 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Marulan | Wingello | Up Main | 2024-04-17 07:00 | 2024-04-17 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Marulan Clr E Frame to Wingello Clr C Frame | Pilot Staff Working | 2023-03-15
IPR-2324-325 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-18 07:00 | 2024-04-18 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-574 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Wingello | Bundanoon | Up Main | 2024-04-18 07:00 | 2024-04-18 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Wingello Clr D Frame to Bundanoon Clr C Frame | Pilot Staff Working | 2023-03-15
IPR-2324-326 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-19 07:00 | 2024-04-19 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1534 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Moss Vale | Bundanoon | Up Main | 2024-04-19 07:00 | 2024-04-19 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Bundanoon clear of B frame - Moss Vale MV84 | Pilot Staff Working | 2023-03-15
IPR-2324-9 | 2022-07-26 | Supported |  |  | 1 | Config 14 | Enfield West | Moss Vale | MS / SSFL | 2024-04-19 22:30 | 2024-04-22 02:00 | 51:30 | Config-14 | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | WE43 ​LPA Closedown | Andrew Duncan | Deane Thrower | Enfield West to Berrima Junction (Exclusive) via SSFL |  | 2022-06-23
IPR-2324-8 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-04-20 06:00 | 2024-04-20 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE43 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-1265 | 2023-07-24 | Approved |  |  | 2 | Total Possession | Glen Thompson | Grampians Loop | Portland Line | 2024-04-20 07:00 | 2024-04-20 17:00 | 10:00 | LX Renewal 294.806km | East - West | Portland Line | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-431 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-21 00:05 | 2024-04-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-7 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-04-21 06:00 | 2024-04-21 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE43 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-327 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-575 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Marulan | Down Main | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Goulburn G75 Sig to Marulan Clr E frame | Pilot Staff Working | 2023-03-15
IPR-2324-1266 | 2023-07-24 | Approved |  |  | 2 | Total Possession | Maroona Loop | Portland | Portland Line | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | LX Renewal | East - West | Portland Line | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-1777 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-22 16:00 | 2024-04-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-333 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-23 07:00 | 2024-04-23 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-576 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Joppa Jct | Up Main | 2024-04-23 07:00 | 2024-04-23 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | Grinding within Yard | John Hilton | Owen Blake |  | TOA | 2023-03-15
IPR-1858 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-23 12:00 | 2024-04-23 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-334 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-24 07:00 | 2024-04-24 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-124 | 2022-12-21 | Supported |  |  | 6 | Special Event | Cootamundra | Cootamundra | All Tracks | 2024-04-25 05:45 | 2024-04-25 06:30 | 0:45 | Anzac Day March | North - South | Goulburn to Junee | ​​No trains will be permitted through Cootamundra during the Anzac Day Dawn Service | Andrew Duncan | Andrew Duncan |  |  | 2022-11-10
IPR-2324-335 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-25 07:00 | 2024-04-25 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-125 | 2022-04-26 | Supported |  |  | 6 | Special Event | Junee | Junee | All Tracks | 2024-04-25 10:40 | 2024-04-25 11:00 | 0:20 | Anzac Day March | North - South | Goulburn to Junee | ​No trains will be permitted through Junee during the Anzac Day March | Andrew Duncan | Dean Rich |  |  | 2022-04-01
IPR-2324-126 | 2022-12-21 | Supported |  |  | 6 | Special Event | Cootamundra | Cootamundra | All Tracks | 2024-04-25 11:00 | 2024-04-25 12:00 | 1:00 | Anzac Day March | North - South | Goulburn to Junee | ​​No trains will be permitted through Cootamundra during the Anzac Day March | Andrew Duncan | Andrew Duncan |  |  | 2022-11-10
IPR-2324-336 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-26 07:00 | 2024-04-26 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-1859 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-27 11:00 | 2024-04-27 23:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-432 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-28 00:05 | 2024-04-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1873 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-28 16:00 | 2024-04-29 04:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-328 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-29 07:00 | 2024-04-29 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1778 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-29 16:00 | 2024-04-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-337 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-30 07:00 | 2024-04-30 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-577 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Yass Jct | Down Main | 2024-04-30 07:00 | 2024-04-30 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Goulburn Clr 101 pts to Yass YJ1 Sig | Pilot Staff Working | 2023-03-15
IPR-1860 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-30 12:00 | 2024-04-30 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-338 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-01 07:00 | 2024-05-01 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-578 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Galong | Yass Jct | Down Main | 2024-05-01 07:00 | 2024-05-01 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr 3E pts to Yass YJ20 Sig | Pilot Staff Working | 2023-03-15
IPR-2324-339 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-02 07:00 | 2024-05-02 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-579 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Harden | Galong | Up Main | 2024-05-02 07:00 | 2024-05-02 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr C Frame to Harden Clr 105 pts | Pilot Staff Working | 2023-03-15
IPR-2324-340 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-03 07:00 | 2024-05-03 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-580 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Galong | Harden | Down Main | 2024-05-03 07:00 | 2024-05-03 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr E Frame to Harden 103 pts | Pilot Staff Working | 2023-03-15
IPR-2324-5 | 2022-07-26 | Supported |  |  | 1 | Config 10-A | Cooks River | Chullora Jct | All Tracks | 2024-05-04 02:00 | 2024-05-06 02:00 | 48:00 | Config-10B | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​​WE45 Config 10B | Andrew Duncan | Deane Thrower | Cooks River to Chullora Junction (Config-10B) |  | 2022-06-23
IPR-2324-581 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Jindalee | Harden | Up Main | 2024-05-04 07:00 | 2024-05-04 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Jindalee CA05 Sig to Harden HN28 Sig | Pilot Staff Working | 2023-03-15
IPR-2324-433 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-05 00:05 | 2024-05-05 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-113 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-05-05 07:00 | 2024-05-27 14:00 | 535:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-2324-582 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Harden | Jindalee | Down Main | 2024-05-05 07:00 | 2024-05-05 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Jindalee CA03 Sig to Harden Clr 105 pts | Pilot Staff Working | 2023-03-15
IPR-2324-329 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-06 07:00 | 2024-05-06 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1779 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-06 16:00 | 2024-05-06 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-341 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-07 07:00 | 2024-05-07 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-342 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-08 07:00 | 2024-05-08 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-343 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-09 07:00 | 2024-05-09 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-344 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-10 07:00 | 2024-05-10 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-434 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-12 00:05 | 2024-05-12 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-330 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-13 07:00 | 2024-05-13 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1780 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-13 16:00 | 2024-05-13 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-345 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-14 07:00 | 2024-05-14 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-346 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-15 07:00 | 2024-05-15 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-347 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-16 07:00 | 2024-05-16 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-348 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-17 07:00 | 2024-05-17 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-435 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-19 00:05 | 2024-05-19 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-331 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-20 07:00 | 2024-05-20 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1781 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-20 16:00 | 2024-05-20 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-349 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-21 07:00 | 2024-05-21 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-350 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-22 07:00 | 2024-05-22 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-351 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-23 07:00 | 2024-05-23 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-352 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-24 07:00 | 2024-05-24 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-436 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-26 00:05 | 2024-05-26 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-332 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-27 07:00 | 2024-05-27 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1782 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-27 16:00 | 2024-05-27 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-453 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-06-01 02:00 | 2024-06-02 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-3 | 2022-07-26 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2024-06-01 06:00 | 2024-06-02 18:00 | 36:00 | Config-16 | North - South | Moss Vale to Unanderra | WE49 ​Closedown LPA | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-437 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-02 00:05 | 2024-06-02 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1783 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-03 16:00 | 2024-06-03 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-2 | 2022-07-26 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Tracks | 2024-06-08 09:00 | 2024-06-10 17:00 | 56:00 | Config-9 | North - South | Telarah to Acacia Ridge | WE50 ​Closedown LPA | Andrew Duncan | Peter Lee | Telarah - Acacia Ridge |  | 2022-06-23
IPR-2324-438 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-09 00:05 | 2024-06-09 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1784 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-10 16:00 | 2024-06-10 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-454 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-06-15 02:00 | 2024-06-16 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-79 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-06-15 22:00 | 2024-06-16 06:00 | 8:00 | RCP Under track Crossing | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-09
IPR-2324-439 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-16 00:05 | 2024-06-16 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1785 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-17 16:00 | 2024-06-17 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-440 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-23 00:05 | 2024-06-23 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1786 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-24 16:00 | 2024-06-24 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-80 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-06-29 22:00 | 2024-06-30 06:00 | 8:00 | RCP Under track Crossing | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-07
IPR-2324-441 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-30 00:05 | 2024-06-30 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1790 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2024-07-27 02:00 | 2024-07-29 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1797 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-08-03 08:00 | 2024-08-04 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1972 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-08-05 03:00 | 2024-08-05 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1794 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-08-07 06:00 | 2024-08-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1894 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Manor Loop | Serviceton | All Tracks | 2024-08-24 06:00 | 2024-08-26 18:00 | 60:00 | Major Maintenance | East - West | Tottenham to Serviceton | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1895 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Serviceton | Belair | All Tracks | 2024-08-24 09:00 | 2024-08-26 21:00 | 60:00 | Major Maintenance | East - West | Serviceton to Islington (SA) | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1874 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Mile End | Islington | Main Line | 2024-08-24 13:00 | 2024-08-27 06:00 | 65:00 | TRJ Project Commissioning | East - West | Serviceton to Islington (SA) | ​Torrens Junction Signalling Upgrade Project - Arrangements to be made to operate Sunday Ghan Service 1AD8 | Bryce Gore | Michael Iannella | Islington Signal 33 to Mile End Signal 44 |  | 2023-11-21
IPR-1973 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-09-09 03:00 | 2024-09-09 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1801 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-09-20 22:30 | 2024-09-23 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1807 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2024-09-21 00:01 | 2024-09-23 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1808 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1811 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1813 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Somerton (Exclusive) to Tottenham (Exclusive) | AO | 2023-11-10
IPR-1798 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-11-02 08:00 | 2024-11-03 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1792 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2024-11-09 02:00 | 2024-11-11 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1802 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-11-22 22:30 | 2024-11-25 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1806 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2024-11-23 06:00 | 2024-11-24 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1795 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-12-07 06:00 | 2024-12-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1799 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-02-08 08:00 | 2025-02-09 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1791 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2025-02-15 02:00 | 2025-02-17 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1803 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-03-28 22:30 | 2025-03-31 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1810 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2025-03-29 00:01 | 2025-03-31 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1809 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1812 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1814 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Somerton (Exclusive) | AO | 2023-11-10
IPR-1796 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2025-04-12 06:00 | 2025-04-13 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1804 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-05-02 22:30 | 2025-05-05 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1805 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2025-05-03 06:00 | 2025-05-04 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1800 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-05-17 08:00 | 2025-05-18 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1793 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2025-06-28 02:00 | 2025-06-30 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15

## NSW & QLD Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Possession Limits | Safeworking Requirements | Date Submitted
IPR-2324-1536 | 2023-09-25 | Cancelled |  |  | 1 | Total Possession | Wagga Wagga | Bomen | Main | 2023-11-25 05:30 | 2023-11-25 13:00 | 7:30 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Possession Impacts 9331 (Cancel or Lift 70") & 7MW7 (Delay 4.5 hours) | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-548 | 2022-12-20 | Approved | 1366-2023 | 2023-11-10 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-11-25 11:00 | 2023-11-25 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-1537 | 2023-09-25 | Cancelled |  |  | 1 | Total Possession | Wagga Wagga | Bomen | Main | 2023-11-26 05:30 | 2023-11-26 11:30 | 6:00 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Possession Impacts 7SM2 (delay 3.5hrs & 7WM7 (Delay 1 hour) | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-1754 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-26 06:00 | 2023-11-26 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1538 | 2023-09-25 | Cancelled |  |  | 3 | Window Possession | Wagga Wagga | Bomen | Main | 2023-11-27 05:30 | 2023-11-27 13:00 | 7:30 | Rerailing on Viaduct | North - South | Junee to Albury | Rerail Viaducts 3 & 4 in Preparation for Re-Transom Works that will remove 1.6km TSR Works need to be completed in early morning to avoid extreme heat. Windows between MTP Services | Andrew Duncan | Adrian Unwin | Wagga to Bomen | TOA | 2023-09-18
IPR-2324-1533 | 2023-09-22 | Approved | 1419-2023 | 2023-11-10 | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2023-11-27 06:00 | 2023-12-16 18:00 | 468:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2023-09-12
IPR-2324-1755 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-27 06:00 | 2023-11-27 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1462 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-11-27 13:00 | 2023-11-27 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1413 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-11-27 16:00 | 2023-11-27 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1756 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-28 06:00 | 2023-11-28 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1757 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-29 06:00 | 2023-11-29 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1758 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-11-30 06:00 | 2023-11-30 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1759 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-01 06:00 | 2023-12-01 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-20 | 2022-07-26 | Approved | 1454-2023 | 2023-11-17 | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2023-12-02 02:30 | 2023-12-03 22:30 | 44:00 | Config-16 | North - South | Moss Vale to Unanderra | WE23 ​Closedown LPA | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-1760 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-02 06:00 | 2023-12-02 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-549 | 2022-12-20 | Approved | 1453-2023 | 2023-11-17 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-02 11:00 | 2023-12-02 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-1761 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-03 06:00 | 2023-12-03 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1733 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 06:00 | 2023-12-04 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1622 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-04 07:30 | 2023-12-04 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1734 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 10:30 | 2023-12-04 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1463 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-04 13:00 | 2023-12-04 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1735 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 14:00 | 2023-12-04 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1414 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-04 16:00 | 2023-12-04 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1736 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 06:00 | 2023-12-05 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1623 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-05 07:30 | 2023-12-05 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1737 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 10:30 | 2023-12-05 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1738 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 13:00 | 2023-12-05 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1624 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-06 07:30 | 2023-12-06 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1625 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-07 07:30 | 2023-12-07 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1626 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-08 07:30 | 2023-12-08 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-550 | 2022-12-20 | Approved | 1458-2023 | 2023-11-17 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-09 11:00 | 2023-12-09 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-1739 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 06:00 | 2023-12-11 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1629 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-11 07:30 | 2023-12-11 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1740 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 10:30 | 2023-12-11 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1464 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-11 13:00 | 2023-12-11 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IP-2324-1596 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2023-12-11 13:00 | 2023-12-11 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1741 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 14:00 | 2023-12-11 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1415 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-11 16:00 | 2023-12-11 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1762 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-12 03:30 | 2023-12-12 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1742 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 06:00 | 2023-12-12 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1630 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-12 07:30 | 2023-12-12 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1743 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 10:30 | 2023-12-12 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1744 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 13:00 | 2023-12-12 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1763 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-13 03:30 | 2023-12-13 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1631 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-13 07:30 | 2023-12-13 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1764 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-14 03:30 | 2023-12-14 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1632 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-14 07:30 | 2023-12-14 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1642 | 2023-10-25 | Cancelled |  |  | 1 | Total Possession | Goobang Jct | Goobang Jct North | Main Line | 2023-12-14 12:45 | 2023-12-14 22:45 | 10:00 | Level Crossing Removal | East - West | Goobang Junction to Broken Hill;#Cootamundra West to Goobang Junction | No Train Period during Possession. | Andrew Duncan | Chan Sarai |  |  | 2023-10-05
IPR-2324-1765 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-15 03:30 | 2023-12-15 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1633 | 2023-10-05 | Approved | 1457-2023 | 2023-11-10 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany Road 3 + 4 | 2023-12-15 07:30 | 2023-12-15 08:00 | 0:30 | BRD | North - South | Port Botany to Marrickville Jct | No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-10-05
IPR-2324-1643 | 2023-10-25 | Cancelled |  |  | 1 | Total Possession | Goobang Jct | Goobang Jct North | Main Line | 2023-12-15 12:45 | 2023-12-15 22:45 | 10:00 | Level Crossing Removal (Contingency) | East - West | Goobang Junction to Broken Hill;#Cootamundra West to Goobang Junction | No Train Period during Possession. | Andrew Duncan | Chan Sarai |  |  | 2023-10-05
IPR-2324-1766 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-16 03:30 | 2023-12-16 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-551 | 2022-12-20 | Approved | 1459-2023 | 2023-11-24 | 1 | Maintenance Window | Macarthur | Moss Vale | Up and Down Mains | 2023-12-16 11:00 | 2023-12-16 16:00 | 5:00 | Weekly Maintenance Window | North - South | Macarthur to Moss Vale | ​​Weekly Maintenance Window (Clear of Moss Vale Yard) | Andrew Duncan | Curtis McClelland |  |  | 2022-12-21
IPR-2324-1768 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-18 03:30 | 2023-12-18 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1465 | 2023-09-07 | Approved | 0075-2023 | 2023-09-07 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2023-12-18 13:00 | 2023-12-18 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-2324-1416 | 2023-08-24 | Approved | 1265-2023 | 2023-09-14 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2023-12-18 16:00 | 2023-12-18 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1767 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-19 03:30 | 2023-12-19 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-461 | 2022-12-21 | Pending |  |  | 5 | Window Possession | Cooks River | Enfield | Up and Down Goods | 2023-12-23 02:00 | 2024-01-08 22:00 | 404:00 | Sydney Metro Southwest | North - South | Sydney MFN | Possessions to be taken ATP on Up Goods LineWindow Possessions advertised on TAA 1484-2023 for Down Goods Line | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1535 | 2023-09-25 | Approved | 1460-2023 | 2023-11-24 | 1 | Total Possession | Enfield West | Enfield West | The Goods Line | 2023-12-23 02:00 | 2024-01-05 02:00 | 312:00 | Sydney Trains Protection | North - South | Sydney MFN | No trains impacted due to already occurring Sydney Trains Possession. No ad-hocs through possession area. No impacts to SSFL. | Andrew Duncan | Deane Thrower | SP3 Signal to EW420 Signal |  | 2023-09-06
IPR-2324-456 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 06:00 | 2023-12-27 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1750 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 08:00 | 2023-12-27 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1751 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 14:10 | 2023-12-27 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1903 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 06:00 | 2023-12-28 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1906 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 08:00 | 2023-12-28 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1908 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 14:10 | 2023-12-28 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1904 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 06:00 | 2023-12-29 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1907 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 08:00 | 2023-12-29 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1909 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 14:10 | 2023-12-29 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1905 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 06:40 | 2023-12-30 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1910 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 10:30 | 2023-12-30 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1911 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-31 09:20 | 2023-12-31 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1912 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 08:00 | 2024-01-01 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1921 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 14:10 | 2024-01-01 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1913 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 06:00 | 2024-01-02 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1917 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 08:00 | 2024-01-02 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1922 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 14:10 | 2024-01-02 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1914 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 06:00 | 2024-01-03 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1918 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 08:00 | 2024-01-03 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1923 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 14:10 | 2024-01-03 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1915 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 06:00 | 2024-01-04 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1919 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 08:00 | 2024-01-04 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1924 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 14:10 | 2024-01-04 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1916 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 06:00 | 2024-01-05 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1920 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 08:00 | 2024-01-05 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1925 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 14:10 | 2024-01-05 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1926 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 06:40 | 2024-01-06 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1430 | 2023-08-24 | Approved | 0009-2024 |  | 2 | Total Possession | Marulan | Goulburn | Down Main | 2024-01-06 10:20 | 2024-01-06 16:30 | 6:10 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​Date changed to avoid additional service impacts ​CriticalCompliance Testing Pilot Staff Working to be Implemented via Up Main Train Alterations Required, NO Cancellations Impacts to: NSWTL: SP33PN: 4PS6, 3924, 1225, 2128, 9327, 9323QUBE: 7MW7 | John Hilton | David Knee | Marulan: Clear of E Frame to Goulburn: Clear of 135 Points | LPA with PSW | 2023-08-21
IPR-1928 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 10:30 | 2024-01-06 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1930 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-07 09:20 | 2024-01-07 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1427 | 2023-08-24 | Approved | 0006-2024 |  | 2 | Total Possession | Wingello | Marulan | Down Main | 2024-01-07 10:30 | 2024-01-07 17:00 | 6:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Up Main Train Alterations Required, No Cancellations Impacts to: NSWTL: SP34, SP33 PN: 2290, 9327, 3924, 1297, 2226 | John Hilton | David Knee | Wingello: Clear of D Frame to Marulan: Clear of E Frame | LPA with PSW | 2023-08-21
IPR-1932 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 08:00 | 2024-01-08 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1428 | 2023-08-24 | Approved | 0007-2024 |  | 1 | Total Possession | Moss Vale | Penrose | Down Main | 2024-01-08 09:40 | 2024-01-08 13:00 | 3:20 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing NO Pilot Staff Working to be Implemented Train Alterations & Cancellations Required 1311 (Qube) Delay1297 (PN) Delay1225 (PN) Delay2225 (PN) Cancel | John Hilton | David Knee | Moss Vale: MV69 Signal to Penrose: 170.9 Signal | TOA: Moss Vale to Penrose May require extension to MY1 to Off-track from 12:00 - 12:30 | 2023-08-21
IPR-2324-1468 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-08 13:00 | 2024-01-08 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2023-08-10
IPR-1935 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 14:10 | 2024-01-08 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1432 | 2023-08-24 | Approved | 0007-2024 |  | 1 | Total Possession | Penrose | Moss Vale | Up Main | 2024-01-08 15:00 | 2024-01-08 17:40 | 2:40 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​Critical Compliance Testing NO Pilot Staff Working to be Implemented Train Alterations & Cancellations Required 2226 (PN) - Cancel2MW7 (Qube) Amend2120 (PN)- Amend2128 (PN) - Delay | John Hilton | David Knee | Penrose: Signal PE2 to Moss Vale: MV60 Signal | TOA: Penrose to Moss Vale via Up Refuge Will require to transition to Down Refuge at end of Window to Off-Track | 2023-08-21
IPR-2324-1417 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-08 16:00 | 2024-01-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1938 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 06:00 | 2024-01-09 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1941 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 08:00 | 2024-01-09 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1429 | 2023-08-24 | Approved | 0008-2024 |  | 1 | Total Possession | Marulan | Wingello | Up Main | 2024-01-09 08:15 | 2024-01-09 13:30 | 5:15 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Down Main Train Alterations and Cancellations Required. Impacts to: NSWTL: SP32, SP31, ST23 (All incur delays)PN: 3930 (Cancel), 3922 (Cancel), 2126 (Amend), 2225 (Cancel), 2226 (Cancel), 7PS6 (Delay 100" at Goulburn), 1225 (Amend), 1297 (Amend)Qube: 1311 (Delay)Aurizon: 3SM1 (Delay) | John Hilton | David Knee | Marulan: Clear of E Frame to Wingello: Clear of D Frame | LPA with PSW | 2023-08-21
IPR-1944 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 14:10 | 2024-01-09 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1947 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 06:00 | 2024-01-10 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1950 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 08:00 | 2024-01-10 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1431 | 2023-08-24 | Approved | 0010-2024 |  | 2 | Total Possession | Marulan | Goulburn | Up Main | 2024-01-10 10:00 | 2024-01-10 17:00 | 7:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Pilot Staff Working to be Implemented via Down Main Train Alterations and Cancellations Required Impacts to: NSWTL: SP34, SP33 (Delays)PN: 3922 (Delays), 2PS7 (Lift 80min), 3924 (Cancel), 1225 (Delays), 9327 (Delays), 4BM4 (Delays), 2128 (Delays), 2120 (Delays)QUBE: 1311 (Delays), 5MW7 (Delays), 5SM7 (Delays)SCT: 4BM9 (Delays) | John Hilton | David Knee | Goulburn: Clear of 130 Points to Marulan: Clear of D Frame | LPA with PSW | 2023-08-21
IPR-1953 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 14:10 | 2024-01-10 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1882 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-10 18:00 | 2024-01-11 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1956 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 06:00 | 2024-01-11 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1959 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 08:00 | 2024-01-11 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1425 | 2023-08-24 | Approved | 0004-2024 |  | 1 | Total Possession | Moss Vale | Medway Jct | Down Main | 2024-01-11 10:00 | 2024-01-11 13:00 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations and Cancellations RequiredImpacts to 1225, 1297, 1311 (All Delay)2225 & 2226 (Cancel) | John Hilton | David Knee | Moss Vale to Medway Junction | TOA | 2023-08-21
IPR-1896 | 2023-08-24 | Approved | 0004-2024 |  | 1 | Total Possession | Lynwood | Medway Jct | Up Main | 2024-01-11 10:00 | 2024-01-11 13:00 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations Required to 2128 | John Hilton | David Knee | Lynwood to Medway Junction | TOA | 2023-08-21
IPR-1962 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 14:10 | 2024-01-11 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1883 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-11 18:00 | 2024-01-12 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1965 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 06:00 | 2024-01-12 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1967 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 08:00 | 2024-01-12 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1426 | 2023-08-24 | Approved | 0005-2024 |  | 2 | Total Possession | Moss Vale | Wingello | Up Main | 2024-01-12 10:30 | 2024-01-12 13:00 | 2:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations Required Impacts to 3922 (Lift)2126 (Lift)2928 (Delay)2290 (Delay) | John Hilton | David Knee | Medway to Moss Vale | TOA | 2023-08-21
IPR-1969 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 14:10 | 2024-01-12 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1884 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-12 18:00 | 2024-01-13 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1927 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 06:40 | 2024-01-13 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1436 | 2023-08-24 | Approved | 0052-2024 | 2023-11-23 | 3 | Window Possession | Moss Vale | Berrima Jct | Up Main, Up Refuge | 2024-01-13 10:00 | 2024-01-13 18:00 | 8:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn;#Macarthur to Moss Vale | ​​CriticalCompliance Testing No Ad Hoc Services, Unhealthy services may be delayed. No Direct Impact to MTP Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-2324-1437 | 2023-08-24 | Approved | 0052-2024 | 2023-11-23 | 3 | Window Possession | Moss Vale | Berrima Jct | Down Main, Down Refuge | 2024-01-13 10:00 | 2024-01-13 18:00 | 8:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn;#Macarthur to Moss Vale | ​​CriticalCompliance Testing No Ad Hoc Services, Unhealthy services may be delayed. No Direct Impact to MTP Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1929 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 10:30 | 2024-01-13 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-387 | 2022-12-21 | Cancelled |  |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-13 11:30 | 2024-01-13 15:30 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​​​4 hour Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. There is access to Moorebank Terminal from the South | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-11-25
IPR-1885 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-13 18:00 | 2024-01-14 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-2324-1433 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Goulburn | Joppa Jct | Down Main | 2024-01-14 06:30 | 2024-01-14 09:30 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1931 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-14 09:20 | 2024-01-14 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1434 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Gunning | Joppa Jct | Up Main | 2024-01-14 09:30 | 2024-01-14 11:30 | 2:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-2324-1435 | 2023-08-24 | Approved | 0053-2024 | 2023-11-23 | 3 | Window Possession | Joppa Jct | Goulburn | Up Main, Up Refuge | 2024-01-14 09:30 | 2024-01-14 13:00 | 3:30 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance TestingNo Ad Hoc Services No Impact to Healthy Mandatory Services | John Hilton | David Knee |  | TOA | 2023-08-21
IPR-1886 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-14 18:00 | 2024-01-15 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1893 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Cooks River | Cooks River | Cooks River Loop | 2024-01-15 06:00 | 2024-01-26 02:00 | 260:00 | Stabling Track Machines | North - South | Port Botany to Marrickville Jct | Cooks River Loop will be unavailable for movements or stowing wagons. | Andrew Duncan | Jensen Kelly | C/O 788A to C/O 787B points |  | 2023-11-23
IPR-2324-111 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-01-15 07:00 | 2024-01-26 14:00 | 271:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-1933 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 08:00 | 2024-01-15 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1469 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-15 13:00 | 2024-01-15 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1597 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-01-15 13:00 | 2024-01-15 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-1936 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 14:10 | 2024-01-15 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1418 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-15 16:00 | 2024-01-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1887 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-15 18:00 | 2024-01-16 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1939 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 06:00 | 2024-01-16 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1942 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 08:00 | 2024-01-16 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1945 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 14:10 | 2024-01-16 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1888 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-16 18:00 | 2024-01-17 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1948 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 06:00 | 2024-01-17 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1951 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 08:00 | 2024-01-17 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1954 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 14:10 | 2024-01-17 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1889 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Forbes | Parkes | Main Line | 2024-01-17 18:00 | 2024-01-18 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1957 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 06:00 | 2024-01-18 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1960 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 08:00 | 2024-01-18 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1963 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 14:10 | 2024-01-18 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1890 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Gunningbland | Gunningbland | Main Line | 2024-01-18 18:00 | 2024-01-19 06:00 | 12:00 | Track Resurfacing | East - West | Goobang Junction to Broken Hill | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1966 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 06:00 | 2024-01-19 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1968 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 08:00 | 2024-01-19 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1970 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 14:10 | 2024-01-19 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1891 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-19 18:00 | 2024-01-20 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-2324-1686 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Cooks River | Cooks River | Up Botany + Cooks Loop | 2024-01-19 22:00 | 2024-01-20 02:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | CR736G Signal TO C/O 790pts |  | 2023-10-06
IPR-2324-1688 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Port Botany Yard | Port Botany Yard | Road 4 + Gelco Siding | 2024-01-19 22:00 | 2024-01-20 02:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | C/O 150pts TO BY15 Signal |  | 2023-10-06
IPR-2324-1787 | 2022-07-26 | Supported |  |  | 1 | Config 10-C | Port Botany Yard | Cooks River | All Tracks | 2024-01-19 22:00 | 2024-01-22 06:00 | 56:00 | Config-10C | North - South | Port Botany to Marrickville Jct | BRD Final CommissioningNo Access to Boral or Cooks River | Andrew Duncan | Jensen Kelly | Port Botany to Cooks River |  | 2022-06-23
IPR-2324-19 | 2022-07-26 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Tracks | 2024-01-20 02:00 | 2024-01-22 02:00 | 48:00 | Config-10A | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​WE30 Config 10A | Andrew Duncan | Deane Thrower | Cooks River to Flemington Junction and Enfield West |  | 2022-06-23
IPR-2324-466 | 2023-04-26 | Cancelled |  |  | 3 | Window Possession | Leightonfield | Glenfield | SSFL | 2024-01-20 02:00 | 2024-01-21 23:00 | 45:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​Windows (min. 4 hours) will be identified and advertised after finalisation of the WE30 train plan. Ad hoc paths may be considered for approval with notice to the Interstate Possessions team. Access to Moorebank will be available from the south only. | Andrew Duncan | Daniel Wakefield | Leightonfield LF11 and LF14 to Glenfield GF16, GF18 and GF22. |  | 2023-01-18
IPR-1825 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-20 09:00 | 2024-01-20 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSFL and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-1892 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-20 18:00 | 2024-01-21 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1826 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-21 09:00 | 2024-01-21 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSLF and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-2324-1689 | 2023-10-25 | Pending |  |  | 3 | Window Possession | Cooks River | Cooks River | Up Botany + Cooks Loop | 2024-01-22 02:00 | 2024-01-22 06:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | CR736G Signal TO C/O 790pts |  | 2023-10-06
IPR-2324-1690 | 2023-10-25 | Pending |  |  | 3 | Window Possession | Port Botany Yard | Port Botany Yard | Road 4 + Gelco Siding | 2024-01-22 02:00 | 2024-01-22 06:00 | 4:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs through window. Late/unhealthy mandatories may be held. | Andrew Duncan | Jensen Kelly | C/O 150pts TO BY15 Signal |  | 2023-10-06
IPR-1934 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 08:00 | 2024-01-22 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1470 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-22 13:00 | 2024-01-22 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-1937 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 14:10 | 2024-01-22 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1419 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-22 16:00 | 2024-01-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1657 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-22 22:00 | 2024-01-22 23:59 | 1:59 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1658 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-23 01:30 | 2024-01-23 02:30 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1659 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-23 04:00 | 2024-01-23 05:00 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-1940 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 06:00 | 2024-01-23 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1943 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 08:00 | 2024-01-23 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1946 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 14:10 | 2024-01-23 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1949 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 06:00 | 2024-01-24 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1952 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 08:00 | 2024-01-24 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1955 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 14:10 | 2024-01-24 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1660 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-24 22:00 | 2024-01-24 23:59 | 1:59 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1661 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-25 01:30 | 2024-01-25 02:30 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-2324-1662 | 2023-10-20 | Supported | 0011-2024 |  | 3 | Window Possession | Cooks River | Port Botany Yard | Up and Down Botany and Loop | 2024-01-25 04:00 | 2024-01-25 05:00 | 1:00 | BRD | North - South | Port Botany to Marrickville Jct | No ad hocs during possession. Late/unhealthy mandatories may be held until completion of works. Access to Cooks River and Boral is open. | Andrew Duncan | Jensen Kelly | CR742G,CR744G Signal to CR761G Signal |  | 2023-10-20
IPR-1958 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 06:00 | 2024-01-25 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1961 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 08:00 | 2024-01-25 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1964 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 14:10 | 2024-01-25 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-388 | 2023-09-25 | Supported |  |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-27 11:30 | 2024-01-27 15:30 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​​​4 hour Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. There is access to Moorebank Terminal from the South | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-11-25
IPR-2324-1111 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-01-29 06:00 | 2024-02-05 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-1471 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-01-29 13:00 | 2024-01-29 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1420 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-01-29 16:00 | 2024-01-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-18 | 2022-07-26 | Supported |  |  | 1 | Config 14 | Enfield West | Moss Vale | Main South | 2024-02-02 22:30 | 2024-02-05 02:00 | 51:30 | Config-14 | North - South | Macarthur to Moss Vale;#Southern Sydney Freight Line | WE32 ​LPA Closedown | Andrew Duncan | Deane Thrower | Glenlee to Berrima Junction (Exclusive) |  | 2022-06-23
IPR-2324-1449 | 2023-08-24 | Supported |  |  | 1 | Config 14 | Leightonfield | Glenfield | SSFL | 2024-02-02 22:30 | 2024-02-05 10:00 | 59:30 | Cabramatta Loop Commissioning | North - South | Southern Sydney Freight Line | ​In conjunction with WE32 Config 14 Possession. To Facilitate Commissioning of Cabramatta Loop.Based on April 2023 Config 14 the following additional services will be impacted. 5PS6, 1MB4, 1MS2, 1WM7, 2124, 2192, T232, T233 | Andrew Duncan | Miguel Alcantara | Leightonfield to Glenfield on SSFL |  | 2022-06-23
IPR-2324-17 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-02-03 06:00 | 2024-02-03 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE32 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-552 | 2023-02-22 | Pending |  |  | 2 | Total Possession | Kiacatoo | Kiacatoo | Mainline | 2024-02-03 16:00 | 2024-02-04 03:30 | 11:30 | Culvert Renewal | East - West | Goobang Junction to Broken Hill | ​​Was 02 - 03 December | Bryce Gore | Kim Lawes | Kiacatoo Down YLB - Up YLB |  | 2023-02-21
IPR-2324-16 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-02-04 06:00 | 2024-02-04 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE32 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-1472 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-05 13:00 | 2024-02-05 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1421 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-05 16:00 | 2024-02-05 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-553 | 2023-02-22 | Pending |  |  | 2 | Total Possession | Kiacatoo | Kiacatoo | Mainline | 2024-02-10 16:00 | 2024-02-11 03:30 | 11:30 | Culvert Renewal | East - West | Goobang Junction to Broken Hill | ​​Was 09 - 12 December | Bryce Gore | Kim Lawes | Kiacatoo Down YLB - Up TLB |  | 2023-02-21
IPR-2324-1473 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-12 13:00 | 2024-02-12 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1598 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-02-12 13:00 | 2024-02-12 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1422 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-12 16:00 | 2024-02-12 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-459 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Cooks River | Enfield | Up and Down Goods | 2024-02-17 02:00 | 2024-02-18 22:00 | 44:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested windows on the Up and Down Goods lines aligned with the Sydenham-Sefton Closedown on the ST Network. This would prevent access to Cooks River and Botany, Enfield would be available from the South only. As at 4/1/23 this is under review by ARTC to determine suitable window to exclude ad hoc trains and possibly impact late/unhealthy mandatory services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-462 | 2022-12-21 | Pending |  |  | 5 | As Traffic Permits | Cooks River | Enfield | Up and Down Goods | 2024-02-17 02:00 | 2024-02-18 22:00 | 44:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested ad hoc windows on the Up and Down Goods as well as the advertised ones. These will be managed solely through the CAA process and will have no impact to services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1474 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-19 13:00 | 2024-02-19 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1423 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-19 16:00 | 2024-02-19 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-12 | 2022-07-26 | Supported | 0022-2024 |  | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2024-02-24 01:00 | 2024-02-25 23:00 | 46:00 | Config-16 | North - South | Moss Vale to Unanderra | Extended Config 16 PossessionRequest for Feedback Email sent 14/11/23 | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-1475 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-02-26 13:00 | 2024-02-26 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1424 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-02-26 16:00 | 2024-02-26 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-452 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-03-02 02:00 | 2024-03-03 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-1476 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-04 13:00 | 2024-03-04 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1770 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-04 16:00 | 2024-03-04 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-82 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Moss Vale | Goulburn | All Tracks | 2024-03-09 00:01 | 2024-03-11 18:00 | 65:59 | SHOO Project Works | North - South | Moss Vale to Goulburn | WE35 ​Construction of Passing Lanes at Joppa Junction and Werai. Other Corridor Works to be conducted | Andrew Duncan | Ewen Henderson | Moss Vale (Exclusive) to Joppa Junction (Inclusive) |  | 2022-09-19
IPR-2324-83 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Goulburn | Albury | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Various Corridor Maintenance & Enhancement Works | North - South | Goulburn to Junee;#Junee to Albury | ​WE35 ​60hr 'Super' Shut in alignment with Vic & North Coast NSW Possessions | Andrew Duncan | Deane Thrower | Goulburn (Exc) to Albury (Inc) |  | 2022-09-19
IPR-2324-84 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Cootamundra West | Forbes | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Various Corridor Maintenance & Enhancement Works | North - South | Cootamundra West to Goobang Junction | ​WE37 ​60hr 'Super' Shut in alignment with Vic & North Coast NSW Possessions | Andrew Duncan | Deane Thrower | Cootamundra West (Inclusive) to Forbes (DYLB) |  | 2022-09-19
IPR-2324-791 | 2023-06-26 | Supported |  |  | 1 | Total Possession | Leightonfield | Glenfield | SSFL | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | Commissioning Cabramatta Loop Project | North - South | Southern Sydney Freight Line | ​This is a contingency window only and if required, will be 12 hours continuous. Times will be determined at T-4 in order to add impact to the least amount of trains possible. | Andrew Duncan | Steven Chance |  |  | 2023-05-02
IPR-2324-1789 | 2023-11-15 | Supported |  |  | 1 | Total Possession | Forbes | Goobang Jct | All Tracks | 2024-03-09 06:00 | 2024-03-12 22:00 | 88:00 | Inland Rail Construction | North - South | Cootamundra West to Goobang Junction | ​Extended Possession for Inland Rail Construction Activities | Andrew Duncan | Chris Fay | Forbes (DYLB) to Goobang Junction (End TOW) | TOA | 2022-09-19
IPR-2324-14 | 2022-07-26 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Tracks | 2024-03-09 09:00 | 2024-03-10 17:00 | 32:00 | Config-9 | North - South | Telarah to Acacia Ridge | WE37 ​Closedown LPA | Andrew Duncan | Peter Lee | Telarah - Acacia Ridge |  | 2022-06-23
IPR-2324-1477 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-11 13:00 | 2024-03-11 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1771 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-11 16:00 | 2024-03-11 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-455 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-03-16 02:00 | 2024-03-17 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-112 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-03-18 07:00 | 2024-03-19 14:00 | 31:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-2324-1478 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-18 13:00 | 2024-03-18 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1599 | 2023-09-25 | Approved | 1322-2023 | 2023-11-03 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-03-18 13:00 | 2024-03-18 17:30 | 4:30 | Monthly Maintenance Window | North - South | Southern Sydney Freight Line | Maintenance Window aligns with current Cabramatta Loop Project Monday windows. | Andrew Duncan | Daniel Wakefield | EW401 Signal to LF12 Signal |  | 2023-09-08
IPR-2324-1772 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-18 16:00 | 2024-03-18 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1115 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-03-19 06:00 | 2024-03-26 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-11 | 2022-07-26 | Supported |  |  | 1 | Config 10-B | Cooks River | Chullora Jct | All Tracks | 2024-03-23 02:00 | 2024-03-25 02:00 | 48:00 | Config-10B | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​​WE39 Config 10B | Andrew Duncan | Deane Thrower | Cooks River to Chullora Junction (Config-10B) |  | 2022-06-23
IPR-2324-1479 | 2023-09-25 | Supported | 0001-2024 |  | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-03-25 13:00 | 2024-03-25 17:30 | 4:30 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. | Andrew Duncan | Daniel Wakefield | LF13, LF11 to GF22, 18, 16. | LPA | 2022-12-01
IPR-2324-1773 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-25 16:00 | 2024-03-25 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1775 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-08 16:00 | 2024-04-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-457 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Cooks River | Enfield | Up and Down Goods | 2024-04-14 02:00 | 2024-04-24 22:00 | 260:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested windows on the Up and Down Goods lines aligned with the Sydenham-Sefton Closedown on the ST Network. This would prevent access to Cooks River and Botany, Enfield would be available from the South only. As at 4/1/23 this is under review by ARTC to determine suitable window to exclude ad hoc trains and possibly impact late/unhealthy mandatory services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-463 | 2022-12-21 | Pending |  |  | 5 | As Traffic Permits | Cooks River | Enfield | Up and Down Goods | 2024-04-14 02:00 | 2024-04-24 22:00 | 260:00 | Sydney Metro Southwest | North - South | Sydney MFN | ​​TfNSW have requested ad hoc windows on the Up and Down Goods as well as the advertised ones. These will be managed solely through the CAA process and will have no impact to services. | John Hilton | Steven Payne | 5.700km to 12.300 km. JD note - this looks to be approx CR711G & CR718G Signals to ED101D and G12.8 Signals at the boundary of Sydney 1 and 2 NC boards |  | 2022-12-15
IPR-2324-1112 | 2022-12-21 | Supported |  |  | 6 | Advice Only | Albury | Albury | 8 Gantry Road | 2024-04-15 06:00 | 2024-04-22 11:30 | 173:30 | NSW Trains stow on Friday (TBC by NSW Trains at T-4 weeks) and depart Monday (TBC by NSW Trains at T-4 weeks) | North - South | Junee to Albury | ​No defective rollingstock can be left in 8 Gantry Road during this time period. | Andrew Duncan | Jenny Dray |  |  | 2022-11-10
IPR-2324-1776 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-15 16:00 | 2024-04-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-573 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Marulan | Wingello | Up Main | 2024-04-17 07:00 | 2024-04-17 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Marulan Clr E Frame to Wingello Clr C Frame | Pilot Staff Working | 2023-03-15
IPR-2324-574 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Wingello | Bundanoon | Up Main | 2024-04-18 07:00 | 2024-04-18 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Wingello Clr D Frame to Bundanoon Clr C Frame | Pilot Staff Working | 2023-03-15
IPR-2324-1534 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Moss Vale | Bundanoon | Up Main | 2024-04-19 07:00 | 2024-04-19 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Bundanoon clear of B frame - Moss Vale MV84 | Pilot Staff Working | 2023-03-15
IPR-2324-9 | 2022-07-26 | Supported |  |  | 1 | Config 14 | Enfield West | Moss Vale | MS / SSFL | 2024-04-19 22:30 | 2024-04-22 02:00 | 51:30 | Config-14 | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | WE43 ​LPA Closedown | Andrew Duncan | Deane Thrower | Enfield West to Berrima Junction (Exclusive) via SSFL |  | 2022-06-23
IPR-2324-8 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-04-20 06:00 | 2024-04-20 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE43 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-7 | 2022-07-26 | Supported |  |  | 1 | Total Possession | Berrima Jct | Joppa Jct | Up and Down Mains | 2024-04-21 06:00 | 2024-04-21 18:00 | 12:00 | Config-14 | North - South | Moss Vale to Goulburn | WE43 Total Possession 0600-1800 Daily. All trains to be cancelled/ amended outside of these times | Andrew Duncan | Deane Thrower | Moss Vale (Inclusive) to Joppa Junction (Inclusive) |  | 2022-06-23
IPR-2324-575 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Marulan | Down Main | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | Railgrinding | North - South | Moss Vale to Goulburn | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Goulburn G75 Sig to Marulan Clr E frame | Pilot Staff Working | 2023-03-15
IPR-2324-1777 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-22 16:00 | 2024-04-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-576 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Joppa Jct | Up Main | 2024-04-23 07:00 | 2024-04-23 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | Grinding within Yard | John Hilton | Owen Blake |  | TOA | 2023-03-15
IPR-2324-124 | 2022-12-21 | Supported |  |  | 6 | Special Event | Cootamundra | Cootamundra | All Tracks | 2024-04-25 05:45 | 2024-04-25 06:30 | 0:45 | Anzac Day March | North - South | Goulburn to Junee | ​​No trains will be permitted through Cootamundra during the Anzac Day Dawn Service | Andrew Duncan | Andrew Duncan |  |  | 2022-11-10
IPR-2324-125 | 2022-04-26 | Supported |  |  | 6 | Special Event | Junee | Junee | All Tracks | 2024-04-25 10:40 | 2024-04-25 11:00 | 0:20 | Anzac Day March | North - South | Goulburn to Junee | ​No trains will be permitted through Junee during the Anzac Day March | Andrew Duncan | Dean Rich |  |  | 2022-04-01
IPR-2324-126 | 2022-12-21 | Supported |  |  | 6 | Special Event | Cootamundra | Cootamundra | All Tracks | 2024-04-25 11:00 | 2024-04-25 12:00 | 1:00 | Anzac Day March | North - South | Goulburn to Junee | ​​No trains will be permitted through Cootamundra during the Anzac Day March | Andrew Duncan | Andrew Duncan |  |  | 2022-11-10
IPR-2324-1778 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-29 16:00 | 2024-04-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-577 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Goulburn | Yass Jct | Down Main | 2024-04-30 07:00 | 2024-04-30 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Goulburn Clr 101 pts to Yass YJ1 Sig | Pilot Staff Working | 2023-03-15
IPR-2324-578 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Galong | Yass Jct | Down Main | 2024-05-01 07:00 | 2024-05-01 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr 3E pts to Yass YJ20 Sig | Pilot Staff Working | 2023-03-15
IPR-2324-579 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Harden | Galong | Up Main | 2024-05-02 07:00 | 2024-05-02 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr C Frame to Harden Clr 105 pts | Pilot Staff Working | 2023-03-15
IPR-2324-580 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Galong | Harden | Down Main | 2024-05-03 07:00 | 2024-05-03 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Galong Clr E Frame to Harden 103 pts | Pilot Staff Working | 2023-03-15
IPR-2324-5 | 2022-07-26 | Supported |  |  | 1 | Config 10-A | Cooks River | Chullora Jct | All Tracks | 2024-05-04 02:00 | 2024-05-06 02:00 | 48:00 | Config-10B | North - South | Port Botany to Marrickville Jct;#Sydney MFN | ​​WE45 Config 10B | Andrew Duncan | Deane Thrower | Cooks River to Chullora Junction (Config-10B) |  | 2022-06-23
IPR-2324-581 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Jindalee | Harden | Up Main | 2024-05-04 07:00 | 2024-05-04 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Jindalee CA05 Sig to Harden HN28 Sig | Pilot Staff Working | 2023-03-15
IPR-2324-113 | 2022-12-21 | Supported |  |  | 3 | Advice Only | Port Botany Yard | Port Botany Yard | Gelco Siding | 2024-05-05 07:00 | 2024-05-27 14:00 | 535:00 | BRD Works | North - South | Port Botany to Marrickville Jct | ​Gelco Siding being used for storing track machines and conduct project works. | Andrew Duncan | Steven Chance | Clear of 151A Points to Clear of 152B Points |  | 2022-10-25
IPR-2324-582 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Harden | Jindalee | Down Main | 2024-05-05 07:00 | 2024-05-05 17:00 | 10:00 | Railgrinding | North - South | Goulburn to Junee | ​Pilot Staff Working. Actual times and location to be confirmed. | John Hilton | Owen Blake | Jindalee CA03 Sig to Harden Clr 105 pts | Pilot Staff Working | 2023-03-15
IPR-2324-1779 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-06 16:00 | 2024-05-06 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1780 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-13 16:00 | 2024-05-13 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1781 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-20 16:00 | 2024-05-20 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1782 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-27 16:00 | 2024-05-27 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-453 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-06-01 02:00 | 2024-06-02 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-3 | 2022-07-26 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | Single Main | 2024-06-01 06:00 | 2024-06-02 18:00 | 36:00 | Config-16 | North - South | Moss Vale to Unanderra | WE49 ​Closedown LPA | Andrew Duncan | Deane Thrower | Unanderra 1032 1034 Signals - Moss vale Clear of 131B AND 122A Points |  | 2022-06-23
IPR-2324-1783 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-03 16:00 | 2024-06-03 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-2 | 2022-07-26 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Tracks | 2024-06-08 09:00 | 2024-06-10 17:00 | 56:00 | Config-9 | North - South | Telarah to Acacia Ridge | WE50 ​Closedown LPA | Andrew Duncan | Peter Lee | Telarah - Acacia Ridge |  | 2022-06-23
IPR-2324-1784 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-10 16:00 | 2024-06-10 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-454 | 2022-05-23 | Supported |  |  | 6 | Advice Only | Acacia Ridge | Acacia Ridge | Main Line | 2024-06-15 02:00 | 2024-06-16 23:59 | 45:59 | Queensland Rail Closedown | North - South | Telarah to Acacia Ridge | ​No XPT Access to Queensland Rail Network. NT31 and NT32 will terminate and commence from Casino. NO TRACK POSSESSION ON ARTC NETWORK | Andrew Duncan | John Hilton | Not Applicable |  | 2022-05-23
IPR-2324-1785 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-17 16:00 | 2024-06-17 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1786 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-24 16:00 | 2024-06-24 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1790 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2024-07-27 02:00 | 2024-07-29 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1797 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-08-03 08:00 | 2024-08-04 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1794 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-08-07 06:00 | 2024-08-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1801 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-09-20 22:30 | 2024-09-23 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1807 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2024-09-21 00:01 | 2024-09-23 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1808 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1798 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-11-02 08:00 | 2024-11-03 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1792 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2024-11-09 02:00 | 2024-11-11 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1802 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-11-22 22:30 | 2024-11-25 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1806 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2024-11-23 06:00 | 2024-11-24 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1795 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-12-07 06:00 | 2024-12-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1799 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-02-08 08:00 | 2025-02-09 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1791 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2025-02-15 02:00 | 2025-02-17 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1803 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-03-28 22:30 | 2025-03-31 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1810 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2025-03-29 00:01 | 2025-03-31 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1809 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1796 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2025-04-12 06:00 | 2025-04-13 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1804 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-05-02 22:30 | 2025-05-05 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1805 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2025-05-03 06:00 | 2025-05-04 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1800 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-05-17 08:00 | 2025-05-18 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1793 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2025-06-28 02:00 | 2025-06-30 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15

## SA & WA Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Possession Limits | Safeworking Requirements | Date Submitted
IPR-2324-1667 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Bordertown | Keith | Mainline | 2023-11-24 07:00 | 2023-11-24 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1668 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Wirrega | Coombe | Mainline | 2023-11-25 07:00 | 2023-11-25 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1748 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-25 08:00 | 2023-11-25 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-1669 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Keith | Coonalpyn | Mainline | 2023-11-26 07:00 | 2023-11-26 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1749 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-26 09:00 | 2023-11-26 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-1670 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Tintinara | Coonalpyn | Mainline | 2023-11-27 07:00 | 2023-11-27 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1671 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Coonalpyn | Tailem Bend | Mainline | 2023-11-28 07:00 | 2023-11-28 17:00 | 10:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1610 | 2023-09-25 | Approved | 1485-2023 | 2023-11-03 | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2023-11-28 14:00 | 2023-11-28 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-09-20
IPR-2324-1672 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Coomandook | Murray Bridge | Mainline | 2023-11-29 08:00 | 2023-11-29 17:00 | 9:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1679 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-11-30 07:00 | 2023-11-30 15:00 | 8:00 | Pt Bonython Rd LX Upgrade | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1673 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Murray Bridge | Mount Barker | Mainline | 2023-11-30 07:20 | 2023-11-30 17:30 | 10:10 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-1680 | 2023-10-25 | Cancelled |  |  | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-01 07:00 | 2023-12-01 13:00 | 6:00 | Pt Bonython Rd LX Upgrade | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1674 | 2023-08-18 | Approved | 1506-2023 | 2023-11-09 | 3 | Window Possession | Mount Barker | Mount Lofty | Mainline | 2023-12-01 08:00 | 2023-12-01 17:00 | 9:00 | Ultrasonic Testing | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | David Knee |  |  | 2023-09-29
IPR-2324-638 | 2023-06-26 | Approved | 1511-2023 | 2023-11-09 | 2 | Total Possession | Snowtown | Redhill | Mainline | 2023-12-02 21:00 | 2023-12-03 11:00 | 14:00 | Underbridge Replacement 159.065km | East - West | Dry Creek to Crystal Brook | ​​No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-639 | 2023-04-26 | Approved | 1511-2023 | 2023-11-09 | 2 | Window Possession | Snowtown | Redhill | Mainline | 2023-12-03 23:00 | 2023-12-04 05:00 | 6:00 | Underbridge Replacement 159.065km | East - West | Dry Creek to Crystal Brook | ​No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-1691 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-04 07:00 | 2023-12-04 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1692 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-05 07:00 | 2023-12-05 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1593 | 2023-09-25 | Cancelled | 1313-2023 |  | 3 | Window Possession | Snowtown | Redhill | Main Line | 2023-12-05 09:20 | 2023-12-05 13:40 | 4:20 | Level Crossing Upgrade | North - South | Dry Creek to Crystal Brook | Level Crossing Upgrade - Lake View Road - 162.288kmNO Ad Hoc Services | Bryce Gore | Jessica Tai | Snowtown 24 Sig (146.586km) to Redhill 3 Sig (170.926km) |  | 2023-09-21
IPR-2324-1693 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-06 07:00 | 2023-12-06 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1681 | 2023-10-25 | Approved | 1535-2023 | 2023-11-21 | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-07 07:00 | 2023-12-07 15:00 | 8:00 | Pt Bonython Rd LX Upgrade and ATMS HiRail Testing | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1694 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-07 07:00 | 2023-12-07 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1682 | 2023-10-25 | Approved | 1535-2023 | 2023-11-21 | 3 | Window Possession | Roopena | Whyalla | Whyalla Line | 2023-12-08 07:00 | 2023-12-08 13:00 | 6:00 | Pt Bonython Rd LX Upgrade and ATMS HiRail Testing | East - West | Whyalla Line | No Adhoc Services | Bryce Gore | Simon Bower | Signal 20 Roopena to Down YLB Whyalla |  | 2023-10-23
IPR-2324-1695 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-08 07:00 | 2023-12-08 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1696 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-09 07:00 | 2023-12-09 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1697 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-10 07:00 | 2023-12-10 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1698 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-11 07:00 | 2023-12-11 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1584 | 2023-09-25 | Approved | 1312-2023 | 2023-11-22 | 2 | Total Possession | Coombe | Coombe | Main Line | 2023-12-12 05:30 | 2023-12-12 13:30 | 8:00 | Turnout Renewal | East - West | Serviceton to Islington (SA) | No Train Period 12 Pts (228.770km) Turnout Renewal. New V-Xing & Timbers - Was 5th Dec | Bryce Gore | Bonnar Mahains | Coombe Signals 14 & 15 to Coombe 16 |  | 2023-09-21
IPR-2324-1699 | 2023-10-25 | Approved | 1519-2023 | 2023-11-13 | 3 | Window Possession | Mingary | Thackaringa | Mainline | 2023-12-12 07:00 | 2023-12-12 17:00 | 10:00 | Embankment Works 343km to 345km | East - West | Broken Hill to Crystal Brook | No Adhoc Services | Bryce Gore | Bonnar Mahains | Signals 5 to 346 |  | 2023-10-23
IPR-2324-1585 | 2023-09-25 | Approved | 1312-2023 | 2023-11-22 | 2 | Total Possession | Coombe | Coombe | Main Line | 2023-12-12 14:30 | 2023-12-12 19:00 | 4:30 | Turnout Renewal | East - West | Serviceton to Islington (SA) | 12 Pts (228.770km) Turnout Renewal. New V-Xing & Timbers - Was 5th Dec Ad-Hoc services only permitted with Project Approval at least 3 days prior to start | Bryce Gore | Bonnar Mahains | Coombe Signals 14 & 15 to Coombe 16 |  | 2023-09-21
IPR-1897 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-13 14:00 | 2023-12-13 17:00 | 3:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-1898 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-16 15:00 | 2023-12-16 17:00 | 2:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-1827 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-08 14:30 | 2024-01-08 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1830 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-09 14:00 | 2024-01-09 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1829 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-10 14:00 | 2024-01-10 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1828 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-01-11 00:30 | 2024-01-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1831 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-13 08:00 | 2024-01-13 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1832 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-14 09:00 | 2024-01-14 20:30 | 11:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-824 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Wirrega | Wirrega | Mainline | 2024-01-15 05:00 | 2024-01-15 11:00 | 6:00 | Turnout renewal | East - West | Serviceton to Islington (SA) | ​Was 19th September 2023 | Bryce Gore | Bonnar Mahains | Wirrega Signals 14 & 15 to 16 |  | 2023-05-22
IPR-1833 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-15 14:30 | 2024-01-15 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-823 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Wirrega | Wirrega | Mainline | 2024-01-16 05:00 | 2024-01-16 14:00 | 9:00 | Turnout renewal | East - West | Serviceton to Islington (SA) | ​Was 18th September 2023​. | Bryce Gore | Bonnar Mahains | Wirrega Signals 14 & 15 to 16 |  | 2023-05-22
IPR-1834 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-16 14:30 | 2024-01-16 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1835 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-17 14:30 | 2024-01-17 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-636 | 2023-04-26 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-01-20 21:00 | 2024-01-21 11:00 | 14:00 | Underbridge Replacement 161.297km | East - West | Dry Creek to Crystal Brook | ​Was 23-24 Sep then 11-12 Nov | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-637 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-01-21 23:00 | 2024-01-22 05:00 | 6:00 | Underbridge Replacement 161.297km | East - West | Dry Creek to Crystal Brook | Was 24-25 Sep then 12-13 Nov | Bryce Gore | Kristen Xiao |  |  | 2023-04-21
IPR-2324-1700 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Balhannah | Balhannah | Main Line | 2024-01-23 10:30 | 2024-01-23 20:00 | 9:30 | Balhannah 20pts V-Crossing Upgrade | East - West | Serviceton to Islington (SA) | No Train Period - Was originally Ped crossing at Petwood | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-2324-1701 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-01-23 11:30 | 2024-01-23 20:30 | 9:00 | Netley Road LX Upgrade 93.019km | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-2324-1656 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-25 22:30 | 2024-01-26 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-1663 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-26 22:30 | 2024-01-27 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-1664 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-27 22:30 | 2024-01-28 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-1665 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mile End | Belair | Mainline | 2024-01-28 22:30 | 2024-01-29 04:30 | 6:00 | Re-railing | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Ruben De Vries |  |  | 2023-10-19
IPR-2324-1702 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Tailem Bend | Tailem Bend | Main Line | 2024-01-30 12:30 | 2024-01-30 21:00 | 8:30 | Magpie Drive LX Renewal at 122.335km | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Bonnar Mahains |  |  | 2023-10-23
IPR-1836 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-30 14:00 | 2024-01-30 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1837 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-31 14:00 | 2024-01-31 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1838 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-01 00:30 | 2024-02-01 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1839 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-03 08:00 | 2024-02-03 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1840 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-04 09:00 | 2024-02-04 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1841 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-05 14:30 | 2024-02-05 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1676 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-06 11:00 | 2024-02-06 22:00 | 11:00 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1842 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-06 14:00 | 2024-02-06 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1677 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-07 11:30 | 2024-02-07 14:00 | 2:30 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1843 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-07 14:00 | 2024-02-07 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1678 | 2023-10-25 | Cancelled |  |  | 2 | Total Possession | Pimba | Burando | Mainline | 2024-02-07 15:00 | 2024-02-07 17:30 | 2:30 | Pimba Rd LX Upgrade 180.939km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1844 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-08 00:30 | 2024-02-08 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1871 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Crystal Brook | Mainline | 2024-02-10 07:30 | 2024-02-10 13:00 | 5:30 | Drovers Rd LX Upgrade 4.722km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1865 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-10 21:00 | 2024-02-11 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1853 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-11 00:30 | 2024-02-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1866 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-11 23:00 | 2024-02-12 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-1683 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Port Augusta | Winninowie | Mainline | 2024-02-12 05:00 | 2024-02-12 11:00 | 6:00 | Harris St LX Upgrade | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-2324-1687 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Mambray Creek | Mambray Creek | Mainline | 2024-02-12 07:30 | 2024-02-12 12:00 | 4:30 | Mambray Creek 7pts and 20pts Renewal | East - West | Crystal Brook to Spencer Junction | No Train Period - Was 14/2 | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1845 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-13 14:00 | 2024-02-13 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1685 | 2023-10-25 | Pending |  |  | 3 | Total Possession | Mambray Creek | Mambray Creek | Mainline | 2024-02-14 05:00 | 2024-02-14 16:00 | 11:00 | Mambray Creek 7pts and 20pts Renewal | East - West | Crystal Brook to Spencer Junction | No Adhocs | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1846 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-14 14:00 | 2024-02-14 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1847 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-15 00:30 | 2024-02-15 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1872 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-16 06:00 | 2024-02-16 15:30 | 9:30 | Turnout replacement at 17 Points | East - West | Crystal Brook to Spencer Junction | ​Crossing Loop - No Access to Pt Germein Siding from Adelaide End | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-11-21
IPR-2324-1684 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-17 07:30 | 2024-02-17 13:00 | 5:30 | Coonamia 8pts Vee Crossing Upgrade | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-10-23
IPR-1849 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-17 08:00 | 2024-02-17 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1850 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-18 09:00 | 2024-02-18 13:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1586 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-18 15:00 | 2024-02-19 03:00 | 12:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-1851 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-19 14:30 | 2024-02-19 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1587 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-19 15:00 | 2024-02-19 20:00 | 5:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2324-1589 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Main Line | 2024-02-19 15:00 | 2024-02-20 03:00 | 12:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Main. Mandatory Trains to use Loop line when Loop not under Possession | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-1588 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-02-20 | 2024-02-20 03:00 | 3:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line. | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2324-880 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-20 06:00 | 2024-02-20 18:00 | 12:00 | Turnout replacement at 16 Points | East - West | Crystal Brook to Spencer Junction | ​Crossing Loop - No Access to Pt Germein Siding from Adelaide End - Was 14/11/2023 | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-06-21
IPR-1861 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 07:00 | 2024-02-20 11:15 | 4:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1862 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 11:45 | 2024-02-20 20:30 | 8:45 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-1590 | 2023-09-25 | Pending | 0002-2024 |  | 2 | Total Possession | Dry Creek | Dry Creek | Main Line | 2024-02-20 14:00 | 2024-02-21 03:00 | 13:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Main. Mandatory Trains to use Loop line when Loop not under Possession | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-1591 | 2023-09-25 | Pending | 0002-2024 |  | 3 | Window Possession | Dry Creek | Dry Creek | Loop | 2024-02-20 14:00 | 2024-02-20 19:30 | 5:30 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Ad Hoc Train Period | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-1852 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-20 14:00 | 2024-02-20 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1592 | 2023-09-25 | Pending | 0002-2024 |  | 3 | Window Possession | Dry Creek | Dry Creek | Loop | 2024-02-21 00:40 | 2024-02-21 03:40 | 3:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Ad Hoc Train Period | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2324-881 | 2023-06-26 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-21 06:00 | 2024-02-21 18:00 | 12:00 | Turnout replacement at 16 Points | East - West | Crystal Brook to Spencer Junction | No Access to Pt Germein Siding from Adelaide End - Was 15/11/2023 | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-06-21
IPR-1848 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-21 14:00 | 2024-02-21 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1857 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-22 00:30 | 2024-02-22 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1868 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-24 21:00 | 2024-02-25 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1867 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-25 23:00 | 2024-02-26 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-2324-1594 | 2023-09-25 | Pending | 0003-2024 |  | 2 | Total Possession | Torrens Jct | Torrens Jct | Main | 2024-02-26 10:40 | 2024-02-26 18:40 | 8:00 | Pedestrian Crossing Upgrade | East - West | Serviceton to Islington (SA) | Pedestrian Crossing Upgrade - Dudley Park Station - 6.353kmNo Train Period - Full Upgrade | Bryce Gore | Jessica Tai | Torrens Junction AN21 (3.042km) to Islington 30 (6.916km) |  | 2023-09-21
IPR-1854 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-27 14:00 | 2024-02-27 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1869 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-27 22:00 | 2024-02-28 09:00 | 11:00 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1856 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-28 14:00 | 2024-02-28 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1870 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-28 21:30 | 2024-02-29 08:00 | 10:30 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1855 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-29 00:30 | 2024-02-29 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1863 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-04 08:45 | 2024-03-04 19:00 | 10:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1864 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-05 07:00 | 2024-03-05 19:00 | 12:00 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1974 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-12 12:45 | 2024-03-13 01:45 | 13:00 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1975 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-13 10:45 | 2024-03-13 15:40 | 4:55 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1978 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 | 2024-03-20 12:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1979 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 19:00 | 2024-03-21 01:00 | 6:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | . | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1980 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-22 03:00 | 2024-03-22 15:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1981 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-23 03:00 | 2024-03-23 13:00 | 10:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1976 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-24 16:00 | 2024-03-25 04:00 | 12:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1977 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-25 21:00 | 2024-03-26 04:00 | 7:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1858 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-23 12:00 | 2024-04-23 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1859 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-27 11:00 | 2024-04-27 23:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1873 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-28 16:00 | 2024-04-29 04:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1860 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-30 12:00 | 2024-04-30 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1895 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Serviceton | Belair | All Tracks | 2024-08-24 09:00 | 2024-08-26 21:00 | 60:00 | Major Maintenance | East - West | Serviceton to Islington (SA) | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1874 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Mile End | Islington | Main Line | 2024-08-24 13:00 | 2024-08-27 06:00 | 65:00 | TRJ Project Commissioning | East - West | Serviceton to Islington (SA) | ​Torrens Junction Signalling Upgrade Project - Arrangements to be made to operate Sunday Ghan Service 1AD8 | Bryce Gore | Michael Iannella | Islington Signal 33 to Mile End Signal 44 |  | 2023-11-21

## VIC Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Possession Limits | Safeworking Requirements | Date Submitted
IPR-2324-1256 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main line | 2023-11-24 07:30 | 2023-11-24 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1257 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-25 07:30 | 2023-11-25 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-410 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-11-26 00:05 | 2023-11-26 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1258 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-26 07:30 | 2023-11-26 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1703 | 2023-10-25 | Approved | 1517-2023 | 2023-11-10 | 3 | Window Possession | Newport | Manor Loop | Mainline | 2023-11-27 07:00 | 2023-11-27 18:00 | 11:00 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Adhoc Traffic | Bryce Gore | Chan Sarai |  |  | 2023-10-23
IPR-2324-1259 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main line | 2023-11-27 07:30 | 2023-11-27 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1260 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-28 07:30 | 2023-11-28 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1704 | 2023-10-25 | Cancelled | 1517-2023 | 2023-11-10 | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-11-29 02:15 | 2023-11-29 07:45 | 5:30 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-10-23
IPR-2324-1261 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-29 07:30 | 2023-11-29 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1262 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-11-30 07:30 | 2023-11-30 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1263 | 2023-07-24 | Cancelled |  |  | 3 | Window Possession | McIntyre Loop | Tullamarine | Main Line | 2023-12-01 07:30 | 2023-12-01 17:00 | 9:30 | Maribymong Viaduct Bearing Works | East - West | Somerton to Tottenham Jct | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1982 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-02 21:30 | 2023-12-03 05:30 | 8:00 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-2324-411 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-03 00:05 | 2023-12-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1716 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-06 07:00 | 2023-12-06 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1717 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-07 07:00 | 2023-12-07 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1731 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-08 07:00 | 2023-12-08 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1983 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-09 00:01 | 2023-12-09 07:30 | 7:29 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-1824 | 2023-10-05 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-09 06:00 | 2023-12-09 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-05
IPR-2324-1721 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-09 07:00 | 2023-12-09 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1264 | 2023-07-24 | Cancelled |  |  | 2 | Total Possession | South Dynon | Sims St Jct | Main Line | 2023-12-09 22:30 | 2023-12-10 07:00 | 8:30 | DYN157, DYN155 and DYN Mixed Gauge Diamond Works | East - West | Melbourne Metro | ​No Train Period - Extension to Sunday morning Maintenance Window | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-412 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-10 00:05 | 2023-12-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1636 | 2023-10-05 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-10 06:00 | 2023-12-10 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-05
IPR-2324-1719 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-10 07:00 | 2023-12-10 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1637 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-11 06:00 | 2023-12-15 18:00 | 108:00 | Level Crossing Upgrades and Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period for continuous 5 day shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1649 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-11 06:00 | 2023-12-15 18:00 | 108:00 | Re-Sleepering | North - South | Benalla to Oakland Line | Total 5 Day Shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1720 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-11 07:00 | 2023-12-11 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1722 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-12 07:00 | 2023-12-12 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1818 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-13 07:00 | 2023-12-13 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1819 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-14 07:00 | 2023-12-14 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1820 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-15 07:00 | 2023-12-15 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1708 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-16 06:00 | 2023-12-16 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1821 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-16 07:00 | 2023-12-16 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1875 | 2023-11-20 | Approved | 1541-2023 | 2023-11-22 | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2023-12-16 15:00 | 2023-12-17 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-11-17
IPR-2324-413 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-17 00:05 | 2023-12-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1709 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-17 06:00 | 2023-12-17 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1822 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-17 07:00 | 2023-12-17 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1710 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-18 06:00 | 2023-12-18 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-1823 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-18 07:00 | 2023-12-18 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1711 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-19 06:00 | 2023-12-19 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1712 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-20 06:00 | 2023-12-20 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1713 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-21 06:00 | 2023-12-21 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1714 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-22 06:00 | 2023-12-22 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1715 | 2023-10-10 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-23 06:00 | 2023-12-23 18:00 | 12:00 | Re-sleepering Works | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-414 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-24 00:05 | 2023-12-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-415 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2023-12-31 00:05 | 2023-12-31 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-416 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-07 00:05 | 2024-01-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1730 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-09 07:00 | 2024-01-09 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 12th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-2324-1718 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-10 07:00 | 2024-01-10 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-2324-1769 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-11 07:00 | 2024-01-11 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-2324-417 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-14 00:05 | 2024-01-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1817 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-15 20:00 | 2024-01-16 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-1646 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Deep Lead | Great Western Loop | Main Line | 2024-01-16 06:00 | 2024-01-16 16:00 | 10:00 | Seaby St Subway Deck Subsidence Repairs | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Vernie Chong |  |  | 2023-10-12
IPR-1876 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-16 20:00 | 2024-01-17 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1877 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-17 20:00 | 2024-01-18 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1878 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-18 20:00 | 2024-01-19 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1879 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-19 20:00 | 2024-01-20 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1880 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-20 20:00 | 2024-01-21 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-418 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-21 00:05 | 2024-01-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1881 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-21 20:00 | 2024-01-22 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-1267 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main Line | 2024-01-22 07:30 | 2024-01-22 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-1647 | 2023-10-25 | Pending |  |  | 2 | Total Possession | Deep Lead | Great Western Loop | Main Line | 2024-01-23 06:00 | 2024-01-23 16:00 | 10:00 | Seaby St Subway Deck Subsidence Repairs | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Vernie Chong |  |  | 2023-10-12
IPR-2324-1268 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main Line | 2024-01-23 07:30 | 2024-01-23 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-1269 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Gheringhap Loop | Barwon Park Loop | Main line | 2024-01-24 07:30 | 2024-01-24 17:00 | 9:30 | Drainage Works at Inverleigh | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-419 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-01-28 00:05 | 2024-01-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-101 | 2022-12-21 | Approved |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-01-29 03:00 | 2024-01-29 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1902 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | All Tracks | 2024-01-29 21:00 | 2024-01-30 03:00 | 6:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | West Track Possession - All services Divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-16
IPR-2324-1723 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-03 06:00 | 2024-02-03 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-2324-420 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-04 00:05 | 2024-02-04 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1724 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-04 06:00 | 2024-02-04 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-2324-102 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-05 05:00 | 2024-02-05 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-103 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-08 06:00 | 2024-02-08 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-262 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-09 06:00 | 2024-02-09 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-263 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-10 06:00 | 2024-02-10 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-421 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-11 00:05 | 2024-02-11 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-264 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-11 06:00 | 2024-02-11 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-104 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-12 05:00 | 2024-02-12 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-265 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-12 06:00 | 2024-02-12 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-266 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-13 06:00 | 2024-02-13 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-267 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-14 06:00 | 2024-02-14 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-268 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-15 06:00 | 2024-02-15 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-269 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-16 06:00 | 2024-02-16 18:00 | 12:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track Continuous for 8 days | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-105 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-16 20:00 | 2024-02-17 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1725 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-17 06:00 | 2024-02-17 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-2324-314 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-17 20:00 | 2024-02-18 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-422 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-18 00:05 | 2024-02-18 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1726 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-18 06:00 | 2024-02-18 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-2324-90 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-02-19 05:00 | 2024-02-19 17:00 | 12:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-270 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-19 20:00 | 2024-02-20 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-271 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-20 20:00 | 2024-02-21 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-272 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-21 20:00 | 2024-02-22 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-273 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-22 20:00 | 2024-02-23 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-274 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-23 20:00 | 2024-02-24 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-315 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-24 20:00 | 2024-02-25 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-423 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-02-25 00:05 | 2024-02-25 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-91 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | West Track | 2024-02-26 18:00 | 2024-02-28 18:00 | 48:00 | Inland Rail - Wangaratta Station - No Access to Platform | North - South | Albury to Somerton | ​​SLR on East Track - Passenger Trains won't have access to Wangaratta Platform for 48hrs after 60hr Vic Shut | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-275 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-26 20:00 | 2024-02-27 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-276 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-27 20:00 | 2024-02-28 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-277 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-02-28 07:00 | 2024-02-28 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-92 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-02-29 07:00 | 2024-02-29 17:00 | 10:00 | Inland Rail - Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-278 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-02-29 20:00 | 2024-03-01 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-353 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-01 07:00 | 2024-03-01 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on New West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-279 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-01 20:00 | 2024-03-02 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-316 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-02 20:00 | 2024-03-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-424 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-03 00:05 | 2024-03-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-93 | 2022-10-12 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-03-04 03:00 | 2024-03-04 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-354 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-04 07:00 | 2024-03-04 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-280 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-04 20:00 | 2024-03-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-355 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-05 07:00 | 2024-03-05 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-281 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-05 20:00 | 2024-03-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-356 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-06 07:00 | 2024-03-06 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-282 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-06 20:00 | 2024-03-07 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-357 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | East Track | 2024-03-07 07:00 | 2024-03-07 17:00 | 10:00 | Inland Rail Glenrowan | North - South | Albury to Somerton | ​​SLR on West Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-283 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-07 20:00 | 2024-03-08 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-358 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wangaratta | Benalla | West Track | 2024-03-08 07:00 | 2024-03-08 17:00 | 10:00 | Inland Rail Genrowan | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-284 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-08 20:00 | 2024-03-09 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-86 | 2022-12-21 | Supported |  |  | 1 | Total Possession | Albury | Tottenham | All Tracks | 2024-03-09 06:00 | 2024-03-11 18:00 | 60:00 | NE Victoria 'Super' Shut | North - South | Albury to Somerton;#Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​NE Victoria 60hr Possession | Bryce Gore | Warren Williams |  |  | 2022-10-11
IPR-1815 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-09 07:00 | 2024-03-09 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1899 | 2023-11-24 | Pending |  |  | 3 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 13:00 | 2024-03-09 15:00 | 2:00 | WGTP | East - West | Melbourne Metro | No Adhocs - Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-1900 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 15:00 | 2024-03-10 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-2324-317 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-09 20:00 | 2024-03-10 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-425 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-10 00:05 | 2024-03-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1901 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-11 | 2024-03-11 06:00 | 6:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-2324-359 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-11 07:00 | 2024-03-11 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1729 | 2023-10-10 | Approved |  |  | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-03-11 18:00 | 2024-03-15 18:00 | 96:00 | Bridge Deck Replacements | North - South | Benalla to Oakland Line | Total 6 Day Shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1753 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-03-11 18:00 | 2024-03-13 18:00 | 48:00 | Inland Rail - Wangaratta Station | North - South | Albury to Somerton | Nil Access to Wangaratta Passenger Platform - All services divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-02
IPR-2324-285 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-11 20:00 | 2024-03-12 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-360 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-12 07:00 | 2024-03-12 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-286 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-12 20:00 | 2024-03-13 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-361 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-13 07:00 | 2024-03-13 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-287 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-13 20:00 | 2024-03-14 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-362 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-14 07:00 | 2024-03-14 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-288 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-14 20:00 | 2024-03-15 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-363 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Chiltern | Wangaratta | East Track | 2024-03-15 07:00 | 2024-03-15 17:00 | 10:00 | Inland Rail - Wangaratta Station - New East Track Construct & Commission | North - South | Albury to Somerton | ​​SLR on New West Track 0700 - 1700 Mon - Friday - Nil Impact to Passenger services | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-289 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-15 20:00 | 2024-03-16 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-318 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-16 20:00 | 2024-03-17 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1442 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Westmere Loop | Tatyoon Loop | Mainline | 2024-03-16 22:00 | 2024-03-17 08:00 | 10:00 | Glenelg Why LX Renewal 213.384km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-426 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-17 00:05 | 2024-03-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1233 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-18 07:00 | 2024-03-18 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1816 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-18 07:00 | 2024-03-18 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-290 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-18 20:00 | 2024-03-19 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-94 | 2022-12-21 | Pending |  |  | 6 | Advice Only | Chiltern | Wangaratta |  | 2024-03-19 07:00 | 2024-06-20 17:00 | 2242:00 | Inland Rail - Wangaratta Station Works | North - South | Albury to Somerton | ​​Passenger Trains run on New East Track to access existing Platform - Freight can use either Tracks | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1234 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main line | 2024-03-19 07:00 | 2024-03-19 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1443 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Tatyoon Loop | Maroona Loop | Mainline | 2024-03-19 07:00 | 2024-03-19 17:00 | 10:00 | Helendite Rd LX Renewal 244.094km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-294 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-19 20:00 | 2024-03-20 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1235 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main line | 2024-03-20 07:00 | 2024-03-20 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-295 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-20 20:00 | 2024-03-21 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1446 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Lubeck | Murtoa Loop | Mainline | 2024-03-21 03:30 | 2024-03-21 13:30 | 10:00 | Murtoa-Donald Rd LX Upgrade 299.010km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1236 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-21 07:00 | 2024-03-21 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-296 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-21 20:00 | 2024-03-22 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1237 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-22 07:00 | 2024-03-22 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-297 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-22 20:00 | 2024-03-23 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1238 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-23 07:00 | 2024-03-23 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-319 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-23 20:00 | 2024-03-24 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1444 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Maroona Loop | Pyrenees | Mainline | 2024-03-23 21:30 | 2024-03-24 07:30 | 10:00 | Walkers Rd LX Renewal 266.728km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1445 | 2023-09-25 | Cancelled |  |  | 2 | Total Possession | Great Western Loop | Deep Lead | Mainline | 2024-03-23 23:00 | 2024-03-24 09:00 | 10:00 | Seaby Rd LX Renewal 241.354km | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-427 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-24 00:05 | 2024-03-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-1239 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-24 07:00 | 2024-03-24 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1240 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-25 07:00 | 2024-03-25 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-291 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-25 20:00 | 2024-03-26 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1447 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Murtoa Loop | Horsham | Mainline | 2024-03-26 06:00 | 2024-03-26 16:00 | 10:00 | North Jung Rd 308.777 LX Upgrade | East - West | Tottenham to Serviceton | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1241 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-26 07:00 | 2024-03-26 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1270 | 2023-07-24 | Approved |  |  | 3 | Window Possession | Lillimur | Kaniva Loop | Main Line | 2024-03-26 07:00 | 2024-03-26 17:00 | 10:00 | Removal of redundant turnout at Kaniva Down end (A4386D) | East - West | Tottenham to Serviceton | ​​No Adhocs | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-298 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-26 20:00 | 2024-03-27 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1242 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-27 07:00 | 2024-03-27 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-299 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-27 20:00 | 2024-03-28 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-1448 | 2023-09-25 | Pending |  |  | 2 | Total Possession | Pimpinio Loop | Dimboola | Mainline | 2024-03-28 04:00 | 2024-03-28 13:00 | 9:00 | Cemetery Rd LX Upgrade 363.139km | East - West | Tottenham to Serviceton | ​No Train Period - Was 29-30 March | Bryce Gore | Ryan Sliwinski |  |  | 2023-09-01
IPR-2324-1243 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-28 07:00 | 2024-03-28 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-300 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-28 20:00 | 2024-03-29 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-301 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-29 20:00 | 2024-03-30 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-320 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-03-30 20:00 | 2024-03-31 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-428 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-03-31 00:05 | 2024-03-31 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1971 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-04-01 03:00 | 2024-04-01 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2324-292 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-01 20:00 | 2024-04-02 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-302 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-02 20:00 | 2024-04-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-306 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-02 20:00 | 2024-04-03 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-303 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-03 20:00 | 2024-04-04 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-307 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-03 20:00 | 2024-04-04 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-304 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-04 20:00 | 2024-04-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-308 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-04 20:00 | 2024-04-05 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-305 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-05 20:00 | 2024-04-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-309 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-05 20:00 | 2024-04-06 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-321 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-06 20:00 | 2024-04-07 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-429 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-07 00:05 | 2024-04-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-293 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-08 20:00 | 2024-04-09 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-310 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-09 20:00 | 2024-04-10 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-311 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-10 20:00 | 2024-04-11 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-312 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-11 20:00 | 2024-04-12 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2324-313 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-12 20:00 | 2024-04-13 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-322 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-13 20:00 | 2024-04-14 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-430 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-14 00:05 | 2024-04-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-323 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-04-15 20:00 | 2024-04-16 05:00 | 9:00 | Inland Rail - Seymour Avenal Rd Western Abutment Demolition | North - South | Albury to Somerton | ​​SLR on East Track 2000 - 0500 each night Monday - Saturday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-106 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-16 07:00 | 2024-04-16 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-324 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-17 07:00 | 2024-04-17 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-325 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-18 07:00 | 2024-04-18 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-326 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-19 07:00 | 2024-04-19 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1265 | 2023-07-24 | Approved |  |  | 2 | Total Possession | Glen Thompson | Grampians Loop | Portland Line | 2024-04-20 07:00 | 2024-04-20 17:00 | 10:00 | LX Renewal 294.806km | East - West | Portland Line | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-431 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-21 00:05 | 2024-04-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-327 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-1266 | 2023-07-24 | Approved |  |  | 2 | Total Possession | Maroona Loop | Portland | Portland Line | 2024-04-22 07:00 | 2024-04-22 17:00 | 10:00 | LX Renewal | East - West | Portland Line | ​No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-07-17
IPR-2324-333 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-23 07:00 | 2024-04-23 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-334 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-24 07:00 | 2024-04-24 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-335 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-25 07:00 | 2024-04-25 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-336 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-26 07:00 | 2024-04-26 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-432 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-04-28 00:05 | 2024-04-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-328 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-29 07:00 | 2024-04-29 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-337 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-04-30 07:00 | 2024-04-30 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-338 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-01 07:00 | 2024-05-01 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-339 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-02 07:00 | 2024-05-02 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-340 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-03 07:00 | 2024-05-03 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-433 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-05 00:05 | 2024-05-05 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-329 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-06 07:00 | 2024-05-06 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-341 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-07 07:00 | 2024-05-07 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-342 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-08 07:00 | 2024-05-08 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-343 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-09 07:00 | 2024-05-09 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-344 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-10 07:00 | 2024-05-10 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-434 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-12 00:05 | 2024-05-12 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-330 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-13 07:00 | 2024-05-13 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-345 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-14 07:00 | 2024-05-14 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-346 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-15 07:00 | 2024-05-15 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-347 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-16 07:00 | 2024-05-16 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-348 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-17 07:00 | 2024-05-17 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-435 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-19 00:05 | 2024-05-19 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-331 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-20 07:00 | 2024-05-20 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-349 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-21 07:00 | 2024-05-21 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-350 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-22 07:00 | 2024-05-22 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-351 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-23 07:00 | 2024-05-23 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-352 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-24 07:00 | 2024-05-24 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-436 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-05-26 00:05 | 2024-05-26 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-332 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-05-27 07:00 | 2024-05-27 17:00 | 10:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Hany Khial |  |  | 2022-10-12
IPR-2324-437 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-02 00:05 | 2024-06-02 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-438 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-09 00:05 | 2024-06-09 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-439 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-16 00:05 | 2024-06-16 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-440 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-23 00:05 | 2024-06-23 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2324-441 | 2022-12-21 | Approved | 0045-2023 | 2022-11-23 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-30 00:05 | 2024-06-30 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1972 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-08-05 03:00 | 2024-08-05 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1894 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Manor Loop | Serviceton | All Tracks | 2024-08-24 06:00 | 2024-08-26 18:00 | 60:00 | Major Maintenance | East - West | Tottenham to Serviceton | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1973 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-09-09 03:00 | 2024-09-09 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1811 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1813 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Somerton (Exclusive) to Tottenham (Exclusive) | AO | 2023-11-10
IPR-1812 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1814 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Somerton (Exclusive) | AO | 2023-11-10

## New Requests (Last 30 Days)
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Possession Limits | Safeworking Requirements | Date Submitted
IPR-2324-1748 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-25 08:00 | 2023-11-25 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-1754 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-26 06:00 | 2023-11-26 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1749 | 2023-11-24 | Approved | 1485-2023 | 2023-11-03 | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2023-11-26 09:00 | 2023-11-26 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-10-31
IPR-2324-1755 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-27 06:00 | 2023-11-27 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1756 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-28 06:00 | 2023-11-28 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1757 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Cootamundra | Harden | Up and Down Main | 2023-11-29 06:00 | 2023-11-29 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Cootamundra CA08 to Harden HN34 and Harden HN29 to Cootamundra CA01 |  | 2023-11-02
IPR-2324-1758 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-11-30 06:00 | 2023-11-30 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1759 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-01 06:00 | 2023-12-01 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1760 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-02 06:00 | 2023-12-02 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-1982 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-02 21:30 | 2023-12-03 05:30 | 8:00 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-2324-1761 | 2023-11-09 | Approved | 1507-2023 | 2023-11-10 | 3 | Window Possession | Junee | Cootamundra | Up and Down Main | 2023-12-03 06:00 | 2023-12-03 18:30 | 12:30 | Undercutting | North - South | Goulburn to Junee | No impact to mandatory services. Ad hocs with 3 days notice. | Andrew Duncan | David Izzard | Junee JE02 to Cootamundra CA78 and Cootamundra CA75 to Junee JE01 |  | 2023-11-02
IPR-2324-1733 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 06:00 | 2023-12-04 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1734 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 10:30 | 2023-12-04 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1735 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-04 14:00 | 2023-12-04 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1736 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 06:00 | 2023-12-05 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1737 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 10:30 | 2023-12-05 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1738 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-05 13:00 | 2023-12-05 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1716 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-06 07:00 | 2023-12-06 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1717 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-07 07:00 | 2023-12-07 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1731 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-08 07:00 | 2023-12-08 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1983 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Newport | Manor Loop | Mainline | 2023-12-09 00:01 | 2023-12-09 07:30 | 7:29 | Laverton Signal Commissioning and Power Supply Changeover | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Chan Sarai |  |  | 2023-11-24
IPR-1824 | 2023-10-05 | Approved | 1516-2023 | 2023-11-10 | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2023-12-09 06:00 | 2023-12-09 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-05
IPR-2324-1721 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-09 07:00 | 2023-12-09 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1719 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-10 07:00 | 2023-12-10 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1739 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 06:00 | 2023-12-11 08:30 | 2:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1720 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-11 07:00 | 2023-12-11 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1740 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 10:30 | 2023-12-11 12:30 | 2:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1741 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Up Main, Up Refuge | 2023-12-11 14:00 | 2023-12-11 17:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 222.8 at 222.740km Goulburn to Signal G 2 at 232.032km at Joppa Junction | TOA | 2023-10-24
IPR-2324-1762 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-12 03:30 | 2023-12-12 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1742 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 06:00 | 2023-12-12 09:30 | 3:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1722 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-12 07:00 | 2023-12-12 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1743 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 10:30 | 2023-12-12 12:00 | 1:30 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1744 | 2023-11-01 | Approved | 1475-2023 | 2023-11-17 | 3 | Window Possession | Goulburn | Goulburn | Down Main | 2023-12-12 13:00 | 2023-12-12 16:00 | 3:00 | Ballast Undercutting | North - South | Goulburn to Junee | MTP Services as planned, Ad Hoc Service Restriction. | Andrew Duncan | Tofiq Ahmed | Signal G 81 at 222.750km Goulburn to Signal G 15 at 229.200km Joppa Junction | TOA | 2023-10-24
IPR-2324-1763 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-13 03:30 | 2023-12-13 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1818 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-13 07:00 | 2023-12-13 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1897 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-13 14:00 | 2023-12-13 17:00 | 3:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-2324-1764 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-14 03:30 | 2023-12-14 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1819 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-14 07:00 | 2023-12-14 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1765 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-15 03:30 | 2023-12-15 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1820 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-15 07:00 | 2023-12-15 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1766 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-16 03:30 | 2023-12-16 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1821 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-16 07:00 | 2023-12-16 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-1875 | 2023-11-20 | Approved | 1541-2023 | 2023-11-22 | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2023-12-16 15:00 | 2023-12-17 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-11-17
IPR-1898 | 2023-10-25 | Approved | 1305-2023 | 2023-10-25 | 2 | Total Possession | Mile End | Islington | Mainline | 2023-12-16 15:00 | 2023-12-16 17:00 | 2:00 | GREP Project Ped Crossing Commissioning | East - West | Serviceton to Islington (SA) | ​No Train Period - Project requested extra window | Bryce Gore | Darren Schulz |  |  | 2023-10-25
IPR-1822 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-17 07:00 | 2023-12-17 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1768 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-18 03:30 | 2023-12-18 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-1823 | 2023-09-25 | Approved | 1532-2023 | 2023-11-17 | 2 | Total Possession | Wangaratta | Wangaratta | East Track | 2023-12-18 07:00 | 2023-12-18 18:00 | 11:00 | Inland Rail | North - South | Albury to Somerton | All services divert to West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-10-25
IPR-2324-1767 | 2023-11-09 | Approved | 1510-2023 | 2023-11-17 | 3 | Window Possession | Cooks River | Port Botany Yard | Down Botany and Roads 3 and 4 | 2023-12-19 03:30 | 2023-12-19 05:00 | 1:30 | BRD | North - South | Port Botany to Marrickville Jct | Mandatory trains as planned. No ad-hocs through window. | Andrew Duncan | Jensen Kelly | CR734G to BY13-BY15 |  | 2023-11-08
IPR-2324-1750 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 08:00 | 2023-12-27 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1751 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-27 14:10 | 2023-12-27 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1903 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 06:00 | 2023-12-28 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1906 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 08:00 | 2023-12-28 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1908 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-28 14:10 | 2023-12-28 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1904 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 06:00 | 2023-12-29 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1907 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 08:00 | 2023-12-29 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1909 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-29 14:10 | 2023-12-29 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1905 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 06:40 | 2023-12-30 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1910 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-30 10:30 | 2023-12-30 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1911 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2023-12-31 09:20 | 2023-12-31 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1912 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 08:00 | 2024-01-01 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1921 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-01 14:10 | 2024-01-01 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1913 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 06:00 | 2024-01-02 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1917 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 08:00 | 2024-01-02 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1922 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-02 14:10 | 2024-01-02 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1914 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 06:00 | 2024-01-03 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1918 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 08:00 | 2024-01-03 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1923 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-03 14:10 | 2024-01-03 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1915 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 06:00 | 2024-01-04 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1919 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 08:00 | 2024-01-04 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1924 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-04 14:10 | 2024-01-04 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1916 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 06:00 | 2024-01-05 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1920 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 08:00 | 2024-01-05 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1925 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-05 14:10 | 2024-01-05 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1926 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 06:40 | 2024-01-06 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1928 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-06 10:30 | 2024-01-06 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1930 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-07 09:20 | 2024-01-07 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1932 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 08:00 | 2024-01-08 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1935 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-08 14:10 | 2024-01-08 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1827 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-08 14:30 | 2024-01-08 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1938 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 06:00 | 2024-01-09 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1730 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-09 07:00 | 2024-01-09 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 12th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1941 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 08:00 | 2024-01-09 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1830 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-09 14:00 | 2024-01-09 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1944 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-09 14:10 | 2024-01-09 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1947 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 06:00 | 2024-01-10 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1718 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-10 07:00 | 2024-01-10 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1950 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 08:00 | 2024-01-10 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1829 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-10 14:00 | 2024-01-10 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1953 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-10 14:10 | 2024-01-10 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1882 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-10 18:00 | 2024-01-11 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1828 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-01-11 00:30 | 2024-01-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1956 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 06:00 | 2024-01-11 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-2324-1769 | 2023-10-25 | Approved |  |  | 2 | Total Possession | Longwood | Violet Town | West Track | 2024-01-11 07:00 | 2024-01-11 17:00 | 10:00 | Inland Rail | North - South | Albury to Somerton | All services divert to East Track - Was 13th Dec 2023 | Bryce Gore | Juliet Ngbeken |  |  | 2023-10-25
IPR-1959 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 08:00 | 2024-01-11 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1896 | 2023-08-24 | Approved | 0004-2024 |  | 1 | Total Possession | Lynwood | Medway Jct | Up Main | 2024-01-11 10:00 | 2024-01-11 13:00 | 3:00 | Ultrasonic Testing via RFDV | North - South | Moss Vale to Goulburn | ​​CriticalCompliance Testing Train Alterations Required to 2128 | John Hilton | David Knee | Lynwood to Medway Junction | TOA | 2023-08-21
IPR-1962 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-11 14:10 | 2024-01-11 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1883 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-11 18:00 | 2024-01-12 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1965 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 06:00 | 2024-01-12 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1967 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 08:00 | 2024-01-12 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1969 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-12 14:10 | 2024-01-12 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1884 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-12 18:00 | 2024-01-13 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1927 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 06:40 | 2024-01-13 08:50 | 2:10 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1831 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-13 08:00 | 2024-01-13 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1929 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-13 10:30 | 2024-01-13 13:30 | 3:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1885 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Milvale | Quandialla | Main Line | 2024-01-13 18:00 | 2024-01-14 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1832 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-14 09:00 | 2024-01-14 20:30 | 11:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1931 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-14 09:20 | 2024-01-14 13:20 | 4:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1886 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-14 18:00 | 2024-01-15 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1893 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Cooks River | Cooks River | Cooks River Loop | 2024-01-15 06:00 | 2024-01-26 02:00 | 260:00 | Stabling Track Machines | North - South | Port Botany to Marrickville Jct | Cooks River Loop will be unavailable for movements or stowing wagons. | Andrew Duncan | Jensen Kelly | C/O 788A to C/O 787B points |  | 2023-11-23
IPR-1933 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 08:00 | 2024-01-15 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1936 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-15 14:10 | 2024-01-15 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1833 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-15 14:30 | 2024-01-15 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1887 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-15 18:00 | 2024-01-16 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1817 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-15 20:00 | 2024-01-16 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1939 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 06:00 | 2024-01-16 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1942 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 08:00 | 2024-01-16 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1945 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-16 14:10 | 2024-01-16 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1834 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-16 14:30 | 2024-01-16 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1888 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Quandialla | Forbes | Main Line | 2024-01-16 18:00 | 2024-01-17 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1876 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-16 20:00 | 2024-01-17 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1948 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 06:00 | 2024-01-17 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1951 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 08:00 | 2024-01-17 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1954 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-17 14:10 | 2024-01-17 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1835 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-17 14:30 | 2024-01-17 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1889 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Forbes | Parkes | Main Line | 2024-01-17 18:00 | 2024-01-18 06:00 | 12:00 | Track Resurfacing | East - West | Cootamundra West to Goobang Junction | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1877 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-17 20:00 | 2024-01-18 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1957 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 06:00 | 2024-01-18 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1960 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 08:00 | 2024-01-18 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1963 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-18 14:10 | 2024-01-18 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1890 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Gunningbland | Gunningbland | Main Line | 2024-01-18 18:00 | 2024-01-19 06:00 | 12:00 | Track Resurfacing | East - West | Goobang Junction to Broken Hill | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1878 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-18 20:00 | 2024-01-19 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1966 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 06:00 | 2024-01-19 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1968 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 08:00 | 2024-01-19 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1970 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-19 14:10 | 2024-01-19 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1891 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-19 18:00 | 2024-01-20 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1879 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-19 20:00 | 2024-01-20 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-2324-1787 | 2022-07-26 | Supported |  |  | 1 | Config 10-C | Port Botany Yard | Cooks River | All Tracks | 2024-01-19 22:00 | 2024-01-22 06:00 | 56:00 | Config-10C | North - South | Port Botany to Marrickville Jct | BRD Final CommissioningNo Access to Boral or Cooks River | Andrew Duncan | Jensen Kelly | Port Botany to Cooks River |  | 2022-06-23
IPR-1825 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-20 09:00 | 2024-01-20 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSFL and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-1892 | 2023-11-24 | Pending | 0054-2024 |  | 3 | Window Possession | Goonumbla | Tomingley West | Main Line | 2024-01-20 18:00 | 2024-01-21 06:00 | 12:00 | Track Resurfacing | East - West | Parkes to Narromine Line | Mandatory trains as planned. No ad-hocs. | Andrew Duncan | Tofiq Ahmed |  |  | 2023-11-21
IPR-1880 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-20 20:00 | 2024-01-21 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1826 | 2023-11-24 | Pending |  |  | 3 | Window Possession | Leightonfield | Leightonfield | SSFL, Loop and Sidings | 2024-01-21 09:00 | 2024-01-21 17:00 | 8:00 | Sydney Trains High Voltage work | North - South | Southern Sydney Freight Line | SSLF and ​Leightonfield Loop and Sidings will be unavailable for ad hoc traffic and crossing activities during this period to facilitate high voltage feeder maintenance by Sydney Trains. | Andrew Duncan | Winson Susanto
IPR-1881 | 2023-11-24 | Pending |  |  | 1P | Total Possession | Dynon | Moonee Ponds Jct | Mainline | 2024-01-21 20:00 | 2024-01-22 06:00 | 10:00 | WGTP Girder Lifts | East - West | Melbourne Metro | Works affect last Vline Albury service accessing Southern Cross - works to be undertaken around PN shunt movements | Bryce Gore | Chan Sarai | DYN122 to MPJ 202, 208, 210 & 214 |  | 2023-11-03
IPR-1934 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 08:00 | 2024-01-22 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1937 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-22 14:10 | 2024-01-22 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1940 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 06:00 | 2024-01-23 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1943 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 08:00 | 2024-01-23 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1946 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-23 14:10 | 2024-01-23 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1949 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 06:00 | 2024-01-24 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1952 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 08:00 | 2024-01-24 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1955 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-24 14:10 | 2024-01-24 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1958 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 06:00 | 2024-01-25 07:30 | 1:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1961 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 08:00 | 2024-01-25 10:00 | 2:00 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1964 | 2022-12-21 | Approved | 1484-2023 | 2023-11-24 | 3 | Window Possession | Cooks River | Enfield | Down Goods | 2024-01-25 14:10 | 2024-01-25 16:40 | 2:30 | Sydney Metro Southwest | North - South | Sydney MFN | Ad Hoc Restriction on Down Goods Line, ATP Possessions on Up Goods Line. Unhealthy MTP mayincur delays | John Hilton | Steven Payne | 5.700km to 12.300 km. CR711G & CR718G Signals to ED101D | TOA | 2022-12-15
IPR-1902 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | All Tracks | 2024-01-29 21:00 | 2024-01-30 03:00 | 6:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | West Track Possession - All services Divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-16
IPR-1836 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-30 14:00 | 2024-01-30 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1837 | 2023-11-24 | Approved |  |  | 3 | Window Possession | Dry Creek | Bolivar | Main Line | 2024-01-31 14:00 | 2024-01-31 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1838 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-01 00:30 | 2024-02-01 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1723 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-03 06:00 | 2024-02-03 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1839 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-03 08:00 | 2024-02-03 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1724 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-04 06:00 | 2024-02-04 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1840 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-04 09:00 | 2024-02-04 21:00 | 12:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1841 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-05 14:30 | 2024-02-05 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1842 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-06 14:00 | 2024-02-06 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1843 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-07 14:00 | 2024-02-07 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1844 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-08 00:30 | 2024-02-08 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1871 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Crystal Brook | Mainline | 2024-02-10 07:30 | 2024-02-10 13:00 | 5:30 | Drovers Rd LX Upgrade 4.722km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1865 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-10 21:00 | 2024-02-11 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1853 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-11 00:30 | 2024-02-11 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1866 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-11 23:00 | 2024-02-12 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1845 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-13 14:00 | 2024-02-13 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1846 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-14 14:00 | 2024-02-14 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1847 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-15 00:30 | 2024-02-15 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1872 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Port Germein | Port Germein | Crossing Loop | 2024-02-16 06:00 | 2024-02-16 15:30 | 9:30 | Turnout replacement at 17 Points | East - West | Crystal Brook to Spencer Junction | ​Crossing Loop - No Access to Pt Germein Siding from Adelaide End | Bryce Gore | Kristen Xiao | Pt Germein Signals 4E to 23E |  | 2023-11-21
IPR-2324-1725 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-17 06:00 | 2024-02-17 18:00 | 12:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1849 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-17 08:00 | 2024-02-17 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2324-1726 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Oaklands Branch Line | 2024-02-18 06:00 | 2024-02-18 12:00 | 6:00 | LX Upgrade | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-27
IPR-1850 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-18 09:00 | 2024-02-18 13:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1851 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-19 14:30 | 2024-02-19 19:00 | 4:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1861 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 07:00 | 2024-02-20 11:15 | 4:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1862 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Murray Bridge | Murray Bridge | Main Line | 2024-02-20 11:45 | 2024-02-20 20:30 | 8:45 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-1852 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-20 14:00 | 2024-02-20 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1848 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-21 14:00 | 2024-02-21 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1857 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-22 00:30 | 2024-02-22 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1868 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-24 21:00 | 2024-02-25 11:00 | 14:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1867 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-02-25 23:00 | 2024-02-26 09:00 | 10:00 | Underbridge Replacement 157.256km | East - West | Dry Creek to Crystal Brook | No Train Period. | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1854 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-27 14:00 | 2024-02-27 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1869 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-27 22:00 | 2024-02-28 09:00 | 11:00 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1856 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-28 14:00 | 2024-02-28 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1870 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Coonamia | Coonamia | Mainline | 2024-02-28 21:30 | 2024-02-29 08:00 | 10:30 | Coonamia Culvert Replacement 4.171km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Kristen Xiao |  |  | 2023-11-21
IPR-1855 | 2023-11-24 | Approved |  |  | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-02-29 00:30 | 2024-02-29 06:30 | 6:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-1863 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-04 08:45 | 2024-03-04 19:00 | 10:15 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-1770 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-04 16:00 | 2024-03-04 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1864 | 2023-11-24 | Pending |  |  | 3 | Total Possession | Monarto South | Monarto South | Crossing Loop | 2024-03-05 07:00 | 2024-03-05 19:00 | 12:00 | Turnout renewal 20pts | East - West | Serviceton to Islington (SA) | No Adhocs | Bryce Gore | Bonnar Mahains |  |  | 2023-11-21
IPR-2324-1789 | 2023-11-15 | Supported |  |  | 1 | Total Possession | Forbes | Goobang Jct | All Tracks | 2024-03-09 06:00 | 2024-03-12 22:00 | 88:00 | Inland Rail Construction | North - South | Cootamundra West to Goobang Junction | ​Extended Possession for Inland Rail Construction Activities | Andrew Duncan | Chris Fay | Forbes (DYLB) to Goobang Junction (End TOW) | TOA | 2022-09-19
IPR-1815 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-09 07:00 | 2024-03-09 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-1899 | 2023-11-24 | Pending |  |  | 3 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 13:00 | 2024-03-09 15:00 | 2:00 | WGTP | East - West | Melbourne Metro | No Adhocs - Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-1900 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-09 15:00 | 2024-03-10 15:00 | 24:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-1901 | 2023-11-24 | Pending |  |  | 2 | Total Possession | South Dynon | Appleton Dock | Port Of Melbourne - All Sidings | 2024-03-11 | 2024-03-11 06:00 | 6:00 | WGTP | East - West | Melbourne Metro | No Access to Port Of Melbourne - All Sidings | Bryce Gore | Chan Sarai |  |  | 2023-10-30
IPR-2324-1771 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-11 16:00 | 2024-03-11 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1729 | 2023-10-10 | Approved |  |  | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-03-11 18:00 | 2024-03-15 18:00 | 96:00 | Bridge Deck Replacements | North - South | Benalla to Oakland Line | Total 6 Day Shut | Bryce Gore | Ryan Sliwinski |  |  | 2023-10-09
IPR-2324-1753 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Chiltern | Benalla | West Track | 2024-03-11 18:00 | 2024-03-13 18:00 | 48:00 | Inland Rail - Wangaratta Station | North - South | Albury to Somerton | Nil Access to Wangaratta Passenger Platform - All services divert via East Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-02
IPR-1974 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-12 12:45 | 2024-03-13 01:45 | 13:00 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1975 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-03-13 10:45 | 2024-03-13 15:40 | 4:55 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1816 | 2023-07-24 | Approved |  |  | 3 | Window Possession | South Dynon | West Footscray | Main Line | 2024-03-18 07:00 | 2024-03-18 17:00 | 10:00 | Sims St Bridge Works | East - West | Melbourne Metro | ​No Adhoc Traffic | Bryce Gore | Ryan Sliwinski |  |  | 2023-06-29
IPR-2324-1772 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-18 16:00 | 2024-03-18 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1978 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 | 2024-03-20 12:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1979 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-20 19:00 | 2024-03-21 01:00 | 6:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | . | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1980 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-22 03:00 | 2024-03-22 15:00 | 12:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1981 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-03-23 03:00 | 2024-03-23 13:00 | 10:00 | Crystal Brook Bridge Replacement | East - West | Broken Hill to Crystal Brook | Min 12hrs req | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1976 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-24 16:00 | 2024-03-25 04:00 | 12:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-2324-1773 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-03-25 16:00 | 2024-03-25 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1977 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coonamia | Port Germein | Mainline | 2024-03-25 21:00 | 2024-03-26 04:00 | 7:00 | Weeroona Bridge Replacement 14.156km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Tayla Storr |  |  | 2023-11-23
IPR-1971 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-04-01 03:00 | 2024-04-01 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2324-1775 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-08 16:00 | 2024-04-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1776 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-15 16:00 | 2024-04-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1777 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-22 16:00 | 2024-04-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1858 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-23 12:00 | 2024-04-23 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1859 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-27 11:00 | 2024-04-27 23:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1873 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-28 16:00 | 2024-04-29 04:00 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-1778 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-04-29 16:00 | 2024-04-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1860 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mile End | Islington | Main Line | 2024-04-30 12:00 | 2024-04-30 22:00 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2324-1779 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-06 16:00 | 2024-05-06 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1780 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-13 16:00 | 2024-05-13 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1781 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-20 16:00 | 2024-05-20 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1782 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-05-27 16:00 | 2024-05-27 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1783 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-03 16:00 | 2024-06-03 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1784 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-10 16:00 | 2024-06-10 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1785 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-17 16:00 | 2024-06-17 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2324-1786 | 2023-08-24 | Supported | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-24 16:00 | 2024-06-24 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-1790 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2024-07-27 02:00 | 2024-07-29 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1797 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-08-03 08:00 | 2024-08-04 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1972 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-08-05 03:00 | 2024-08-05 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1794 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-08-07 06:00 | 2024-08-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1894 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Manor Loop | Serviceton | All Tracks | 2024-08-24 06:00 | 2024-08-26 18:00 | 60:00 | Major Maintenance | East - West | Tottenham to Serviceton | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1895 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Serviceton | Belair | All Tracks | 2024-08-24 09:00 | 2024-08-26 21:00 | 60:00 | Major Maintenance | East - West | Serviceton to Islington (SA) | ​​Major Maintenance being conducted. Reconditioning Work in Sleeps Hill Tunnel. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1874 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Mile End | Islington | Main Line | 2024-08-24 13:00 | 2024-08-27 06:00 | 65:00 | TRJ Project Commissioning | East - West | Serviceton to Islington (SA) | ​Torrens Junction Signalling Upgrade Project - Arrangements to be made to operate Sunday Ghan Service 1AD8 | Bryce Gore | Michael Iannella | Islington Signal 33 to Mile End Signal 44 |  | 2023-11-21
IPR-1973 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-09-09 03:00 | 2024-09-09 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-1801 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-09-20 22:30 | 2024-09-23 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1807 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2024-09-21 00:01 | 2024-09-23 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1808 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1811 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1813 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2024-09-21 06:00 | 2024-09-23 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Shut |  | Warren Williams | Somerton (Exclusive) to Tottenham (Exclusive) | AO | 2023-11-10
IPR-1798 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2024-11-02 08:00 | 2024-11-03 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1792 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2024-11-09 02:00 | 2024-11-11 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1802 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2024-11-22 22:30 | 2024-11-25 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1806 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2024-11-23 06:00 | 2024-11-24 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1795 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-12-07 06:00 | 2024-12-08 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1799 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-02-08 08:00 | 2025-02-09 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1791 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2025-02-15 02:00 | 2025-02-17 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15
IPR-1803 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-03-28 22:30 | 2025-03-31 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1810 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2025-03-29 00:01 | 2025-03-31 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. |  | Warren Williams | Moss Vale Yard (Inclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-1809 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 |  | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1812 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1814 | 2023-11-24 | Supported |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2025-03-29 06:00 | 2025-03-31 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Possession |  | Warren Williams | Somerton (Exclusive) | AO | 2023-11-10
IPR-1796 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2025-04-12 06:00 | 2025-04-13 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN |  | Warren Williams |  | LPA | 2023-11-10
IPR-1804 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Jct | SSFL, Up Main, Down Main | 2025-05-02 22:30 | 2025-05-05 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. |  | Warren Williams |  | LPA | 2023-11-10
IPR-1805 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Jct | Cootamundra | All Lines | 2025-05-03 06:00 | 2025-05-04 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard |  | Warren Williams |  | LPA | 2023-11-10
IPR-1800 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Acacia Ridge | All Lines | 2025-05-17 08:00 | 2025-05-18 20:00 | 36:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains.Possession Stages & Times to be refined |  | Warren Williams |  | LPA | 2023-11-11
IPR-1793 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2025-06-28 02:00 | 2025-06-30 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open |  | Warren Williams |  | LPA | 2023-11-15