## HUNTERVALLEY
HUNTER VALLEY POSSESSION PROGRAMME NOVEMBER 2023 TO DECEMBER 2024 - OCTOBER 2023 RELEASE
Region | Network | Status | Location | Work Description | Track | Start | Finish | Hours | ID | Impact | Impact Level
NOVEMBER 2023
CNW | ARTC HV | Approved | Narrabri Coal to Narrabri Junction | N2TLU Construction |  | 2023-11-01 10:00 | 2023-11-01 16:00 | 6 | TAA 1183 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Morandoo | Switch Upgrades | Morandoo 1 Road, Morandoo 2 Road | 2023-11-02 06:00 | 2023-11-02 18:00 | 12 | TMP 40 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Singleton to Camberwell Junction | Turnout Maintenance | Up Main, Up Relief, Down Main | 2023-11-02 08:15 | 2023-11-02 09:15 | 1 | TAA 1375 | 6 | 6: Speno ¦ Info Only
CNW | ARTC HV | Approved | Narrabri Coal to Narrabri Junction | N2TLU Construction |  | 2023-11-02 10:00 | 2023-11-02 16:00 | 6 | TAA 1183 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Morandoo | Switch Upgrades | Morandoo 1 Road, Morandoo 2 Road, Morandoo Road 3, Morandoo 9 Road, Morandoo 11 Road, Morandoo 13 Road | 2023-11-03 06:00 | 2023-11-03 18:00 | 12 | TMP 40 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-03 08:00 | 2023-11-03 16:00 | 8 | TAA 1319 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-04 06:00 | 2023-11-04 14:00 | 8 | TAA 1319 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Muswellbrook to Bengalla | Track Walk | Down Main, Up Main, Single Main, Single North Main | 2023-11-07 08:30 | 2023-11-07 09:30 | 1 | TAA 1328 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-07 10:00 | 2023-11-07 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2023-11-07 20:00 | 2023-11-08 04:00 | 8 | TAA 1348 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | East Maitland to Farley Junction | Track Walk | Down Coal Road, Down North Main, Up Coal Road, Up North Main | 2023-11-08 09:30 | 2023-11-08 10:30 | 1 | TAA 1334 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-08 10:00 | 2023-11-08 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Muswellbrook | Rail Grinding |  | 2023-11-08 20:00 | 2023-11-09 04:00 | 8 | TAA 1349 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-09 10:00 | 2023-11-09 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Allandale to Camberwell Junction | Rail Grinding | Up Main North | 2023-11-09 20:00 | 2023-11-10 04:00 | 8 | TAA 1368 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-10 08:00 | 2023-11-10 16:00 | 8 | TAA 1320 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-10 10:00 | 2023-11-10 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | High Street to Branxton | Rail Grinding |  | 2023-11-10 20:00 | 2023-11-11 04:00 | 8 | TAA 1369 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-11 10:00 | 2023-11-11 18:00 | 8 | TAA 1320 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-11 10:00 | 2023-11-11 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | East Maitland to Farley | Special Event - REMEMBRANCE DAY |  | 2023-11-11 10:30 | 2023-11-11 11:30 | 1 | SPECIAL EVENT | 6 | 6: Special Events ¦ Info Only
1 2 3 | ARTC HV | Approved | Grasstree to Bengalla / Aberdeen | Special Event - REMEMBRANCE DAY |  | 2023-11-11 10:30 | 2023-11-11 11:30 | 1 | SPECIAL EVENT | 6 | 6: Special Events ¦ Info Only
3 | ARTC HV | Approved | Braefield to Bells Gate | Special Event - REMEMBRANCE DAY |  | 2023-11-11 10:30 | 2023-11-11 11:30 | 1 | SPECIAL EVENT | 6 | 6: Special Events ¦ Info Only
CNW | ARTC HV | Approved | Narromine | Special Event - REMEMBRANCE DAY |  | 2023-11-11 10:30 | 2023-11-11 11:30 | 1 | SPECIAL EVENT | 6 | 6: Special Events ¦ Info Only
1 | ARTC HV | Approved | Sandgate to Maitland | Rail Grinding |  | 2023-11-11 20:00 | 2023-11-12 04:00 | 8 | TAA 1370 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-12 10:00 | 2023-11-12 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-13 10:00 | 2023-11-13 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-14 10:00 | 2023-11-14 16:00 | 6 | TAA 1289 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Branxton | Turnout Maintenance | Down Main North, Up Main North, Up Relief | 2023-11-14 12:30 | 2023-11-14 13:30 | 1 | TAA 1376 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
1 | ARTC HV | Approved | Allandale | Turnout Maintenance | Down Main North, Up Main North | 2023-11-16 07:30 | 2023-11-16 08:30 | 1 | TAA 1377 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
1 | ARTC HV | Cancelled | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2023-11-16 07:30 | 2023-11-16 11:30 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-17 08:00 | 2023-11-17 16:00 | 8 | TAA 1412 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo Fletchers to Ballimore | Unload Sleeper Train |  | 2023-11-18 10:00 | 2023-11-18 18:00 | 8 | TAA 1412 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Cancelled | Hanbury Jct to Maitland Coal Roads | Resurfacing |  | 2023-11-18 20:00 | 2023-11-19 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-20 22:00 | 2023-11-24 08:00 | 82 | TAA 1350 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-11-20 22:00 | 2023-11-24 08:00 | 82 | TAA 1346 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri to Narrabri North | N2TLU Construction |  | 2023-11-20 22:00 | 2023-11-24 08:00 | 82 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 2 3 | ARTC HV | Approved | Hunter Valley Closedown | Closedown |  | 2023-11-21 06:30 | 2023-11-24 06:30 | 72 | TAA 0600 0601 | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2023-11-21 20:20 | 2023-11-22 03:30 | 7.2 | TAA 0600 0601 | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2023-11-22 07:00 | 2023-11-22 13:30 | 6.5 | TAA 0029 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2023-11-22 20:20 | 2023-11-23 03:30 | 7.2 | TAA 0600 0601 | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-25 10:00 | 2023-11-25 16:00 | 6 | TAA 1351 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-11-25 10:00 | 2023-11-25 16:00 | 6 | TAA 1347 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-26 10:00 | 2023-11-26 16:00 | 6 | TAA 1351 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-11-26 10:00 | 2023-11-26 16:00 | 6 | TAA 1347 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Waratah to Maitland | Rail Grinding | Up and Down Main | 2023-11-26 22:35 | 2023-11-27 03:00 | 4.4 | TAA 1371 | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-27 10:00 | 2023-11-27 16:00 | 6 | TAA 1351 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-11-27 10:00 | 2023-11-27 16:00 | 6 | TAA 1347 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Waratah to Maitland | Rail Grinding | Up and Down Main | 2023-11-27 22:35 | 2023-11-28 03:00 | 4.4 | TAA 1372 | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
CNW | ARTC HV | Approved | Merrygoen | Signalling Maintenance | All Lines | 2023-11-28 07:00 | 2023-11-28 13:30 | 6.5 | TAA 0030 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-11-28 10:00 | 2023-11-28 16:00 | 6 | TAA 1347 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-11-28 10:00 | 2023-11-28 16:00 | 6 | TAA 1351 | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Nundah to Padulla (3rd Road) | Rail Grinding |  | 2023-11-28 20:00 | 2023-11-29 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Branxton (3rd Road) | Rail Grinding |  | 2023-11-28 20:00 | 2023-11-29 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Branxton (3rd Road) | Rail Grinding |  | 2023-11-29 20:00 | 2023-11-30 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Greta to Farley (3rd Road) | Rail Grinding |  | 2023-11-29 20:00 | 2023-11-30 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
DECEMBER 2023
1 | ARTC HV | Approved | Branxton to Whittingham | Unload Railset | Up Main, Up Relief | 2023-12-02 07:00 | 2023-12-02 12:30 | 5.5 | TAA 1005 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
CNW | ARTC HV | Approved | Minore to Troy Junction | Dubbo MC Commissioning Works | Main Line, Triangle Loop, Branch Line | 2023-12-02 08:00 | 2023-12-04 08:00 | 48 | TAA 1417 | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Branxton to Whittingham | Unload Railset | Up North Main, Up Relief | 2023-12-03 07:00 | 2023-12-03 12:30 | 5.5 | TAA 1006 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
1 | ARTC HV | Approved | Muswellbrook to Bengalla | Track Walk | Down Main, Up Main, Single Main, Single North Main | 2023-12-05 07:40 | 2023-12-05 08:40 | 1 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-05 10:00 | 2023-12-05 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-05 10:00 | 2023-12-05 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | East Maitland to Farley Junction | Track Walk | Down Coal Road, Down North Main, Up Coal Road, Up North Main | 2023-12-06 07:40 | 2023-12-06 08:40 | 1 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-06 10:00 | 2023-12-06 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-06 10:00 | 2023-12-06 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-07 10:00 | 2023-12-07 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-07 10:00 | 2023-12-07 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-08 10:00 | 2023-12-08 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-08 10:00 | 2023-12-08 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-09 10:00 | 2023-12-09 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-09 10:00 | 2023-12-09 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-10 10:00 | 2023-12-10 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-10 10:00 | 2023-12-10 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-11 10:00 | 2023-12-11 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-11 10:00 | 2023-12-11 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri Junction | N2TLU Construction |  | 2023-12-12 10:00 | 2023-12-12 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Turrawan | N2TLU Construction |  | 2023-12-12 10:00 | 2023-12-12 16:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2023-12-14 07:30 | 2023-12-14 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2023-12-20 07:00 | 2023-12-20 13:30 | 6.5 | TAA 0031 | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Loop Or Sidings Unavailable
JANUARY 2024
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Resurfacing | Single Main, Crossing Loops | 2024-01-12 18:00 | 2024-01-13 02:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Resurfacing | Single Main, Crossing Loops | 2024-01-13 18:00 | 2024-01-14 02:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Ulan | Resurfacing | Single Main, Crossing Loops | 2024-01-14 18:00 | 2024-01-15 02:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-01-15 12:00 | 2024-01-15 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
2 | ARTC HV | Approved | Muswellbrook to Ulan | Resurfacing | Single Main, Crossing Loops | 2024-01-15 18:00 | 2024-01-16 02:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-01-17 07:00 | 2024-01-17 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Drayton Jct to Muswellbrook | Unload Railset |  | 2024-01-18 07:00 | 2024-01-18 12:00 | 5 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Drayton Junction | Preventative Maintenance Possession |  | 2024-01-18 07:30 | 2024-01-18 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Port Waratah | Unload Railset |  | 2024-01-19 09:00 | 2024-01-19 13:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Port Waratah | Unload Railset |  | 2024-01-20 09:00 | 2024-01-20 13:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
FEBRUARY 2024
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-02-01 20:00 | 2024-02-02 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Hexham East | Rail Grinding | Up Coal Road, Up North Fork, Down North Fork | 2024-02-03 20:00 | 2024-02-04 00:30 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Kooragang | Rail Grinding | Up North Fork, Down North Fork, Down Branch | 2024-02-03 23:30 | 2024-02-04 04:00 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Port Waratah | Rail Grinding | Down Coal Road, Up Coal Road, Arrival Road 1, Arrival Road 3 | 2024-02-04 20:00 | 2024-02-05 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri North | N2TLU Rerailing |  | 2024-02-06 06:30 | 2024-02-09 08:00 | 73.5 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-02-06 06:30 | 2024-02-09 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-02-06 20:20 | 2024-02-07 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-02-07 20:20 | 2024-02-08 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Telarah | HM8 Ultrasonic | Up & Down Main, Up Refuge | 2024-02-10 21:00 | 2024-02-11 04:00 | 7 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Kooragang to Drayton Junction | Preventative Maintenance Possession |  | 2024-02-15 07:30 | 2024-02-15 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-02-15 12:00 | 2024-02-15 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Drayton Jct to Muswellbrook | Rail Grinding | Up Main | 2024-02-17 20:00 | 2024-02-18 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Newdell Jct to Drayton Jct | Rail Grinding | Up Main | 2024-02-17 23:00 | 2024-02-18 04:00 | 5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Camberwell Jct to Mt Owen Jct | Rail Grinding | Up Main | 2024-02-18 20:00 | 2024-02-19 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Rail Grinding | Up Main | 2024-02-18 23:00 | 2024-02-19 04:00 | 5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Branxton to Minimbah | Rail Grinding | Up Main | 2024-02-19 20:00 | 2024-02-20 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Branxton | Rail Grinding | Up North Main | 2024-02-20 20:00 | 2024-02-21 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland Yard | Rail Grinding | Up North Main, Up Coal Road | 2024-02-20 23:00 | 2024-02-21 04:00 | 5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Maitland | Rail Grinding | Up Coal Road | 2024-02-21 20:00 | 2024-02-22 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-02-22 07:00 | 2024-02-22 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-02-29 07:30 | 2024-02-29 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
MARCH 2024
1 | ARTC HV | Approved | East Maitland to Minimbah | Rail Grinding | Down Coal Road, Down North Main | 2024-03-02 20:00 | 2024-03-03 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hexham East to Hexham West | Rail Grinding | Up Coal Road, Hexham Refuge Roads 1-5 | 2024-03-02 20:00 | 2024-03-03 02:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Branxton to Minimbah | Rail Grinding | Down Main | 2024-03-03 20:00 | 2024-03-04 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Rail Grinding | Down Main | 2024-03-04 20:00 | 2024-03-05 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Newdell Jct to Drayton Jct | Rail Grinding | Down Main | 2024-03-05 20:00 | 2024-03-06 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Yarrawa | Rail Grinding | Single Main, Crossing Loops | 2024-03-06 20:00 | 2024-03-07 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Baerami | Rail Grinding | Single Main, Crossing Loops | 2024-03-07 20:00 | 2024-03-08 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Yarrawa to Kerrabee | Rail Grinding | Single Main, Crossing Loops | 2024-03-08 20:00 | 2024-03-09 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-03-09 03:00 | 2024-03-11 01:00 | 46 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Morandoo | Rerailing / Resleepering | Morandoo Siding 1, Morandoo Siding 2, Morandoo Siding 3 | 2024-03-09 06:00 | 2024-03-10 18:00 | 36 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Telarah | Closedown |  | 2024-03-09 09:00 | 2024-03-11 01:00 | 40 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-03-13 12:00 | 2024-03-13 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
CNW | ARTC HV | Approved | Narromine South to Minore | Level Crossing Upgrade | All Lines | 2024-03-15 08:00 | 2024-03-18 18:00 | 82 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
2 | ARTC HV | Approved | Sandy Hollow to Kerrabee | Unload Railset |  | 2024-03-15 09:00 | 2024-03-15 12:00 | 3 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Drayton Jct to Muswellbrook | Unload Railset |  | 2024-03-15 13:00 | 2024-03-15 15:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Dubbo West to Troy Junction | Dubbo MC Works | All Lines | 2024-03-16 08:00 | 2024-03-18 08:00 | 48 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Unload Railset |  | 2024-03-16 09:00 | 2024-03-16 13:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Bobbiwaa | Rail Grinding | Single Main, Crossing Loops | 2024-03-16 19:00 | 2024-03-17 03:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Unload Railset |  | 2024-03-17 09:00 | 2024-03-17 13:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narrabri Coal to Bobbiwaa | Rail Grinding | Single Main, Crossing Loops | 2024-03-17 19:00 | 2024-03-18 03:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Moree South to North Star | Rail Grinding | Single Main, Crossing Loops | 2024-03-18 19:00 | 2024-03-19 03:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Moree South to North Star | Rail Grinding | Single Main, Crossing Loops | 2024-03-19 19:00 | 2024-03-20 03:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-03-20 07:00 | 2024-03-20 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Moree South to North Star | Rail Grinding | Single Main, Crossing Loops | 2024-03-20 19:00 | 2024-03-21 03:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-03-21 07:30 | 2024-03-21 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
APRIL 2024
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-04-02 07:00 | 2024-04-02 17:00 | 10 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-04-03 06:30 | 2024-04-06 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Turrawan to Narrabri North | N2TLU Rerailing |  | 2024-04-03 06:30 | 2024-04-06 08:00 | 73.5 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-04-03 06:30 | 2024-04-06 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-04-03 20:20 | 2024-04-04 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-04-04 20:20 | 2024-04-05 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Greta to Farley | Resurfacing | Up Relief | 2024-04-08 20:00 | 2024-04-09 04:00 | 8 | TAA | 4 | 4: Mandatory Trains As Planned ¦ All Services Divert
1 | ARTC HV | Approved | Whittingham to Branxton (3rd Road) | Rail Grinding | Up Relief | 2024-04-08 20:00 | 2024-04-09 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Branxton | Resurfacing | Up Relief | 2024-04-09 20:00 | 2024-04-10 04:00 | 8 | TAA | 4 | 4: Mandatory Trains As Planned ¦ All Services Divert
1 | ARTC HV | Approved | Greta to Farley (3rd Road) | Rail Grinding | Up Relief | 2024-04-09 20:00 | 2024-04-10 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-04-11 20:00 | 2024-04-12 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-04-12 12:00 | 2024-04-12 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Newcastle to Maitland Mains | Special Event |  | 2024-04-13 08:00 | 2024-04-14 18:00 | 34 | TAA | 6 | 6: Special Events ¦ Info Only
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-04-18 07:30 | 2024-04-18 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-04-24 07:00 | 2024-04-24 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | East Maitland to Farley | ANZAC Ceremony | Up & Down Main North, Up & Down Coal Road | 2024-04-25 05:30 | 2024-04-25 06:15 | 0.8 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narromine | ANZAC Ceremony | Single Main | 2024-04-25 05:30 | 2024-04-25 06:15 | 0.8 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 2 3 | ARTC HV | Approved | Antiene to Bengalla / Aberdeen | ANZAC Ceremony | Up & Down Main North | 2024-04-25 05:45 | 2024-04-25 06:30 | 0.8 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Braefield to Bells Gate | ANZAC Ceremony | Single Main | 2024-04-25 06:00 | 2024-04-25 06:30 | 0.5 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 2 3 | ARTC HV | Approved | Antiene to Bengalla / Aberdeen | ANZAC Ceremony | Up & Down Main North | 2024-04-25 10:15 | 2024-04-25 11:45 | 1.5 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | East Maitland to Farley | ANZAC Ceremony | Up & Down Main North, Up & Down Coal Road | 2024-04-25 11:00 | 2024-04-25 12:15 | 1.2 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narromine | ANZAC Ceremony | Single Main | 2024-04-25 11:00 | 2024-04-25 11:30 | 0.5 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Braefield to Bells Gate | ANZAC Ceremony | Single Main | 2024-04-25 11:20 | 2024-04-25 11:40 | 0.3 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Newcastle to Maitland Mains | Special Event |  | 2024-04-27 12:00 | 2024-04-28 02:00 | 14 | TAA | 6 | 6: Special Events ¦ Info Only
MAY 2024
1 | ARTC HV | Approved | Camberwell Jct to Mt Owen Jct | Unload Railset |  | 2024-05-04 09:00 | 2024-05-04 11:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Unload Railset |  | 2024-05-04 13:00 | 2024-05-04 17:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Togar to Parkville | Special Event | Single Main | 2024-05-05 10:15 | 2024-05-05 12:20 | 2.1 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Unload Railset |  | 2024-05-05 13:00 | 2024-05-05 17:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Camberwell Jct to Mt Owen Jct | Unload Railset |  | 2024-05-06 09:00 | 2024-05-06 11:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-05-13 12:00 | 2024-05-13 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Muswellbrook to Minimbah | Rail Grinding | Up Main | 2024-05-14 20:00 | 2024-05-15 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to East Maitland | Rail Grinding | Up North Main, Up Coal Road | 2024-05-15 20:00 | 2024-05-16 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Rail Grinding | Up Coal Road | 2024-05-16 20:00 | 2024-05-17 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-05-19 20:00 | 2024-05-20 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Turrawan to Narrabri North | N2TLU Rerailing |  | 2024-05-20 06:30 | 2024-05-24 08:00 | 97.5 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Boggabri to Narrabri Coal | Closedown |  | 2024-05-20 06:30 | 2024-05-24 06:30 | 96 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Gunnedah to Boggabri | Closedown |  | 2024-05-20 06:30 | 2024-05-24 06:30 | 96 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Closedown |  | 2024-05-20 06:30 | 2024-05-24 06:30 | 96 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-05-20 07:00 | 2024-05-20 17:00 | 10 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-05-21 06:30 | 2024-05-24 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-05-21 06:30 | 2024-05-24 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-05-21 20:20 | 2024-05-22 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-05-22 07:00 | 2024-05-22 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-05-22 20:20 | 2024-05-23 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
2 | ARTC HV | Approved | Bylong to Ulan | Rail Grinding | Single Main, Crossing Loops | 2024-05-28 05:00 | 2024-05-28 11:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Bylong to Ulan | Rail Grinding | Single Main, Crossing Loops | 2024-05-29 05:00 | 2024-05-29 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Drayton Junction | Preventative Maintenance Possession |  | 2024-05-30 07:30 | 2024-05-30 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
JUNE 2024
1 | ARTC HV | Approved | Islington Junction to Telarah | HM8 Ultrasonic | Up & Down Main | 2024-06-01 21:00 | 2024-06-02 04:00 | 7 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Whittingham to Allandale | Weighbridge Calibration | Up Relief, Up North Main, Down North Main | 2024-06-02 08:00 | 2024-06-02 14:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ Single Line Working
1 | ARTC HV | Approved | Whittingham to Allandale | Weighbridge Calibration | Up Relief, Up North Main, Down North Main | 2024-06-03 08:00 | 2024-06-03 14:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ Single Line Working
1 | ARTC HV | Approved | Whittingham to Allandale | Weighbridge Calibration | Up Relief, Up North Main, Down North Main | 2024-06-04 08:00 | 2024-06-04 14:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ Single Line Working
1 | ARTC HV | Approved | Whittingham to Allandale | Weighbridge Calibration | Up Relief, Up North Main, Down North Main | 2024-06-05 08:00 | 2024-06-05 14:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ Single Line Working
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-06-08 03:00 | 2024-06-10 23:00 | 68 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Port Waratah | Closedown |  | 2024-06-08 03:00 | 2024-06-10 23:00 | 68 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Scholey Street to Hanbury Junction | Closedown |  | 2024-06-08 03:00 | 2024-06-10 23:00 | 68 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Maitland to Telarah | Closedown |  | 2024-06-08 09:00 | 2024-06-10 23:00 | 62 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-06-11 12:00 | 2024-06-11 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Maitland to Branxton | Ballast Train Unload | Down Main, Up Main, Up Relief | 2024-06-16 07:00 | 2024-06-16 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Thornton to Maitland Coal Roads | Ballast Train Unload | Down Main, Up Main | 2024-06-18 07:00 | 2024-06-18 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-06-19 07:00 | 2024-06-19 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Branxton | Ballast Train Unload | Down Main, Up Main, Up Relief | 2024-06-20 07:00 | 2024-06-20 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-06-20 07:30 | 2024-06-20 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Branxton to Minimbah | Ballast Train Unload | Down Main, Up Main, Up Relief | 2024-06-22 07:00 | 2024-06-22 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Newcastle to Maitland Mains | Ballast Train Unload | Down Main, Up Main | 2024-06-24 07:00 | 2024-06-24 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
JULY 2024
3 | ARTC HV | Approved | Gunnedah to Boggabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-01 10:10 | 2024-07-01 14:10 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-02 06:50 | 2024-07-02 10:50 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-03 07:00 | 2024-07-03 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-07-04 07:30 | 2024-07-04 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-04 11:00 | 2024-07-04 15:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Gunnedah to Boggabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-06 10:30 | 2024-07-06 14:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Gunnedah to Boggabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-08 10:30 | 2024-07-08 14:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Boggabri to Narrabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-10 10:00 | 2024-07-10 14:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Gunnedah to Boggabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-11 10:30 | 2024-07-11 14:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Boggabri to Narrabri | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-12 11:30 | 2024-07-12 15:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-07-15 12:00 | 2024-07-15 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-16 07:40 | 2024-07-16 11:40 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-07-17 07:00 | 2024-07-17 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-07-18 07:30 | 2024-07-18 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-18 08:00 | 2024-07-18 12:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-20 07:10 | 2024-07-20 11:10 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Ballast Train Unload | Single Main, Crossing Loop | 2024-07-23 07:00 | 2024-07-23 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Drayton Jct to Muswellbrook | Ballast Train Unload | Down Main, Up Main | 2024-07-27 07:00 | 2024-07-27 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Drayton Jct to Muswellbrook | Ballast Train Unload | Down Main, Up Main | 2024-07-30 13:30 | 2024-07-30 17:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
AUGUST 2024
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-08-01 07:30 | 2024-08-01 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Mt Owen Jct to Newdell Jct | Ballast Train Unload | Down Main, Up Main | 2024-08-01 07:45 | 2024-08-01 11:45 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Camberwell Jct to Mt Owen Jct | Ballast Train Unload | Down Main, Up Main | 2024-08-03 07:00 | 2024-08-03 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Hexham East | Rail Grinding | Up Coal Road, Up North Fork, Down North Fork | 2024-08-06 20:00 | 2024-08-06 23:00 | 3 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Kooragang | Rail Grinding | Up North Fork, Down North Fork, Down Branch | 2024-08-06 22:00 | 2024-08-07 02:00 | 4 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Sandgate | Rail Grinding | Up Coal Road | 2024-08-07 20:00 | 2024-08-08 02:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-08-09 07:00 | 2024-08-09 17:00 | 10 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Elong Elong to Mendooran | Rerailing | Single Main, Crossing Loops | 2024-08-10 03:00 | 2024-08-13 03:00 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-08-10 03:00 | 2024-08-13 03:00 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Hunter Valley Mains Closedown - 4 Track | Closedown |  | 2024-08-10 03:00 | 2024-08-13 03:00 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-08-16 20:00 | 2024-08-17 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Aberdeen | Vietnam Veterans Ceremony | Single Main | 2024-08-18 15:30 | 2024-08-18 16:30 | 1 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-08-20 04:00 | 2024-08-20 10:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-08-21 04:00 | 2024-08-21 10:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-08-21 07:00 | 2024-08-21 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-08-22 04:00 | 2024-08-22 10:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Ulan | Rail Grinding |  | 2024-08-23 05:00 | 2024-08-23 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Wilpinjong | Rail Grinding |  | 2024-08-24 05:00 | 2024-08-24 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Wilpinjong | Rail Grinding |  | 2024-08-25 05:00 | 2024-08-25 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Wilpinjong | Rail Grinding |  | 2024-08-26 05:00 | 2024-08-26 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Wilpinjong | Rail Grinding |  | 2024-08-27 05:00 | 2024-08-27 12:00 | 7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-08-29 07:30 | 2024-08-29 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
SEPTEMBER 2024
2 | ARTC HV | Approved | Muswellbrook to Ulan | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-03 08:00 | 2024-09-03 12:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Ulan | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-05 07:00 | 2024-09-05 11:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Ulan | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-07 08:00 | 2024-09-07 12:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
2 | ARTC HV | Approved | Mangoola to Wilpinjong | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-10 08:00 | 2024-09-10 12:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-09-10 12:00 | 2024-09-10 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
2 | ARTC HV | Approved | Muswellbrook to Ulan | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-11 08:00 | 2024-09-11 12:00 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
2 | ARTC HV | Approved | Muswellbrook to Ulan | Ballast Train Unload | Single Main, Crossing Loop | 2024-09-13 08:30 | 2024-09-13 12:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-09-18 07:00 | 2024-09-18 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-09-26 07:30 | 2024-09-26 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Greta to Farley | Resurfacing | Up Relief | 2024-09-28 08:00 | 2024-09-28 16:00 | 8 | TAA | 4 | 4: Mandatory Trains As Planned ¦ All Services Divert
1 | ARTC HV | Approved | Whittingham to Branxton | Resurfacing | Up Relief | 2024-09-29 08:00 | 2024-09-29 16:00 | 8 | TAA | 4 | 4: Mandatory Trains As Planned ¦ All Services Divert
OCTOBER 2024
CNW | ARTC HV | Cancelled | Tamarang to Neilrex | Bridge Replacement |  | 2024-10-01 06:30 | 2024-10-05 06:30 | 96 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-10-01 06:30 | 2024-10-04 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-10-01 20:20 | 2024-10-02 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-10-02 20:20 | 2024-10-03 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-10-06 20:00 | 2024-10-07 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-10-10 12:00 | 2024-10-10 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Islington Junction to Telarah | HM8 Ultrasonic | Up & Down Main, Up Refuge | 2024-10-12 21:00 | 2024-10-13 04:00 | 7 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
3 | ARTC HV | Approved | Murrurundi to Willow Tree | Unload Railset |  | 2024-10-16 06:00 | 2024-10-16 11:00 | 5 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Branxton to Minimbah | Unload Railset | Up Main, Up Relief | 2024-10-17 07:30 | 2024-10-17 11:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-10-17 07:30 | 2024-10-17 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Maitland to Sandgate | Rail Grinding | Up Main | 2024-10-19 22:35 | 2024-10-20 03:20 | 4.8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Islington Junction | Rail Grinding | Up Main | 2024-10-20 02:00 | 2024-10-20 03:45 | 1.7 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Telarah to Thornton | Rail Grinding | Up Main, Up North Coast | 2024-10-20 22:30 | 2024-10-21 03:00 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Waratah | Unload Railset |  | 2024-10-20 23:00 | 2024-10-21 02:00 | 3 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Telarah to Mindaribba | Rail Grinding | Up and Down North Coast, Single North Coast | 2024-10-21 01:00 | 2024-10-21 03:00 | 2 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Sandgate | Rail Grinding | Down Main | 2024-10-21 21:00 | 2024-10-21 23:20 | 2.3 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Maitland | Rail Grinding | Down Main | 2024-10-21 22:30 | 2024-10-22 03:00 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Muswellbrook to Whittingham | Rail Grinding | Up Main | 2024-10-22 20:00 | 2024-10-23 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-10-23 07:00 | 2024-10-23 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Camberwell Jct to Allandale | Rail Grinding | Up North Main, Up Coal Road | 2024-10-23 20:00 | 2024-10-24 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Branxton to East Maitland | Rail Grinding | Up North Main, Up Coal Road | 2024-10-30 20:00 | 2024-10-31 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
NOVEMBER 2024
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Rail Grinding |  | 2024-11-01 17:00 | 2024-11-02 01:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-11-02 03:00 | 2024-11-04 01:00 | 46 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Maitland to Telarah | Closedown |  | 2024-11-02 09:00 | 2024-11-04 01:00 | 40 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Rail Grinding |  | 2024-11-02 17:00 | 2024-11-03 01:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Rail Grinding |  | 2024-11-03 17:00 | 2024-11-04 01:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gunnedah | Rail Grinding |  | 2024-11-04 17:00 | 2024-11-05 01:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
2 | ARTC HV | Approved | Murrumbo to Wilpinjong | Unload Railset |  | 2024-11-06 09:00 | 2024-11-06 14:00 | 5 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Camberwell Jct | Unload Railset |  | 2024-11-07 07:30 | 2024-11-07 11:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-11-07 07:30 | 2024-11-07 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
1 | ARTC HV | Approved | Maitland to Branxton | Unload Railset | Up Main, Up Relief | 2024-11-09 13:30 | 2024-11-09 17:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Farley | Remembrance Day Ceremony | Up & Down Coal Road | 2024-11-11 10:30 | 2024-11-11 11:30 | 1 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 2 3 | ARTC HV | Approved | Antiene to Bengalla / Aberdeen | Remembrance Day Ceremony | Up & Down Main North | 2024-11-11 10:30 | 2024-11-11 11:30 | 1 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Braefield to Bells Gate | Remembrance Day Ceremony | Single Main | 2024-11-11 10:30 | 2024-11-11 11:30 | 1 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Approved | Narromine | Remembrance Day Ceremony | Single Main | 2024-11-11 10:30 | 2024-11-11 11:30 | 1 | SPECIAL EVENT | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-11-11 12:00 | 2024-11-11 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
1 | ARTC HV | Approved | Nundah to Padulla (3rd Road) | Rail Grinding | Up Relief | 2024-11-13 20:00 | 2024-11-13 23:45 | 3.8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Branxton (3rd Road) | Rail Grinding | Up Relief | 2024-11-14 00:15 | 2024-11-14 04:00 | 3.8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Whittingham to Branxton (3rd Road) | Rail Grinding | Up Relief | 2024-11-14 20:00 | 2024-11-14 23:45 | 3.8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Greta to Farley (3rd Road) | Rail Grinding | Up Relief | 2024-11-15 00:15 | 2024-11-15 04:00 | 3.8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Hanbury Jct to Hexham East | Rail Grinding | Up Coal Road, Up North Fork, Down North Fork | 2024-11-15 20:00 | 2024-11-16 00:30 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Kooragang | Rail Grinding | Up North Fork, Down North Fork, Down Branch | 2024-11-15 23:30 | 2024-11-16 04:00 | 4.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Sandgate to Maitland | Rail Grinding | Up Coal Road | 2024-11-16 20:00 | 2024-11-17 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
CNW | ARTC HV | Cancelled | Tamarang to Neilrex | Bridge Replacement |  | 2024-11-19 06:30 | 2024-11-23 06:30 | 96 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 2 3 | ARTC HV | Approved | Hunter Valley Major Closedown | Closedown |  | 2024-11-19 06:30 | 2024-11-22 06:30 | 72 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-11-19 20:20 | 2024-11-20 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-11-20 07:00 | 2024-11-20 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Islington Junction to Maitland | Closedown |  | 2024-11-20 20:20 | 2024-11-21 03:30 | 7.2 | TAA | 1 | 1: All Services Cancelled ¦ Closure >10 Hours
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Resurfacing | Up & Down Coal Road, Hexham Relief Road 1-5 | 2024-11-24 20:00 | 2024-11-25 04:00 | 8 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-11-28 20:00 | 2024-11-29 02:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-11-29 20:00 | 2024-11-30 02:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Maitland to Branxton | Unload Railset |  | 2024-11-30 13:30 | 2024-11-30 17:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
3 | ARTC HV | Approved | Muswellbrook to Werris Creek | Rail Grinding |  | 2024-11-30 20:00 | 2024-12-01 02:00 | 6 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
DECEMBER 2024
1 | ARTC HV | Approved | Hanbury Jct to Maitland Coal Roads | Unload Railset |  | 2024-12-01 22:00 | 2024-12-02 03:00 | 5 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Port Waratah | Unload Railset |  | 2024-12-04 09:00 | 2024-12-04 12:00 | 3 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang | Unload Railset | Up and Down Branch | 2024-12-05 07:30 | 2024-12-05 11:30 | 4 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-12-05 07:30 | 2024-12-05 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments
3 | ARTC HV | Approved | Werris Creek to Gap Junction | Ground Frame Maintenance | Main Line, Goods Loop, Up Loop, NW Main Line, NW Loop, Line, No 1 Grain Siding, No 2 Grain Siding | 2024-12-12 12:00 | 2024-12-12 14:00 | 2 | TAA | 3 | 3: Mandatory Trains As Planned ¦ No Ad Hocs ¦ Sidings Not Available
CNW | ARTC HV | Approved | Minore to Narromine South | Signalling Maintenance | All Lines | 2024-12-18 07:00 | 2024-12-18 13:30 | 6.5 | TAA | 2 | 2: Mandatory Trains Diverted/Amended ¦ No Ad Hocs
1 | ARTC HV | Approved | Kooragang to Bengalla | Preventative Maintenance Possession |  | 2024-12-19 07:30 | 2024-12-19 11:45 | 4 | TAA | 1P | 1P: Passenger Services Cancel ¦ All Other Services Run With Amendments

## Legend (hidden)
LEGEND
Closedown of 10 or More Hours
Overnight Mains Closedown
Preventative Maintenance Possession
All Other Level 1 Impacts
Inland Rail Continuous Closedown
N2TLU Daily Possession
Special Working
Special Event
Cancelled